## Timeline (hidden)
March | April | May | June
Analytics | Onboard FL, MI, TX | Onboard & Go-Lives | Onboard & Go-Lives
Contracting | Engage Sarah's DBOS HH Team
Survey Distributed & Returned | Engage Zach Underwood (Growth Training)
IT Review | Finalize Go-Live Schedule
Build People Engagement/Comms/Training Plans | Finalize People Engagement/Comms/Training Plans
Culture Discovery | Identify, Train Ambassadors
Adoption & Behavior Maturity Matrix | Provisoning for Users | Provisoning for Users | Provisoning for Users
Build Ambassador Model | AllScripts Sunset Plan | AllScripts Sunset Plan | AllScripts Sunset Plan
| Additional BOT identification, accounts & provisoning | Additional BOT identification, accounts & provisoning | Additional BOT identification, accounts & provisoning

## Action Issue Tracker (hidden)
Commure Rollout - Action Item Tracker
| TOTAL |  | NOT STARTED | IN PROCESS | AT RISK | COMPLETE | NO LONGER NEEDED
ID | Action or Issue? | Date Ticket Submitted | Action Item / Issue | Description / Details | Owner | Date Identified | Target Date | Status | Notes
1 | Action |  | Partner Referral Lists to Commure |  | Luke/Michael |  |  | Complete | Is this still needed?
2 | Action |  | RVP Update Emails |  | Paige |  |  | No Longer Needed
3 | Action |  | User Guide for All roles | Add other role content to updated Growth Guide | Paige |  |  | Complete | Draft sent to Michael on 6/18
4 | Action |  | Distribute Q&A | Send updated Q&A to all leaders live on Commure | Paige |  |  | Complete | Review by Michael in process
5 | Action |  | DL Creation for Commure Updates |  | Paige/Sara |  |  | Not Started | Explore current options with David/Bassam
6 | Action |  | Static Doc Teams Folder | Create Teams folder & place all static files |  |  |  | Not Started
7 | Action |  | Monthly Intake Agenda for Jodie |  | Paige | 2026-06-17 |  | Complete | Paige/Jodie meeting on 6/18
8 | Action |  | Leader Launch Slides Wk 3 Revisions | Add Role Responsibility Slides | Paige | 2026-06-10 |  | Complete
9 | Action |  | New Hire Education Transition to ED Team | Begin conversation with HH Education Leaders to include Commure training in new hire onboarding | Paige/Sara | 2026-06-11 |  | Not Started
10 | Action |  | Create Partnership Assessment Survey |  | Paige | 2026-06-17 |  | Complete
11 | Action |  | Commure Contractor Requests |  | Paige |  |  | Complete | DOBs received 6/17
12 | Issue |  | Do Not Readmit | Patient on DNR not captured in Commure | Paige/Sara | 2026-06-18 |  | Complete | F/U with Dany, Bre, Piecka - are patients being flagged as Do not readmit
13 | Action |  | 20 Additional Service Accounts | . | Paige | 2026-06-17 |  | Complete | Credential email to Mustafa Commure email on 6/18
14 | Action |  | General Commure UAT Login/Password |  | Paige |  |  | No Longer Needed
15 | Issue |  | IN Ensocare Referrals | Per Lorissa email 6/18, no IN referrals in Ensocare |  |  |  | Complete
16 | Issue |  | Growth Team Auto Assign |  |  |  |  | In Process
17 | Issue |  | Contribution Margin Indicator |  |  |  |  | Complete
18 | Issue |  | CarePort Referral |  |  |  |  | Complete
19 | Issue |  | Sporadic FL Ensocare Issue | Commure not talking back to Ensocare and marking patients in needs review. |  | 2026-06-17 |  | Complete
20 | Action |  | Asana for OpEx |  | Paige | 2026-06-18 |  | No Longer Needed
21 | Action |  | Get all Job Aids from Bre/Holly/Dany/Piecka/Rakcsha |  | Paige | 2026-06-18 |  | Complete | Emails sent to request on 6/18
22 | Action |  | Q&A added to User Guide - remove job related questions |  | Paige | 2026-06-18 |  | Complete
23
24
25
26
27
28
29
30
31
32

## Date Tracking Legend (hidden)
Date Tracking - Calculation Logic
Activity | Calculation (relative to Launch / Go-Live)
Go-Live Intro Email to Leaders | 6 weeks before go-live (GL minus 42 days) - heads-up of launch and what to expect
Teams Channel Created | 4 weeks before go-live (GL minus 28 days)
Pre-Launch Mtg #1 | Thursday ~4 weeks before GL (Thu-before-GL minus 21)
Pre-Launch Mtg #2 | Thursday 3 weeks before GL
Pre-Launch Mtg #3 | Thursday 2 weeks before GL
Pre-Launch Mtg #4 (Last) | Thursday immediately before GL
Pre-Launch Momentum Survey | 2 weeks before GL (GL minus 14)
BOC/BOM/ED Email - Lunch & Materials | 2 weeks before GL (GL minus 14)
Leader Talking Points #1 | 2 weeks before GL (GL minus 14)
Email to Leaders - Go-Live Specifics | 1 week before GL (GL minus 7)
Teams Access - Leaders | 1 week before GL (GL minus 7)
Technical Training | Friday immediately before GL
Leader Talking Points #2 | Friday before GL (with Tech Training)
Teams Access - All Users | Friday before GL (day of Tech Training)
GO-LIVE | Day of go-live - both Remote and In-Person appointments
Leader Talking Points #3 | Monday of go-live week
All-Day Office Hours | Day after go-live (GL + 1)
Office Hours - Daily | Begins 2 days after GL; runs every weekday for 2 weeks
Momentum Survey #1 - Leaders | 3 days after GL
Growth & Ops Session #1 | 1 week after GL (GL + 7)
Leader Session #1 | 1 week after GL (GL + 7)
Insurance & Intake Session | 1 week after GL - first launch in state ONLY
User Survey #1 | 1 weeks after GL
Momentum Survey #2 - Leaders | 2 weeks after GL
Office Hours - 3x/Week | Starts ~Week 3 (GL + 16); runs for 2 weeks
Leader Talking Points #4 | 3 weeks after GL
User Survey #2 | 4 weeks after GL
Momentum Survey #3 - Leaders | 4 weeks after GL
Growth & Ops Session #2 | 30 days after GL
Leader Session #2 | 30 days after GL
Office Hours - 1x/Week | Starts ~Week 5 (GL + 30); runs 2 weeks; huddles transition
Leader Talking Points #5 | 5 weeks after GL
Momentum Survey #4 - Leaders | 6 weeks after GL
Intake Huddles Begin | ~Week 7 (GL + 44) - led by Intake Directors
Leader Talking Points #6 | 7 weeks after GL
User Survey #3 | 8 weeks after GL
Momentum Survey #5 - Final | 8 weeks after GL

## Overall Project
HH Scheduling & Capacity Management |  |  | Key Milestones
Item# | Category | Phase | Task Description | OpEx Owner | Due Date | Status | Date Complete | Notes/Decision
Governance
1 | Governance | Discovery | Stage 0 — Test the presented problem ("scheduling is broken") against cross-functional evidence before accepting it | Colin | 2026-07-24 | Complete | 2026-07-24 | Reframed: schedulers are administrators, not schedulers. Capacity and scheduling are two functions run through one artifact — a manual spreadsheet grid. Capacity must be solved first.
2 | Governance | Discovery | Stage 0 — Document why the prior HCHB Smart Scheduling pilot (Alabama) failed | Colin | 2026-07-24 | Complete | 2026-07-24 | Change management, not technology. Leaders constrained the tool to mirror the manual process and permitted clinician rejection — it was never truly piloted.
3 | Governance | Discovery | Stage 2 — Hold on-site current-state validation session: process owner + system-of-record SME + executive lead | Colin / Laci / Evan | 2026-08-13 | Complete | 2026-08-13 | Three seats deliberately chosen. Decision-maker in the room is why ten decisions were registered in one day.
4 | Governance | Discovery | Stage 2 — Register decisions DE-01 through DE-10 | Colin | 2026-08-13 | Complete | 2026-08-13 | Numbered, quotable, never renumbered.
5 | Governance | Discovery | Stage 2 — Record deferrals and out-of-scope items with the same discipline as decisions | Colin | 2026-08-13 | Complete | 2026-08-13 | Deferred: future-state map; deep auth-side mapping (DE-06); weekend and after-hours; aide/MSW/ST scheduling paths; per-trigger recert/ROC/new-order differences.
6 | Governance | Discovery | Stage 7 — Adopt the three-module target architecture: Capacity Management, Scheduling Engine, Patient Engagement | Evan | 2026-08-13 | Complete | 2026-08-13 | DE-02. Became the organising frame of the one-pager, the questionnaire coverage grid and the business case workstreams.
7 | Governance | Discovery | Stage 7 — Set Phase 1 scope: capacity first, and visualisation only — no automation in the first release | Evan | 2026-08-13 | Complete | 2026-08-13 | DE-03. The direct answer to Alabama. You cannot optimise what you cannot yet see.
8 | Governance | Discovery | Stage 7 — Set the automation posture as policy: the tool recommends, the human accepts | Evan | 2026-08-13 | Complete | 2026-08-13 | DE-09. Stated before meeting any product, so posture overreach could be read as a fit problem rather than a feature win.
9 | Governance | Discovery | Stage 7 — Confirm the capacity tool replaces the scheduling grid — same object, do not build both | Evan | 2026-08-13 | Complete | 2026-08-13 | DE-04.
10 | Governance | Discovery | Stage 7 — State the target-state scheduling role and headcount shape plainly | Evan | 2026-08-13 | Complete | 2026-08-13 | DE-10. ~300 schedulers today, ~100 in target state, with the air-traffic-control function deliberately preserved.
11 | Governance | Discovery | Stage 6 — Review and approve the business case register, its tiering convention and its exclusions | Evan |  | In Process |  | Tiers: committed / modelled / directional / not yet valued / risk avoided. Includes the anti-double-counting rules and the "must never claim" list.
12 | Governance | Discovery | Stage 8 — Confirm the vendor shortlist and authorise issue of the questionnaire | Evan | 2026-08-20 | Complete | 2026-08-20 | 6-7 candidates carried from the discovery session.
13 | Governance | Discovery | Establish the constraint register, bottleneck dossiers and decision log as standing governance artifacts |  | 2026-08-17 | Complete | 2026-08-17 | Stable IDs (CN-, CP-, DE-, SH-, C-, S-, CO-) are the join key across every downstream document.
14 | Governance | Discovery | Gate: Discovery exit review — evidence pack, risks, recommendation, formal go/no-go into Pre-Pilot Development | Evan |  | Predecessor Required |  | Blocked on: point-system definition, baseline data pack, and the eleven finance/ops inputs that convert modelled cases to committed.
Project Team/OpEx
15 | Project Team/OpEx | Discovery | Stage 1 — Run the full-day cross-functional discovery session (scheduling ops, clinical, technology/data) | Colin | 2026-07-24 | Complete | 2026-07-24 | Primary ground truth. Produced the end-to-end workflow chain, the tooling landscape and the Next Steps list.
16 | Project Team/OpEx | Discovery | Stage 1 — Capture the operator SME download into a capacity strategy foundation | Colin | 2026-07-24 | Complete | 2026-07-24 | The capacity stack: staffing model caps territory caps day-to-day; culture multiplies all three.
17 | Project Team/OpEx | Discovery | Stage 1 — Build the SME discovery framework and the tactic-capture schema | Colin | 2026-07-24 | Complete | 2026-07-24 | Every tactic must convert to a system rule or an agent guardrail. If it converts to neither it is a story — log as context.
18 | Project Team/OpEx | Discovery | Stage 1 — Draft the five role-perspective briefs (Branch ED, DCS/Clinical Manager, Senior Scheduler, Field RN/SOC nurse, Workforce Strategist) | Colin | 2026-07-24 | Complete | 2026-07-24 | Seeded v0 hypotheses to validate with real SMEs, not settled truth. Makes the interviews faster.
19 | Project Team/OpEx | Discovery | Stage 1 — Draft the scheduler insight session agenda and question bank | Colin | 2026-07-24 | Complete | 2026-07-24
20 | Project Team/OpEx | Discovery | Stage 1 — Run the scheduler insight session and observe end-of-day workflow |  |  | Not Started |  | Carried from the discovery session Next Steps. The frontline layer of discovery is still open.
21 | Project Team/OpEx | Discovery | Stage 1 — Maintain a line-numbered verbatim transcript so every citation resolves |  | 2026-08-13 | Complete | 2026-08-13 | What makes a claim auditable eight weeks on.
22 | Project Team/OpEx | Discovery | Stage 3 — Build the constraint register CN-01…CN-51, classified by changeability | Colin | 2026-08-17 | Complete | 2026-08-17 | Classes: regulatory / payer / HCHB-configurable / HCHB product limit / Compassus policy / cultural / labour agreement.
23 | Project Team/OpEx | Discovery | Stage 3 — Isolate the nine constraints that cannot be toggled — the case for building | Colin | 2026-08-17 | Complete | 2026-08-17 | CN-22…CN-30. These nine are the entire argument for a new platform.
24 | Project Team/OpEx | Discovery | Stage 3 — Isolate the Compassus-owned constraints that need no new system | Colin | 2026-08-17 | Complete | 2026-08-17 | CN-18, CN-31, CN-32, CN-33 — four of the loudest pain points. Run on a separate, faster track.
25 | Project Team/OpEx | Discovery | Stage 3 — Write the twelve bottleneck dossiers, ranked by leverage | Colin | 2026-08-17 | Complete | 2026-08-17 | Seven fields each: mechanism, evidence, downstream effects, what to measure, candidate remedies, open questions, rank. First four are the ones worth solving first.
26 | Project Team/OpEx | Discovery | Stage 3 — Map the ten capacity-to-scheduling connection points CP-1…CP-10 |  | 2026-08-17 | Complete | 2026-08-17 | CP-3 (SOC capacity gates admission) governs growth. CP-4 governs waste. CP-5 (points) underlies both and was undefined.
27 | Project Team/OpEx | Discovery | Stage 3 — Score the variable inventory for MVP weight, gating, conflict risk and automation posture | Colin / Laci | 2026-08-13 | Complete | 2026-08-13 | 79 scored rows (76 numbered + 3 unnumbered) across SH-, C-, S-, CO-. Gating is a knockout: a product that cannot do it is disqualified however well it scores.
28 | Project Team/OpEx | Discovery | Stage 3 — Publish the nine open questions in dependency order |  | 2026-08-17 | Complete | 2026-08-17 | Question 1 is the point system. Almost nothing downstream can be specified until it is pinned.
29 | Project Team/OpEx | Discovery | Stage 4 — Fix the flow-map design system before drawing (palette, type scale, block semantics, legend) | Colin | 2026-08-17 | Complete | 2026-08-17 | Captured as a reusable skill so the conventions are never re-derived by hand.
30 | Project Team/OpEx | Discovery | Stage 4 — Redraw current state as seven flow sheets, generated from source scripts | Colin | 2026-08-18 | Complete | 2026-08-18 | Primary map, detailed composite, SOC/ROC, routine visits, authorization, recert & discharge, DCS/scheduler handoff.
31 | Project Team/OpEx | Discovery | Stage 4 — Correct the map legend: colour is the actor, and the person beats the system | Colin | 2026-08-18 | Complete | 2026-08-18 | DE-07. The corrected legend showed that genuine automation in HCHB is approximately nil. The colour rule is the finding.
32 | Project Team/OpEx | Discovery | Stage 4 — Retain the full correction history as the completeness record | Colin | 2026-08-18 | Complete | 2026-08-18 | 26 numbered rounds. Current state is done when a session produces no new corrections — not when the drawing looks good.
33 | Project Team/OpEx | Discovery | Stage 4 — Build the worked scenario sheets (day-in-the-life, call-out recovery, territory review) | Colin | 2026-08-12 | Complete | 2026-08-12 | Illustrative — fictional patients and figures, real decision logic. Registers do not convince anyone; a worked day does.
34 | Project Team/OpEx | Discovery | Stage 4 — Build the future-state process map | Colin |  | Not Started |  | Deliberately deferred until current state stopped moving. Now unblocked.
35 | Project Team/OpEx | Discovery | Ingest and index the full Drive working folder; publish the source-of-truth rules |  | 2026-08-18 | Complete | 2026-08-18 | Workbook is upstream for variables; the repo is upstream for flow sheets — regenerate, publish, never edit the published PDF.
36 | Project Team/OpEx | Discovery | Stage 8 — Publish the vendor one-pager before writing a single question | Colin / Evan | 2026-08-19 | Complete | 2026-08-19 | The control variable for the whole exercise, and the internal alignment document. Ends with the thesis in one line.
37 | Project Team/OpEx | Discovery | Stage 8 — Draft, review and issue the vendor questionnaire (v1 to MASTER to MASTER 2.0) | Colin / Evan | 2026-08-20 | Complete | 2026-08-20 | Three-dropdown coverage grid (In Scope / Status / How It Runs) built specifically to defeat overselling. Instructions and Meta tabs ship with it.
38 | Project Team/OpEx | Discovery | Stage 8 — Hold back round-two and finalist deep-dive questions deliberately, and record them | Colin | 2026-08-20 | Complete | 2026-08-20 | Additional Questions, Vetting-for-Leaders and Coverage-Expanded tabs. Pricing held from round one: asking early anchors the negotiation.
39 | Project Team/OpEx | Discovery | Stage 8 — Run vendor virtual calls against the held-back question bank | Evan |  | Not Started
40 | Project Team/OpEx | Discovery | Stage 8 — Build the side-by-side vendor comparison from the returned coverage grids |  |  | Not Started |  | Compare against the stated automation posture per capability, not on weighted score alone.
41 | Project Team/OpEx | Discovery | Document the onset process end to end as a reusable procedure for future initiatives | Colin | 2026-08-22 | Complete | 2026-08-22 | playbooks/initiative-onset-playbook.md — nine stages, checklists, deliverable specs, and the mapping back into this workbook.
Communications
42 | Communications | Discovery | Issue the steering-committee stakeholder update on discovery outcomes | Michael |  | Complete |  | Groups covered: referral coordinators, growth, insurance ops, operations.
43 | Communications | Discovery | Publish the one-pager plus per-category variable reference as the standing four-page handout set | Colin | 2026-08-17 | Complete | 2026-08-17 | One vocabulary used everywhere: meetings, email, print, and the vendor pack.
44 | Communications | Pre-Pilot Development | Agree the clinician framing before any pilot communication goes out |  |  | Not Started |  | "Personal assistant, not control mechanism." On pay-per-visit offices, lead with the earnings story.
45 | Communications | Pre-Pilot Development | Build the pre-launch communication plan from the intake-platform date-tracking legend |  |  | Not Started |  | Reuse the GL-offset calendar: intro email GL-42, Teams channel GL-28, four weekly pre-launch meetings, talking points at six intervals.
46 | Communications | Pre-Pilot Development | Adopt the momentum-survey and office-hours cadence from the intake rollout |  |  | Not Started |  | Momentum surveys at GL+3 days and weeks 2, 4, 6, 8. Office hours daily for two weeks, then 3x/week, then 1x/week.
Team Member Experience Plan + Recognition
47 | Team Member Experience Plan + Recognition | Pre-Pilot Development | Confirm the clinician value proposition separately for each pay model |  |  | Not Started |  | Per-visit clinicians gain sellable capacity; salaried and union populations cannot be incentivised the same way. A meaningful share are not money-motivated at all.
48 | Team Member Experience Plan + Recognition | Pre-Pilot Development | Design the clinician-facing view that shows them their own results |  |  | Not Started |  | Raised in executive questionnaire feedback: schedule, engagement surface, and demonstrated benefit (e.g. points change over a period). Adoption depends on it.
49 | Team Member Experience Plan + Recognition | Pre-Pilot Development | Assess incentive mechanisms for hard-to-fill visits |  |  | Not Started |  | HCHB non-visit-activity coding already pays differentiated percentages. Caveats: clinicians learn to hold out for the higher offer; union and salaried populations differ.
50 | Team Member Experience Plan + Recognition | Discovery | Survey to validate the unpaid evening confirmation estimate before it carries a business case |  |  | Not Started |  | ~3,000 clinicians x ~30 min/day is a session estimate, deliberately carried as an estimate. Gates business case lever W7.
51 | Team Member Experience Plan + Recognition | Pre-Pilot Development | Give clinicians capability they lack today, not only a new process |  |  | Not Started |  | Hand a visit to their own LPN; see a supervisee schedule; self-serve open visits (HCHB Shift Finder pattern, already available and not turned on).
Training, Materials & Ambassadors
52 | Training, Materials & Ambassadors | Pre-Pilot Development | Adopt the ambassador model proven on the intake-platform rollout |  |  | Not Started |  | Identify and train ambassadors ahead of each wave; ambassador counts sized per wave in the precedent Rollout Schedule.
53 | Training, Materials & Ambassadors | Pre-Pilot Development | Scope scheduler retraining for the target-state role |  |  | Not Started |  | The retained function is urgency, local knowledge and relationship-based coverage — not task processing.
54 | Training, Materials & Ambassadors | Pre-Pilot Development | Build the pilot-site training plan, job aids and user guide |  |  | Not Started
55 | Training, Materials & Ambassadors | Pre-Pilot Development | Build the technical-training and go-live-day schedule from the precedent template |  |  | Not Started |  | Technical training the Friday immediately before go-live; all-day office hours at GL+1.
Measurement - Analytics & Feedback
56 | Measurement - Analytics & Feedback | Discovery | Define the primary and secondary KPI set | Colin | 2026-08-13 | Complete | 2026-08-13 | Primary: quantified capacity and utilisation; referral turn-down for capacity; premium labour share; LUPA rate and leakage; clinician turnover.
57 | Measurement - Analytics & Feedback | Discovery | Record which KPIs do not exist today as a live number — baseline capture is itself project work | Colin | 2026-08-13 | Complete | 2026-08-13 | Several primary metrics are unavailable today. This is a finding, not a gap in the analysis.
58 | Measurement - Analytics & Feedback | Discovery | Define the point system — value by visit type and discipline, targets, and how travel is treated |  |  | Need Assist |  | Open question #1. The shared currency of both capacity and scheduling, referenced everywhere and defined nowhere. Gates most downstream specification.
59 | Measurement - Analytics & Feedback | Discovery | Reconstruct the scheduling grid field by field — it becomes the initial data model |  |  | Not Started |  | Columns, rows, update triggers, ownership, access, embedded calculations.
60 | Measurement - Analytics & Feedback | Discovery | Define "an open slot" |  |  | Not Started |  | Visit, time block, point allocation or admission? Discipline- and territory-specific or fungible? And the formula that converts roster plus targets into a slot count.
61 | Measurement - Analytics & Feedback | Discovery | Build the 13-week baseline data pack from HCHB and Pulse |  |  | Not Started |  | Scheduled vs completed visits, points, mileage, missed-visit reasons, OASIS/recert cycles, on-call load. With documented provenance and agreed metric definitions.
62 | Measurement - Analytics & Feedback | Discovery | Stage 5 — Build the payer and episode economics reference plus the sourced research corpus | Colin | 2026-08-19 | Complete | 2026-08-19 | Payment is per 30-day period, not per certification period. There is a ceiling as well as a floor. Several levers invert by payer class.
63 | Measurement - Analytics & Feedback | Discovery | Stage 6 — Match the house business-case format before drafting anything | Colin | 2026-08-21 | Complete | 2026-08-21 | Waterfall left (hard, countable, removable), upside panel right (probabilistic), each upside lever as a percentage of a named revenue base.
64 | Measurement - Analytics & Feedback | Discovery | Stage 6 — Write the business case register: mechanism, evidence, sizing formula, tier, missing input | Colin | 2026-08-21 | Complete | 2026-08-21 | Seven families. Includes the anti-double-counting rules and the list of claims the case must never make.
65 | Measurement - Analytics & Feedback | Discovery | Stage 6 — Build the assumptions model that feeds the house waterfall and upside output |  |  | Not Started |  | One sheet of named, editable inputs so the case is argued at the assumption level rather than the conclusion level.
66 | Measurement - Analytics & Feedback | Discovery | Stage 6 — Obtain the eleven finance and operations inputs that convert modelled cases to committed |  |  | Need Assist |  | None can be sourced externally. Each row names the case it unlocks.
67 | Measurement - Analytics & Feedback | Active Pilot | Pre-register the pilot primary metric, success thresholds and kill criteria |  |  | Predecessor Required |  | Committed in advance, at the pilot charter, not decided at readout.
Shared Services (IT, Contracting, Marketing, Legal)
68 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | IT review of the system landscape and integration points |  |  | In Process |  | HCHB (core, manual sync), Commure (intake), NestMed (real-time docs), Pulse (utilisation), Workday (PTO), external coding vendor, Circadia.
69 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Legal review of outbound automated patient contact constraints | Colin |  | Not Started |  | Text and email consents are not signed until the SOC visit. California treats any non-manually-triggered outbound call as a robocall. Washington/Providence requires a safety screening script.
70 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Confirm hosting, SOC 2 / HITRUST posture and BAA willingness for shortlisted vendors |  |  | Not Started |  | Deliberately held out of round one — near-certain to be satisfied, and verifiable afterwards.
71 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Agree the contracting approach and the value-sharing position | Evan |  | Not Started |  | Questionnaire E3 tees it up open-ended. Options: revenue share, cap-table participation, penny warrants, co-marketing fees.
72 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Activate the Workday to HCHB PTO integration — it exists and is switched off |  |  | Not Started |  | Free, immediate, removes manual entry and prevents five of seven nurses being approved off the same day. Business case lever W5.
73 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Evaluate routing referral documents from Commure to the NestMed face-to-face module |  |  | Not Started |  | Reduces downstream coding discrepancies that create plan-of-care holds.
74 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Add a scheduling-grid view within Commure below referral tasks |  |  | Not Started |  | Pending referrals with payer, expected discharge date, discipline ordered and status — to retire the Excel grids.
Workforce
75 | Workforce | Discovery | Obtain the pay-model split across the branch estate — per visit, hourly, salaried, points |  |  | Need Assist |  | The highest-value single input. For per-visit clinicians cost is linear and scheduling optimisation cannot create margin; for salaried the marginal visit is near-free.
76 | Workforce | Discovery | Resolve the pilot-site tension this creates, in advance |  |  | Not Started |  | The named pilot candidates are the per-visit offices: the best sites for adoption and the worst sites for proving a margin case. Decide deliberately, not at readout.
77 | Workforce | Discovery | Obtain the scheduler loaded cost and headcount baseline |  |  | Need Assist |  | Unlocks business case levers W1 and W2 — the largest single hard lever in the initiative.
78 | Workforce | Discovery | Obtain contract, per-diem and overtime spend baselines by discipline |  |  | Need Assist |  | Unlocks W3 and W4.
79 | Workforce | Discovery | Obtain clinician turnover rate and replacement cost |  |  | Need Assist |  | Turnover reduction is already an accepted waterfall lever in the house format, not an upside item.
80 | Workforce | Pre-Pilot Development | Define the target-state scheduler role and the transition plan for the function |  |  | Not Started |  | DE-10 preserves the role at reduced scale. Initiatives that avoid this question have it answered for them by rumour.
Business Continuity
81 | Business Continuity | Discovery | Document the hard system stop: once a clinician accepts a visit, the back office cannot pull it | Colin | 2026-08-18 | Complete | 2026-08-18 | All same-day changes are phone-only. This single constraint reshapes any target-state design.
82 | Business Continuity | Discovery | Document the Medicare compliance windows the schedule must never breach | Colin | 2026-08-18 | Complete | 2026-08-18 | 48-hour MD notification on missed visits; 30-day therapy reassessments; 14-day HHA supervisory visits; the TIC clock from referral; the in-home physical calendar as a CoP requirement.
83 | Business Continuity | Pre-Pilot Development | Define the fallback if the platform is unavailable during a launch week |  |  | Not Started |  | Vendor questionnaire finalist agenda asks the same question: what happens when the system is down on a Monday morning?
84 | Business Continuity | Active Pilot | Run the scheduling grid in parallel through the pilot, and set the criteria to retire it |  |  | Predecessor Required |  | DE-04 says they are the same object. Retire on evidence, not on go-live date.
85 | Business Continuity | Pre-Pilot Development | Confirm data extractability and exit position before contracting |  |  | Not Started |  | Can we get our own data out, and can we build on top? Held for the finalist deep dive.
Finish the Job Priorities
86 | Finish the Job Priorities | Discovery | Fast-track the four Compassus-owned constraints — no vendor dependency, no waiting | Colin |  | Not Started |  | CN-18, CN-31, CN-32, CN-33. Banks a visible win early and funds the initiative credibility.
87 | Finish the Job Priorities | Pre-Pilot Development | Discipline-role match: default to the paraprofessional with explicit opt-out |  |  | Not Started |  | DE-08. Two returns at once — lower cost per visit, and freed assessing-clinician capacity for starts, which is exactly where growth is blocked.
88 | Finish the Job Priorities | Pre-Pilot Development | Assign the care team at referral rather than per visit |  |  | Not Started |  | DE-05. System recommends the full team, a human approves or edits, visits thereafter route to the established team. Collapses the per-discipline task explosion.
89 | Finish the Job Priorities | Pre-Pilot Development | Data-driven territory design, encoding local knowledge |  |  | Not Started |  | There is no data behind territory design today. The system must encode the Jacksonville bridge (one zip, two non-interchangeable sides) and the California interstate crossing window.
90 | Finish the Job Priorities | Pre-Pilot Development | Surface payer rules at plan-of-care creation |  |  | Not Started |  | The data already exists — the auth team writes it into a coordination note at verification. This is a schema and a surfacing point, not a data-gathering programme. And it is a patient-care win.
91 | Finish the Job Priorities | Pre-Pilot Development | Turn on the HCHB Shift Finder pattern for clinician self-serve of open visits |  |  | Not Started |  | Already available and not enabled.
92 | Finish the Job Priorities | Pre-Pilot Development | Select the pilot site: a new-integration or brand-new branch go-live |  |  | Not Started |  | Favour a site where existing habits will not fight the tool. Avoid leading with tenured-clinician offices. Weigh against the pay-model tension recorded under Workforce.
93 | Finish the Job Priorities | Pre-Pilot Development | Design the "flare button" for call-out recovery |  |  | Not Started |  | Triage by clinical priority (SOC, IV, wound, labs due, ortho) and recommend nearby coverage, with clinical sign-off retained. The named ask from the whiteboard session.

## GoLive Wave Tawas Portage (hidden)
HH Intake Application Launch Tawas City/Alpena/Portage MI |  | Key Milestones
|  | Go-Live Date: 3/11 for Tawas/Alpena & 3/12 for Portage |  | 1:33
|  | In-Person Training Date: 3/11 for Tawas/Alpena & 3/12 for Portage |  | Join
|  | Technical Training Date: 3/6/26 |  | Mike Davis joined the conversation.
Item# | Phase | Task Description | Owner/Resources | Due Date | Status | Date Complete | Notes/Decision
Leadership & Planning
| Leadership & Planning | 4-week meeting series prior to launch date with formal go/no-go on week 4 |  |  | Complete
| Leadership & Planning | Go-Live Readiness checklist |  |  | Complete
| Leadership & Planning | Confirm launch date alignment with vendor |  |  | Complete
| Leadership & Planning | Confirm go-live schedule with RVP/RME |  |  | Complete
| Leadership & Planning | Obtain go-live date alignment with IT/Reporting/Operations (competing launches/pilots?) |  |  | Complete
| Leadership & Planning | Leadership participates in daily huddles during launch period |  |  | Complete
| Leadership & Planning | Manage wave-based action register |  |  | Complete
| Leadership & Planning | Support lead attend tiered escalation huddle (daily) with OpEx/Vendor team |  |  | Complete
| Leadership & Planning | Transition wave huddle to product manager |  |  | Complete
| Leadership & Planning | Distribute Leader Talking Points for 1 week pre-Launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for Go-Live Day | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 1-2 weeks post-launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 3-4 weeks post-launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 5-6 weeks post-launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 7-8 weeks post-launch | Paige |  | Not Applicable
Pre-Go-Live
| >4 Weeks Pre-Go-Live | Invites for 4 weekly pre-go live huddles sent + welcome communication sent |  |  | Complete
| >4 Weeks Pre-Go-Live | Completion of any market/agency specific platform modifications by vendor (payor, portals, etc.) |  |  | Complete
| 4 weeks Pre-Go-Live | Meeting 1 content: overview deck, review timeline, validate nuances/portals captured in survey, & identify local champions |  |  | Complete
| 4 weeks Pre-Go-Live | Request for data delivery from Compassus to application (Add location to existing feeds/files + AC/growth list) |  |  | Complete
| 4 weeks Pre-Go-Live | Submit request for new production/BOT accounts (if needed) |  |  | Complete
| 4 weeks Pre-Go-Live | Valiadate partnered & growth member assignment in HCHB |  |  | Complete
| 4 weeks Pre-Go-Live | Validate ZIP code master & confirm update in PowerBI |  |  | Complete |  | Issue being investigated
| 4 weeks Pre-Go-Live | Identify referral sources with auto patient placement after portal acceptance |  |  | Not Applicable |  | No partner referral sources in MI
| 4 weeks Pre-Go-Live | Request full user list with email & user category |  |  | Complete
| 3 weeks Pre-Go-Live | Meeting 2 content: Explore in tool, discuss VBE if applicable, validate week 1 requests & show early results |  |  | Complete
| 3 weeks Pre-Go-Live | Provision users & BOTs to platform/HCHB and Compassus SSO for both UAT & PROD (Compasus email, hospicecom.com email, User Group, Branch Codes Needing Access to) |  |  | Complete
| 3 weeks Pre-Go-Live | Submit ticket for DL creation per HCHB Branch ID (note single vs multi branch DLs & exceptions) |  |  | Not Applicable
| 3 weeks Pre-Go-Live | Request date to sever portal feeds to HCHB (including Forcura) |  |  | Complete
| 2 weeks Pre-Go-Live | Meeting 3 content: Go-live logistics, on-site planning, review baseline metrics |  |  | Complete
| 2 weeks Pre-Go-Live | Request revenue (insurance) grant BOT access to Availity, etc. as needed |  |  | Complete
| 2 weeks Pre-Go-Live | Assess need for updates to user guides and/or training decks |  |  | Complete
| 1 week Pre-Go-Live | Meeting 4 content: GO/No-GO decision, final prep, go-live expectations, path forward |  |  | Complete
| 1 week Pre-Go-Live | Establish pre & post -go-live leader huddles |  |  | Complete
| 1 week Pre-Go-Live | Send Office Hours invitations |  |  | Complete
| 1 week Pre-Go-Live | Referral Source Notification (Specifically referral partners) |  |  | Complete
| 1 week Pre-Go-Live | Set-up Teams site or channel for go-live wave |  |  | Complete
| 1 week Pre-Go-Live | Create action register for go-live wave + add to Teams site/channel |  |  | Complete
Training
| Training | Identify trainers & ambassadors for Growth/Intake/Insurance |  |  | Complete
| Training | Provide ambassadors with standaridzed tool-kit |  |  | Complete
| Training | Develop ambassador deployment plan |  |  | Complete
| Training | Develop DBOS deployment plan |  |  | Not Applicable
| Training | Arrange room & lunches for in-person training |  |  | Complete
| Training | Request BOC/BOM to print user guides for training |  |  | Complete
| Training | Send Technical Training Invite (remote) |  |  | Complete
| Training | Send Go-Live Session Invites (one remote/one in-person) |  |  | Complete
| Training | Provide user guides and tip sheets (via email & in trainiing) |  |  | Complete
| Training | Complete training deck revisions |  |  | Complete
| Training | Complete user guide revisions |  |  | Complete
| Training | Grant access to applicable Teams folder |  |  | Complete
| Training | Schedule post-go live breakout sessions for each user group |  |  | Complete
| Training | Distribute testimonial video |  |  | Not Applicable
Go-Live
| Final Readiness Check | Confirm SSO for identified users |  |  | Complete
| Final Readiness Check | Complete readiness checklist |  |  | Complete
| Final Readiness Check | Confirm portal feeds ready for cutover |  |  | Complete
| Final Readiness Check | Confirm go-live time with vendor/agency |  |  | Complete
| Go-Live Day | Distribute go-live communication (or day before?) |  |  | Complete
| Go-Live Day | Confirm portal cutover executed |  |  | Complete
| Go-Live Day | Monitor first referral intake |  |  | Complete
| Go-Live Day | Validate HCHB writebacks |  |  | Complete
| Go-Live Day | Validate eligilility/insurance |  |  | Complete
| Go-Live Day | Provide all-day office hours support & ambassador on-site day of go-live. |  |  | Complete
| Go-Live Day | Validate all users have access to Teams chat for wave |  |  | Complete
| Week 1-2 | Assess need for all-day office hours/support for day after go-live. Send Teams invite. |  |  | Complete
| Week 1-2 | Hold twice-daily office hours for 2 weeks |  |  | Complete
| Week 1-2 | Conduct week 1 breakout sessions & send invitations | Mike |  | Complete
| Week 1-2 | Distribute user surveys bi-weekly for for week 1 | Paige |  | Complete
| Week 3-4 | Distribute user surveys |  |  | Complete
| Week 3-4 | Review user surveys |  |  | Complete
| Week 3-4 | Coach based off of user surveys |  |  | Complete
| Week 3-4 | Capture testiminals from surveys |  |  | Complete
| Week 3-4 | ED/AME/RME Coaching |  |  | Complete
| Week 3-4 | Initial maturity |  |  | Not Applicable
| Week 3-4 | Behavior establishment |  |  | Not Applicable
| Week 5-6 | Distribute user surveys |  |  | Complete
| Week 5-6 | Review user surveys |  |  | Complete
| Week 5-6 | Coach based off of user surveys |  |  | Complete
| Week 5-6 | Capture testiminals from surveys |  |  | Complete
| Week 7-8 | Distribute user surveys |  |  | Complete
| Week 7-8 | Review user surveys |  |  | Complete
| Week 7-8 | Coach based off of user surveys |  |  | Complete
| Week 7-8 | Capture testiminals from surveys |  |  | Complete
| Week 7-8 | Distribute rewards |  |  | Not Applicable |  | Thank you message sent
Stabilization & Optimization
| Stabilization & Optimization | Transition ownership to business owner |  |  | Complete
| Stabilization & Optimization | Confirm & communicate on-going support model |  |  | Complete
| Stabilization & Optimization | Capture Lessons Learned post 30-day go-live (including leaders, ambassadors, opex) |  |  |  |  | Captured in regional huddles
| Stabilization & Optimization | Track & prioritize optimization/enhancement requests |  |  | Complete
| Stabilization & Optimization | Track & Trend Weekly/Monthly Intake Metrics |  |  | In Process
| Stabilization & Optimization | Provide weekly executive snapshot report to market/region leaders |  |  | Complete
| Stabilization & Optimization | Conduct daily/weekly huddles with market leadership for feedback/support |  |  | Complete
| Stabilization & Optimization | Meet with Frontline teams to root cause issues |  |  | Complete
| Week 5-6 | Begin role/title changes |  |  | Not Applicable

## GoLive Market Template
HH Scheduling <Market> Launch |  | Key Milestones
Item# | Phase | Task Description | Owner/Resources | Due Date | Status | Date Complete | Notes/Decision
Pre-Wave Planning
Pre-Go-Live
Training
Go-Live
Stabilization & Optimization
Sunsetting AutomationEdge

## Rollout Schedule (hidden)
HH Intake Platform Rollout Schedule 2026 — Compassus Operational Excellence
TX: Waco+Austin May 12, Kyle+Burnet+Bastrop May 13 ¦ FL: Jax Apr 28, Pen+PC+Tampa+St Pete Apr 29 ¦ KY Jun 2 ¦ OH Wk1 Jun 2-3 (Lorain/Youngstown/Lima/Tiffin), Wk2 Jun 9-10 (Columbus/Mansfield/Marion/Athens) ¦ TN Jun 16 ¦ IN Jun 23-24 ¦ KS+MO Jul 14 ¦ WI Jul 21-22 ¦ OK+MT+NM Jul 28-29 ¦ AL Aug 4 ¦ CA Aug 25-Sep 30 ¦ WA+AK Oct 6-13 ¦ Oregon Oct 20 ¦ Complete Oct 20, 2026
Wave | Month(s) | State(s) | Top 2 Portals | Portal Trigger | # Locs | # Amb | Tue Wk 1 | Wed Wk 1 | Tue Wk 2 | Wed Wk 2 | CHAP Notes | Rollout Notes
Wave 1 | Apr 28–29 | FL | Ensocare #1 Epic CareLink #2 | Ensocare live May | 5 | 2 | 4/28 Tue FL-A: Jacksonville FL | 4/29 Wed FL-A: Pensacola FL FL-B: Panama City FL FL-C: Tampa FL FL-D: St Pete FL | — | — | —
Wave 1 | May 12–13 | TX | AllScripts #1 Epic CareLink #2 | AllScripts ✓ CarePort ✓ | 5 | 2 | 5/12 Tue TX-A: Waco TX TX-B: Austin TX | 5/13 Wed TX-A: Kyle TX TX-B: Burnet TX TX-C: Bastrop TX | — | — | CHAP Feb–Aug (Austin)
Wave 2 | Jun 23–24 | IN | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 8 | 4 | 6/23 Tue IN-A: Anderson IN IN-B: Kokomo IN IN-C: Evansville IN | 6/24 Wed IN-A: Indianapolis IN IN-B: Lafayette IN IN-C: Bloomington IN IN-D: N. Vernon IN IN-D: Veedersburg IN | — | — | CHAP Jan–Apr (past ✓)
Wave 2 | 2026-06-16 | KY | Epic CareLink #1 Aidin #2 | Aidin live Jun | 1 | 1 | 6/2 Tue KY-A: Paducah KY | — | — | — | —
Wave 2 | Jun 9–10 (Wk 2) | OH 1 | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 4 | 2 | 6/9 Tue OH-A: Lorain OH OH-B: Youngstown OH | 6/10 Wed OH-A: Lima OH OH-B: Tiffin OH | — | — | —
Wave 2 | Jun 2–3 (Wk 1) | OH 2 | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 4 | 2 | 6/2 Tue OH-A: Columbus OH OH-B: Mansfield OH | 6/3 Wed OH-A: Marion OH OH-B: Athens OH | — | — | —
Wave 2 | Jun 16 | TN | AllScripts #1 Epic CareLink #2 | AllScripts ✓ + Epic Jul | 2 | 1 | 6/16 Tue TN-A: Centerville TN TN-B: Nashville TN | — | — | — | CHAP May–Jul (past ✓)
Wave 3 | Jul 14 | KS | Ensocare #1 Epic CareLink #2 | Ensocare live May | 2 | 2 | 7/14 Tue KS-A: Pittsburg KS KS-B: Wichita KS | — | — | — | —
Wave 3 | Jul 14 | MO | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 1 | 1 | 7/14 Tue MO-A: Columbia MO | — | — | — | —
Wave 3 | Jul 28–29 | MT + NM | Epic CareLink #1 NaviHealth #2 | Epic + NaviHealth Jul | 4 | 2 | 7/28 Tue MT-A: Butte MT NM-A: Santa Fe NM | 7/29 Wed MT-A: Billings MT NM-A: Albuquerque NM | — | — | MT: CHAP Jan–Apr (past ✓)
Wave 3 | Jul 28 | OK | Ensocare #1 Epic CareLink #2 | Ensocare live May | 2 | 2 | 7/28 Tue OK-A: Bartlesville OK OK-B: Tulsa OK | — | — | — | CHAP Feb–Jul
Wave 3 | Jul 14 | SC | NaviHealth #1 Ensocare #2 | NaviHealth live Jul | 1 | 1 | 7/14 Tue SC-A: Greenville SC | — | — | — | —
Wave 3 | Jul 14–15 | VA | NaviHealth #1 Epic CareLink #2 | NaviHealth + Epic Jul | 4 | 2 | 7/14 Tue VA-A: Richmond VA VA-B: Suffolk VA | 7/15 Wed VA-A: Newport News VA VA-B: Virginia Beach VA | — | — | —
Wave 3 | Jul 21–22 (all 12 locs) | WI | Epic CareLink #1 NaviHealth #2 | Epic + NaviHealth Jul | 12 | 6 | 7/21 Tue WI-A: Arbor Vitae WI WI-B: Rhinelander WI WI-C: Sturgeon Bay WI WI-D: Green Bay WI WI-E: Neenah WI | 7/22 Wed WI-A: Racine WI WI-B: Sheboygan WI WI-C: Chippewa Falls WI WI-D: Marshfield WI WI-E: Wausau WI WI-F: Milwaukee WI WI-G: Plover WI | — | — | — | All 12 WI in 1 week with 6 ambassadors. Moved from Aug 4-5 per revised timeline.
Wave 4 | Aug 4 | AL | WATERSHED #1 AllScripts #2 | Watershed live Aug | 2 | 1 | 8/4 Tue AL-A: Pell City AL AL-B: Vestavia AL | — | — | — | —
Wave 4 | Aug 25– Sep 30 | CA (10 locs, slow roll) | AIDA #1 Epic CareLink #2 | AIDA live Sep | 10 | 2 | 8/25: LA North CA 9/8: Inland Empire CA 9/15: Humboldt Co. CA 9/22: Napa Valley CA 9/29: OC Mission Viejo CA | 8/26: High Desert CA 9/9: OC Anaheim CA 9/16: LA South CA 9/23: Sonoma Co. CA 9/30: OC South CA | — | — | CHAP Apr–Jun past Oct–Dec: monitor | CA slow roll 2 locs/wk. Begins Aug 25, completes Sep 30.
Wave 4 | Oct 20 | OR (placeholder) | AIDA #1 | AIDA live Sep | 1 | 1 | 10/20 Tue OR-A: Oregon Launch (TBD) | — | — | — | — | Oregon placeholder. Dates/locations TBD. Added after all other locs complete.
Wave 4 | Oct 6–13 | WA + AK | AIDA #1 Epic CareLink #2 | AIDA live Sep (after CA done) | 6 | 2 | 10/6 Tue WA-A: Spokane WA WA-B: Olympia WA | 10/7 Wed WA-A: Seattle WA WA-B: Snohomish Co. WA AK-A: Anchorage AK | 10/13 Tue WA-A: Walla Walla WA | — | WA: CHAP Apr–Dec (buffer applied) | WA+AK after CA completes. 2 amb. AK shares Wed Oct 7.

## GoLive (hidden)
HH Intake Application Launch |  | Key Milestones
Item# | Phase | Task Description | Owner/Resources | Due Date | Status | Date Complete | Notes/Decision
Pre-Wave Planning
| Leadership & Planning | Establish 4-week meeting series prior to launch date with formal go/no-go on week 4
| Leadership & Planning | Establish go-live window
| Leadership & Planning | Obtain go-live date alignment with IT/Reporting/Operations (competing launches/pilots?)
| Leadership & Planning | Establish operating model to include transition from local to regional on--going support
| Leadership & Planning | Ambassador identification & alignment
| Leadership & Planning | Distribute Leader Talking Points for 1 week pre-Launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for Go-Live Day | Paige
| Leadership & Planning | Distribute Leader Talking Points for 1-2 weeks post-launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for 3-4 weeks post-launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for 5-6 weeks post-launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for 7-8 weeks post-launch | Paige
Pre-Go-Live
| >4 Weeks Pre-Go-Live | Invites for 4 weekly pre-go live huddles sent + welcome communication sent
| >4 Weeks Pre-Go-Live | Completion of any market/agency specific platform modifications by vendor (payor, portals, etc.)
| 4 weeks Pre-Go-Live | Confirm go-live schedule with RVP/RME
| 4 weeks Pre-Go-Live | Meeting 1 content: overview deck, review timeline, validate nuances/portals captured in survey, & identify local champions
| 4 weeks Pre-Go-Live | Request for data delivery from Compassus to application (Add location to existing feeds/files + AC/growth list)
| 4 weeks Pre-Go-Live | Submit request for new production/BOT accounts (if needed)
| 4 weeks Pre-Go-Live | Valiadate partnered & growth member assignment in HCHB
| 4 weeks Pre-Go-Live | Validate ZIP code master & confirm update in PowerBI
| 4 weeks Pre-Go-Live | Identify referral sources with auto patient placement after portal acceptance
| 4 weeks Pre-Go-Live | Request full user list with email & user category
| 3 weeks Pre-Go-Live | Meeting 2 content: Explore in tool, discuss VBE if applicable, validate week 1 requests & show early results
| 3 weeks Pre-Go-Live | Confirm launch date alignment with vendor
| 3 weeks Pre-Go-Live | Provision users & BOTs to platform/HCHB and Compassus SSO for both UAT & PROD (Compasus email, hospicecom.com email, User Group, Branch Codes Needing Access to)
| 3 weeks Pre-Go-Live | Submit ticket for DL creation per HCHB Branch ID (note single vs multi branch DLs & exceptions)
| 3 weeks Pre-Go-Live | Request date to sever portal feeds to HCHB (including Forcura)
| 2 weeks Pre-Go-Live | Meeting 3 content: Go-live logistics, on-site planning, review baseline metrics
| 2 weeks Pre-Go-Live | Request revenue (insurance) grant BOT access to Availity, etc. as needed |  |  |  |  | No need for additional access per Natalia & Kitty
| 2 weeks Pre-Go-Live | Assess need for updates to user guides and/or training decks
| 1 week Pre-Go-Live | Meeting 4 content: GO/No-GO decision, final prep, go-live expectations, path forward
| 1 week Pre-Go-Live | Establish pre & post -go-live leader huddles
| 1 week Pre-Go-Live | Send Office Hours invitations
| 1 week Pre-Go-Live | Referral Source Notification (Specifically referral partners) |  |  |  |  | Add to week 3 deck
| 1 week Pre-Go-Live | Set-up Teams site or channel for go-live wave
| 1 week Pre-Go-Live | Create action register for go-live wave + add to Teams site/channel
| Pre-Go-Live Testing | Enable and validate portal feeds in Commure by the Friday prior to go/no-go decisions | Sara
| Pre-Go-Live Testing | Confirm testing readiness, including user access, test scenarios, insurance configurations, ZIP routing, and Facilitate writeback functionality. | OpEx Team
| Pre-Go-Live Testing | Conduct payer map / audit review (1:1 Home Care Home Base payer map check) | Sara
| Pre-Go-Live Testing | 1:1 payor match for state confirmed before go-live | Sara
| Pre-Go-Live Testing | Confirm referrals are flowing to Commure PROD for go-live branches and accessible to users for pre-launch testing | OpEx / IT
| Pre-Go-Live Testing | On Monday/Tuesday of go/no-go week, conduct extensive end-to-end testing for insurance workflows, ZIP code routing, referral processing, and writebacks, including pushing test referrals to validate operational workflows and system performance. | Intake Supervisor, Intake SME, Insurance Supervisor
| Pre-Go-Live Testing | Track and resolve identified issues, review testing outcomes, and provide readiness recommendations for final go/no-go decisions | OpEx Team
| Pre-Go-Live Testing | Build at-risk technical connection / integration items list for weekly IT call | OpEx Team
Training
| Training | Identify trainers & ambassadors for Growth/Intake/Insurance
| Training | Provide ambassadors with standaridzed tool-kit
| Training | Develop ambassador deployment plan
| Training | Develop DBOS deployment plan
| Training | Arrange room & lunches for in-person training
| Training | Request BOC/BOM to print user guides for training
| Training | Send Technical Training Invite (remote)
| Training | Send Go-Live Session Invites (one remote/one in-person)
| Training | Provide user guides and tip sheets (via email & in trainiing)
| Training | Complete training deck revisions
| Training | Complete user guide revisions
| Training | Grant access to applicable Teams folder
| Training | Schedule post-go live breakout sessions for each user group
| Training | Distribute testimonial video
Go-Live
| Final Readiness Check | Confirm SSO for identified users
| Final Readiness Check | Complete readiness checklist
| Final Readiness Check | Confirm portal feeds ready for cutover
| Final Readiness Check | Confirm go-live time with vendor/agency
| Go-Live Day | Distribute go-live communication (or day before?)
| Go-Live Day | Confirm portal cutover executed
| Go-Live Day | Monitor first referral intake
| Go-Live Day | Validate HCHB writebacks
| Go-Live Day | Validate eligilility/insurance
| Go-Live Day | Provide all-day office hours support & ambassador on-site day of go-live.
| Go-Live Day | Validate all users have access to Teams chat for wave
| Week 1-2 | Assess need for all-day office hours/support for day after go-live. Send Teams invite.
| Week 1-2 | Hold twice-daily office hours for 2 weeks
| Week 1-2 | Conduct week 1 breakout sessions & send invitations | Mike
| Week 1-2 | Distribute user surveys bi-weekly for for week 1 | Paige
| Week 1-2 | Distribute rewards
| Week 3-4 | Distribute user surveys
| Week 3-4 | Review user surveys
| Week 3-4 | Coach based off of user surveys
| Week 3-4 | Capture testiminals from surveys
| Week 3-4 | ED/AME/RME Coaching
| Week 3-4 | Initial maturity
| Week 3-4 | Behavior establishment
| Week 5-6 | Distribute user surveys
| Week 5-6 | Review user surveys
| Week 5-6 | Coach based off of user surveys
| Week 5-6 | Capture testiminals from surveys
| Week 5-6 | Begin role/title changes
| Week 7-8 | Distribute user surveys
| Week 7-8 | Review user surveys
| Week 7-8 | Coach based off of user surveys
| Week 7-8 | Capture testiminals from surveys
| Week 7-8 | Distribute rewards
| Week 7-9 | Transition wave huddle to regional intake director (regional intake huddle)
Stabilization & Optimization
| Stabilization & Optimization | Transition ownership to business owner
| Stabilization & Optimization | Confirm & communicate on-going support model
| Stabilization & Optimization | Capture Lessons Learned post 30-day go-live (including leaders, ambassadors, opex)
| Stabilization & Optimization | Track & prioritize optimization/enhancement requests
| Stabilization & Optimization | Track & Trend Weekly/Monthly Intake Metrics
| Stabilization & Optimization | Provide weekly executive snapshot report to market/region leaders
| Stabilization & Optimization | Conduct daily/weekly huddles with market leadership for feedback/support
| Stabilization & Optimization | Meet with Frontline teams to root cause issues
| Stabilization & Optimization | Test all enhancements/changes in test environment and validate before promoting to production | OpEx Team

## Monthly View (hidden)
Month-by-Month Rollout 2026 — HH Intake Platform ¦ Apr 28 – Oct 20, 2026
April 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 1 | FL – Jacksonville FL | Apr 28 (Tue) — FL-A solo | Ensocare
Wave 1 | FL – Pensacola, Panama City, Tampa, St. Pete | Apr 29 (Wed) — FL-A,B,C,D | Ensocare
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 1 | TX – Waco + Austin TX | May 12 (Tue) — TX-A + TX-B + TX-C | AllScripts ✓
Wave 1 | TX – Kyle + Burnet + Bastrop TX | May 13 (Wed) — TX-A (Kyle) + TX-B (Burnet) + TX-C (Bastrop) ✓ ALL TX done by May 13 | AllScripts ✓
⛔ SKIP | Memorial Day week | Week of May 25 — NO LAUNCHES | Holiday blackout
June 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 2 | TN – Centerville TN + Nashville TN | Jun 16 (Tue) — TN-A + TN-B (same day) | AllScripts + Epic; CHAP May–Jul
Wave 2 | KY – Paducah KY | Jun 16 (Tue) — KY-A | Aidin live Jun
Wave 2 | OH Wk2 – Lorain, Youngstown, Lima, Tiffin | Jun 9 (Tue) + Jun 10 (Wed) — OH-A + OH-B | AllScripts ✓ live
Wave 2 | OH Wk1 – Columbus, Mansfield, Marion, Athens | Jun 2 (Tue) + Jun 3 (Wed) — OH-A + OH-B | AllScripts ✓
Wave 2 | IN (all 8) | Jun 23 (Tue) + Jun 24 (Wed) — 4 ambassadors (IN-A/B/C/D) | AllScripts ✓ — CHAP Jan–Apr past
⛔ SKIP | Independence Day week | Week of Jun 29 — NO LAUNCHES | Holiday blackout
July 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
⛔ SKIP | Jul 7 (Tuesday) | Jul 7 — NO LAUNCH (holiday) | Holiday blackout
Wave 3 | SC – Greenville SC ¦ KS – Pittsburg + Wichita ¦ MO – Columbia MO | Jul 14 (Tue) — SC-A + KS-A/B + MO-A | NaviHealth (SC) · Ensocare (KS) · AllScripts (MO)
Wave 3 | VA – Richmond, Suffolk, Newport News, Virginia Beach | Jul 14 (Tue) + Jul 15 (Wed) — VA-A + VA-B | NaviHealth + Epic Jul
Wave 3 | CA PILOT – California (1 location TBD) | 📍 START PILOT IN CALIFORNIA Jul 14 (Tue) — length TBD | TBD
Wave 3 | WI – All 12 locations (Tue: Arbor Vitae, Rhinelander, Sturgeon Bay, Green Bay, Neenah · Wed: Racine, Sheboygan, Chippewa Falls, Marshfield, Wausau, Milwaukee, Plover) | Jul 21 (Tue) + Jul 22 (Wed) — 6 ambassadors (WI-A/B/C/D/E/F) | Epic + NaviHealth
Wave 3 | OK – Bartlesville + Tulsa ¦ MT – Butte MT + Billings MT ¦ NM – Santa Fe NM + Albuquerque NM | Jul 28 (Tue) — OK-A/B + MT-A + NM-A Jul 29 (Wed) — MT-A (Billings) + NM-A (Albuquerque) | Ensocare (OK) · Epic+NaviHealth (MT/NM)
August 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 3 | AL – Pell City + Vestavia (all locations same day) | Aug 4 (Tue) — AL-A + AL-B | Watershed (AL)
Wave 4 | CA – LA North CA (slow roll begins) | Aug 25 (Tue) — CA-A | AIDA live Sep — 2 locs/wk pace
September 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
⛔ SKIP | Sept 7 (Tuesday) | Jul 7 — NO LAUNCH (holiday) | Holiday blackout
Wave 4 | CA – Inland Empire + OC Anaheim | Sep 8 (Tue) + Sep 9 (Wed) — CA-A + CA-B | AIDA
Wave 4 | CA – Humboldt Co. + LA South | Sep 15 (Tue) + Sep 16 (Wed) — CA-A + CA-B | AIDA
Wave 4 | CA – Napa Valley + Sonoma Co. | Sep 22 (Tue) + Sep 23 (Wed) — CA-A + CA-B | AIDA
October 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 4 | WA – Spokane + Olympia | Oct 6 (Tue) — WA-A + WA-B | AIDA
Wave 4 | WA – Seattle + Snohomish Co. ¦ AK – Anchorage | Oct 7 (Wed) — WA-A + WA-B + AK-A | AIDA
Wave 4 | WA – Walla Walla WA | Oct 13 (Tue) — WA-A ✓ WA+AK COMPLETE Oct 13 | AIDA
Wave 4 | OR – Oregon Launch (TBD) 📍 | Oct 20 (Tue) — OR-A (PLACEHOLDER) ✓ ALL ROLLOUTS COMPLETE | AIDA / Tango

## Timeline View (hidden)
2026 Rollout Timeline — Home Health Intake Platform ¦ Apr 28 – Oct 20, 2026
State (Wave) | Apr/May | June | July | Aug | Sep | Oct | Additional Project Team Support
FL (Wave 1) | Apr 28 (Tue): Jacksonville FL Apr 29 (Wed): Pensacola + Panama City + Tampa & St. Pete | [5 empty] | James or Paige go to Panama City
TX (Wave 1) | May 12 (Tue): Waco + Austin May 13 (Wed): Kyle + Burnet + Bastrop | [5 empty] | Michael/Luke
KY (Wave 2) |  | Jun 16 (Tue): Paducah KY
OH (Wave 2) |  | Jun 9-10: Wk1 (Lorain, Youngstown, Lima, Tiffin) Jun 2-3: Wk2 (Columbus, Mansfield, Marion, Athens) |  |  |  |  | All available support
TN (Wave 2) |  | Jun 16 (Tue): Centerville + Nashville |  |  |  |  | Paige/James
IN (Wave 2) |  | Jun 23–24: All 8 locs (4 ambassadors) |  |  |  |  | TBD to Indianapolis + Evansville + Anderson
KS (Wave 3) |  |  | Jul 14 (Tue): Pittsburg + Wichita (2 ambassadors)
MO (Wave 3) |  |  | Jul 14 (Tue): Columbia MO
CA PILOT (Wave 3) |  |  | 📍 START PILOT IN CALIFORNIA Jul 14 (Tue) — length TBD
SC (Wave 3) |  |  | Jul 14 (Tue): Greenville SC
VA (Wave 3) |  |  | Jul 14 (Tue) + Jul 15 (Wed): Richmond, Suffolk, Newport News, Virginia Beach
WI (Wave 3) |  |  | Jul 21 (Tue) + Jul 22 (Wed): All 12 locs (6 ambassadors) |  |  |  | TBD to Milwaukee; Neenah; Racine
OK (Wave 3) |  |  | Jul 28 (Tue): Bartlesville + Tulsa (2 ambassadors)
MT (Wave 3) |  |  | Jul 28 (Tue): Butte MT Jul 29 (Wed): Billings MT
NM (Wave 3) |  |  | Jul 28 (Tue): Santa Fe NM Jul 29 (Wed): Albuquerque NM
AL (Wave 3) |  |  |  | Aug 4 (Tue): Pell City + Vestavia (all locations same day) |  |  | Paige & James
CA (Wave 4) |  |  |  | Aug 25 (Tue): slow roll begins (2 locs/wk) | Sep 8–30: Continued slow roll ✓ Done Sep 30 |  | TBD
WA (Wave 4) | [5 empty] | Oct 6 (Tue): Spokane + Olympia Oct 7 (Wed): Seattle + Snohomish Co. Oct 13 (Tue): Walla Walla | TBD
AK (Wave 4) | [5 empty] | Oct 7 (Wed): Anchorage AK | TBD
OR (Wave 4) | [5 empty] | Oct 20 (Tue): Oregon (placeholder) 📍 TBD — COMPLETE | TBD
⛔ NO LAUNCHES: Week of May 25 (Memorial Day) · Week of Jun 29 (Independence Day) · Week of Jul 6 (week after Jul 4) · Jul 7 is a Tuesday — no launch
Wave 1 — Apr/May ¦ FL · TX |  | Wave 2 — June ¦ KY · TN · OH · IN |  | Wave 3 — July ¦ KS · MO · SC · VA · WI · OK · MT · NM · AL |  | Wave 4 — Aug–Oct ¦ CA · WA · AK · OR

## Legend (hidden)
Launch Date Reference — HH Intake Platform Rollout 2026 ¦ Complete by Oct 20, 2026
Wave | State | # Locs | First Launch | Last Launch
Wave 1 | FL | 5 | Tue Apr 28, 2026 | Wed Apr 29, 2026
Wave 1 | TX | 5 | Tue May 12, 2026 | Wed May 13, 2026
Wave 2 | KY | 1 | Tue Jun 16, 2026 | Tue Jun 16, 2026
Wave 2 | OH | 8 | Tue Jun 2, 2026 | Wed Jun 10, 2026
Wave 2 | TN | 2 | Tue Jun 16, 2026 | Tue Jun 16, 2026
Wave 2 | IN | 8 | Tue Jun 23, 2026 | Wed Jun 24, 2026
Wave 3 | KS | 2 | Tue Jul 14, 2026 | Tue Jul 14, 2026
Wave 3 | MO | 1 | Tue Jul 14, 2026 | Tue Jul 14, 2026
Wave 3 | SC | 1 | Tue Jul 14, 2026 | Tue Jul 14, 2026
Wave 3 | VA | 4 | Tue Jul 14, 2026 | Wed Jul 15, 2026
Wave 3 | WI | 12 | Tue Jul 21, 2026 | Wed Jul 22, 2026
Wave 3 | OK | 2 | Tue Jul 28, 2026 | Tue Jul 28, 2026
Wave 3 | MT | 2 | Tue Jul 28, 2026 | Wed Jul 29, 2026
Wave 3 | NM | 2 | Tue Jul 28, 2026 | Wed Jul 29, 2026
Wave3 | AL | 2 | Tue Aug 4, 2026 | Tue Aug 4, 2026
Wave 4 | CA | 10 | Tue Aug 25, 2026 | Wed Sep 30, 2026
Wave 4 | WA | 5 | Tue Oct 6, 2026 | Tue Oct 13, 2026
Wave 4 | AK | 1 | Wed Oct 7, 2026 | Wed Oct 7, 2026
Wave 4 | OR | 1 | Tue Oct 20, 2026 (placeholder) | Tue Oct 20, 2026

## Discovery Survey Results (hidden)
ED Survey Received | RME/AME Survey Received | REGION | Branch Code | Branch Name | Street | City | State | Phone | Fax | Home Health Branch ID (M0016) | Time Zone ID | Tech Training | Breakout Training | GO-LIVE | RVP/RME/ED Rollout Notes | Require Extra Attention | Feb 2026 | # of 2025 Months <-5% Budget | 2026 CHAP Survey Anticipated | Benefits (25%) | Efforts (25%) | Risks (25%) | Alignment (25%) | Score | ED SURVEY | 1. Program Name | 2. Branches | 3. Manage increase in referrals/admissions with current clinical staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 4. Current Field Clinician Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. VBE Status | 6 SCORE | 7. Major Initiatives | 7 SCORE | 8. Team response to new process or tool | 8 SCORE | 9. Groups requiring more change management | 9 SCORE | 10. Challenging referral source relationships | 10 SCORE | 11. Task "Monitor referral portals & respond to new referrals" | 11 SCORE | 11. Task "Gather missing referral documents & patient information" | 11 SCORE | 11. Task "Create chart in HCHB for new referral" | 11 SCORE | 11. Task "Complete "Review External Referral Request" workflow in HCHB" | 11 SCORE | 11. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 11 SCORE | 11. Task "Schedule patient's SOC visit in HCHB" | 11 SCORE | 11. Task "Make welcomes/readiness calls" | 11 SCORE | 11. Task "Lead referral huddles" | 11 SCORE | 12. Divided duties | 12 SCORE | 13. Cross functional roles | 13 SCORE | 14. Growth team authority to accept referrals with no ED/DCS input | 14 SCORE | 15. When do welcome calls occur? | 15 SCORE | 16. Handling of urgent or high priority referrals? | 16 SCORE | 17. Weekend Schedulers | 17 SCORE | 18. Weekend Referral Management | 18 SCORE | 19. Additional Input | RME/AME Survey | 1. Market Name | HH Locations | 3. Manage increase in referrals/admissions with current growth staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. All Portals Used in Order | 7. Portals NOT used | 6 & 7 SCORE | 8. Portals Used Not Listed in #7 | 8 SCORE | 9. Payors requiring extra op steps | 9 SCORE | 10. VBE Status | 10 SCORE | 11. Major initiatives | 11 SCORE | 12. Team Response to New Process/Tool | 12 SCORE | 13. Groups requiring more change management | 13 SCORE | 14. Referral source creating challenges | 14 SCORE | 15. Task " Monitor referral portals & respond to new referrals" | 15 SCORE | 15. Task "Gather missing referral documents & patient information" | 15 SCORE | 15. Task "Create chart in HCHB for new referral" | 15 SCORE | 15. Task "Complete "Review External Referral Request" workflow in HCHB" | 15 SCORE | 15. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 15 SCORE | 15. Task "Schedule patient's SOC visit in HCHB" | 15 SCORE | 15. Task "Make welcomes/readiness calls " | 15 SCORE | 15. Task "Lead referral huddles" | 15 SCORE | 16. Divided duties | 16 SCORE | 17. Cross functional roles | 17 SCORE | 18. Growth team authority to accept referrals with no ED/DCS input | 18 SCORE | 19. When do welcome calls occur? | 19 SCORE | 20. Handling of urgent or high priority referrals? | 20 SCORE | 21. Weekend Schedulers | 21 SCORE | 22. Weekend Referral Management | 22 SCORE | 23. Additional Input
|  | 50 | A00 | VESTAVIA AL (CC1028) | 1900 INTERNATIONAL PARK DR STE 250 | BIRMINGHAM | AL | (205) 313-2800 | (205) 313-2801 | N | (GMT - 06:00) CENTRAL | [5 empty] | 1021 | [7 empty] | Kerri Couch | Vestavia AL | No | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Risk for rehospitalization, ORTHO, IV, Wound, New 02 | 1 | L1 No Plan for 2026 | 1 | We currently have 3 new DCS's, 1 on leave and 2 with 6m experience. We have hired over 10 new nurses for the field currently in training. | 1 | L1 Open to Change Adapt Quickly | 1 | Scheduling | 1 | VA Getting Auth Approvals | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Referral Coordinators and DCS will process non-admits, RC will do it if it is done prior to scheduling the patient out to a clinician. We have RN clinical coordinator that will do readiness calls and run the scheduling meeting at 3:30 to triage all of admissions. | 2 | Our Schedulers work a day on the weekend and take a day off during the week, Our DCS take call during the weeknights and on the weekends work at their computers all day Saturday and Sunday. Document Specialist work weekends. | 2 | Yes | 1 | Once the SOC comes to workflow | 0 | growth team member usually gives us a heads up that it is coming in an email so we are prepared. We have a scheduling meeting daily at 3:30. It is on our grid already and we schedule it out once it comes to workflow and it is confirmed. | 1 | Yes | 1 | Document Specialists | 1 | The weekends are the worst for missed referrals and/or slow process for getting them to workflow to assign to the clinicians in the field. We use a excel spreadsheet to put the patients on daily and it could be anywhere from 40-100 patients on that grid depending on the day. So, we get a ton of emails to follow for the patient to enter on that grid. | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
|  | 50 | A01 | PELL CITY AL (CC1027) | 2401 STEMLEY BRIDGE RD STE 7 | PELL CITY | AL | (205) 884-7202 | (205) 313-2801 | N | (GMT - 06:00) CENTRAL | [5 empty] | 666 | [7 empty] | Christina Isbell | Pell City AL | None | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | pt acuity criteria, referral partner consideration, time sensitive care coordination | 1 | H3 Currently on VBE | 3 | Annual Skills check off March 10-11, none other scheduled at this time | 0 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators, Scheduling, Document Specialists | 3 | None at this time | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | ED/DCS | 0 | referral portals- Growth, gather missing info- referral coordinator, non-admit reason in HCHB- DCS/ED, Schedule pt- DCS/ED, Make welcome calls- DCS/ED, Lead referral Huddles- Referral coordinator & Growth management | 3 | We currently have a scheduler on the weekends to assist DCS with schedules, we have RC/Doc specialists managing portals and keying referrals, | 2 | No | 2 | within the first 48 hrs referral received | 0 | management notifies PCC of high priority to schedule urgently | 1 | Yes | 1 | Doc specialists, RC | 0 | None | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
|  | 52 | A02 | PORTAGE MI (CC3146) | 5136 LOVERS LN STE 200A | PORTAGE | MI | (269) 459-3700 | (855) 384-1890 | N | (GMT - 05:00) EASTERN | [5 empty] | 367 | [7 empty] | Stephanie Watkins | Compassus Home Health - Portage MI | NA | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Infusion, Tube Feeding, Chest Tubes, Pleurx or Aspira drains, Chole Tubes, Nephrostomy Tubes, Tracheostomy, new to Self Catheterization, some wound care patients as they all may need same day care and education. | 1 | L1 No Plan for 2026 |  | We are actually just starting our Commure Pilot, Realignment of agency activities and trainings to standardize across the company in April and May. | 0 | M2 Some Coaching and Reinforcement |  | Growth, Scheduling, ED/DCS | 3 | Beacon Hospitals just went online with a new EMR and referral portal of Ensocare but they are not functioning efficiently in those platforms at this time impacting timeliness of referral updates, orders and even notification of discharges. They have no current format to write home care orders in their EMR and using a paper form and faxing but frequently forget, they are not routinely confirming assignment of referrals to agency in Ensocare and are not utilizing the system for updates or communication. Previously when they were Ascension facilities, we had access in the version of Cerner being used and could assist their Care Management and Discharge Planning teams in getting the necessary information to agency timely. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | Referral Coordinators also monitor referral portals and respond to new referrals on the weekends. ED/DCS assist with assigning patient's SOC visit in HCHB on weekends or afterhours, Scheduling assists Growth PTC with welcome and readiness calls. | 0 | As above we have no weekend scheduling so ED/DCS covering the Administrator on Call role assigns out needed SOC/ROC visits for weekend and Mondays. Will also sometimes work to track down referral information but does not have access to all needed portals or EMRs as growth does. The Admin on Call also responds to the referral emails if agency is unable to accept a referral for follow up by the referral coordinators/growth team. | 1 | Yes | 1 | When the discharge is confirmed and the referral is complete. | 0 | Growth notifies the team when received with anticipated DC date and location to confirm branch can safely accept and admit. | 0 | No | 2 | Referral Coordinators, occasionally growth will assist if they are expecting information on the weekends who then email th | 0 | None | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
|  | 52 | A03 | GRAND BLANC MI (CC3145) | 5445 ALI DR DEPT 500 | GRAND BLANC | MI | (800) 922-5220 | (844) 552-6193 | N | (GMT - 05:00) EASTERN | [5 empty] | 443 | [7 empty] | Cynthia Voelker | [55 empty] | Ronald Boggia
|  | 52 | A04 | WARREN MI (CC3144) | 28120 DEQUINDRE RD | WARREN | MI | (586) 913-0345 | (844) 526-5624 | P | (GMT - 05:00) EASTERN | [5 empty] | 557 |  | November 2026-February 2027 | [5 empty] | Cynthia Voelker | [55 empty] | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
|  | 52 | A06 | TAWAS CITY MI (CC3147) | 808 W CEDAR ST BLDG A | STANDISH | MI | (989) 310-4003 | (844) 445-7729 | N | (GMT - 05:00) EASTERN | [5 empty] | 294 | [7 empty] | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
|  | 53 | A07 | NEENAH WI (CC5824) | 816 W WINNECONNE AVE | NEENAH | WI | (920) 727-2000 | (844) 887-0047 | P | (GMT - 06:00) CENTRAL | [5 empty] | 595 | [7 empty] | Brenda Lefeber | Neenah Wi | Green Bay WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A08 | STURGEON BAY WI (CC5828) | 231 KEEL CT | STURGEON BAY | WI | (920) 695-3150 | (844) 887-0706 | N | (GMT - 06:00) CENTRAL | [5 empty] | 118 | [7 empty] | Marla Wills | AAH w/Compassus Sturgeon Bay | N/A | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | IV patient, pleurex, CHF/COPD | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | NA | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Referral Coordinators | 1 | Ed/DCS | 0 | NA | 0 | NA | 0 | No | 2 | After Intake | 0 | By Ed Direction | 0 | No | 2 | Admin on Call | 1 | N/A | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A09 | MARSHFIELD WI (CC5822) | 303 W UPHAM ST STE 208 | MARSHFIELD | WI | (715) 301-7260 | (844) 887-0042 | P | (GMT - 06:00) CENTRAL | [5 empty] | 375 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A10 | PLOVER WI (CC5825) | 1840 POST RD STE 5 | PLOVER | WI | (715) 301-7260 | (844) 887-0042 | 52Q7189001 | (GMT - 06:00) CENTRAL | [5 empty] | 243 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A11 | WAUSAU WI (CC5829) | 2600 STEWART AVE STE 160 | WAUSAU | WI | (715) 301-7260 | (844) 887-0042 | 52Q7189002 | (GMT - 06:00) CENTRAL | [5 empty] | 247 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A12 | RHINELANDER WI (CC5827) | 111 E DAVENPORT ST STE 101 | RHINELANDER | WI | (715) 301-7210 | (844) 887-0049 | P | (GMT - 06:00) CENTRAL | [5 empty] | 137 | [7 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A13 | ARBOR VITAE WI (CC5821) | 1571 HIGHWAY 51 N STE C | ARBOR VITAE | WI | (715) 301-7200 | (844) 885-3825 | 52Q7218001 | (GMT - 06:00) CENTRAL | [5 empty] | 112 | [7 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A14 | MILWAUKEE WI (CC5823) | 135 S 84TH ST STE 150 | MILWAUKEE | WI | (414) 455-9500 | (844) 887-8721 | P | (GMT - 06:00) CENTRAL | [5 empty] | 458 | [7 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A15 | RACINE WI (CC5826) | 13200 GLOBE DR STE 228 | MOUNT PLEASANT | WI | (262) 417-9393 | (844) 887-8721 | 52Q7187001 | (GMT - 06:00) CENTRAL | [5 empty] | 346 | [7 empty] | Melissa Steger | Racine | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H1 Well Staffed |  | Episodic, infusion, ortho, wound | 2 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | No | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | HHCC and CTC make welcome calls. PTC monitors referral portals and gather info as needed. | 1 | If schedulers are unable to contact patients, our PTC will sometimes assist with contacting. | 1 | No | 2 | Once the referral is 'pushed to scheduling' and is in our scheduler's workflow, the scheduler will make the readiness call. The growth team members make their welcome calls prior to this step. | 1 | ED and AME involvement as needed | 0 | Yes | 1 | RC team, AOC, and scheduler | 0 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 52 | A16 | BURNET TX (CC5233) | 309 INDUSTRIAL BLVD STE 2 | BURNET | TX | (512) 756-7511 | (512) 756-8046 | P | (GMT - 06:00) CENTRAL | [5 empty] | 140 |  | May-August | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 52 | A17 | AUSTIN TX (CC5235) | 9430 RESEARCH BLVD STE II310 | AUSTIN | TX | (512) 863-3842 | (844) 809-2238 | 67Q7154001 | (GMT - 06:00) CENTRAL | [5 empty] | 332 |  | May-August | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 52 | A18 | KYLE TX (CC5234) | 1300 DACY LN STE 170 | KYLE | TX | (512) 549-3490 | (888) 529-6396 | P | (GMT - 06:00) CENTRAL | [5 empty] | 173 |  | Feb-June 2026 | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 52 | A19 | WACO TX (CC5236) | 510 N VALLEY MILLS DR STE 504 | WACO | TX | (254) 523-6970 | (844) 308-5076 | P | (GMT - 06:00) CENTRAL | [5 empty] | 394 |  | April-July 2026 | [5 empty] | Wendi Pack | Ascension at Home Waco TX | NA | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Immediate skilled needs such as wound care, IV, or Ortho patients. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Once the chart has been green tagged. | 1 | Growth member lets the DCS and schedulers know | 0 | No | 2 | Intake checks the portals and the DCS on call monitors the emails/ schedules out the admissions. | 0 | NA | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 51 | A20 | ANDERSON IN (CC2311) | 600 CORPORATION DR STE 104 | PENDLETON | IN | (765) 203-2616 | (844) 724-7537 | P | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 210 |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A21 | KOKOMO IN (CC2315) | 2626 S WEBSTER RD STE B | KOKOMO | IN | (765) 252-1600 | (844) 724-7537 | 15Q7059001 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 327 |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A22 | INDIANAPOLIS IN (CC2314) | 8909 PURDUE RD STE 107 | INDIANAPOLIS | IN | (317) 829-2122 | (844) 724-7536 | P | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 319 | [7 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A24 | Bloomingham IN (Bedford) | 1324 K ST STE 150 | BLOOMINGTON | IN | (812) 578-3260 | (812) 276-1244 | 15Q7083004 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful | Bedford IN – smaller program with only 1 DCS and BOC in the office – DCS in partN Vernon IN – smaller program with only 1 DCS and BOC I the office – tend to have challenges when new technology is introducedicular is more resistive to change and they have been resistant in the past to changing anything with referral management | 89 | [7 empty] | Darla Bell | Evansville/Bloomington | Bloomington (managed by Darla)is actually branch of Idianapolis managed by Suchi | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A25 | NORTH VERNON IN (CC2316) | 2337 NICHOLAS CT STE C | SEYMOUR | IN | (812) 953-4120 | (812) 346-9889 | 15Q7083003 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 43 | [7 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A26 | EVANSVILLE IN (CC2313) | 7321 EAGLE CREST BLVD STE A | EVANSVILLE | IN | (812) 774-9760 | (812) 475-1739 | N | (GMT - 06:00) CENTRAL |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 298 |  | Jan-April 2026 | [5 empty] | Darla Bell | Evansville/Bloomington | None | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | We are in the CHAP window in Evansville 1st quarter. | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 52 | A27 | WICHITA KS (CC2504) | 301 N MAIN ST STE 950 | WICHITA | KS | (316) 268-8588 | (316) 264-1265 | N | (GMT - 06:00) CENTRAL | [5 empty] | 517 | [7 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 52 | A28 | PITTSBURG KS (CC2503) | 200 E CENTENNIAL DR STE 13 | PITTSBURG | KS | (620) 231-3088 | (844) 724-7530 | N | (GMT - 06:00) CENTRAL | [5 empty] | 111 | [7 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 52 | A29 | TULSA OK (CC4514) | 4612 S HARVARD AVE STE C | TULSA | OK | (918) 747-7901 | (844) 724-7540 | N | (GMT - 06:00) CENTRAL | [5 empty] | 300 |  | April-July 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | St John's Tulsa- unhappy with not being in network with patient's insurance | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 52 | A30 | BARTLESVILLE OK (CC4513) | 3061 SE WASHINGTON BLVD | BARTLESVILLE | OK | (918) 907-3010 | (844) 721-8184 | P | (GMT - 06:00) CENTRAL | [5 empty] | 146 |  | Feb-June 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 53 | A50 | ALBUQUERQUE NM (CC4004) | 7770 JEFFERSON ST NE STE 110 | ALBUQUERQUE | NM | (505) 881-0425 | (505) 349-3363 | P | (GMT - 07:00) MOUNTAIN | [5 empty] | 244 | [7 empty] | Raechel Dominguez | Region 53- New Mexico(Albuquerque and Santa Fe) | Albuquerque & Santa Fe | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV ABX, wound vac, ortho | 1 | L1 No Plan for 2026 |  | NA | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Welcome call as soon as referral is received, readiness call is done once referral comes to scheduling prior to assigning to clinician. | 1 | They are flagged and take priority. | 0 | No | 2 | ED | 1 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A51 | BILLINGS MT (CC3506) | 490 N 31ST ST STE 130B | BILLINGS | MT | (406) 652-8883 | (406) 652-8879 | N | (GMT - 07:00) MOUNTAIN STANDARD | [5 empty] | 205 | [7 empty] | Joanne Wirtjes | Billings MT | NA | Strongly Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | ortho pts, IV abx pts, cardiac pts | 1 | L1 No Plan for 2026 |  | New ED in 1/2026, new DCS in 3/26, rapid growth over last couple of months - plan on continuing growth, added 6 new clinicians in 2 months. | 2 | L1 Open to Change Adapt Quickly |  | None | 0 | VA - awaiting auth for SOC of pts and bundled and non-bundled for patients. | 1 | Growth | 0 | Referral Coordinators | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | EDDCS | 1 | Referral Coordinators | 1 | not sure whose task to build the hchb chart | 0 | NA | 0 | Yes | 1 | Ideally prior to chart getting pushed to scheduling | 0 | discussed in daily huddle/referral meeting and via TEAMS | 0 | No | 2 | AC Team | 0 | None | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A52 | BUTTE MT (CC3508) | 19 DISCOVERY DR | BUTTE | MT | (406) 494-0039 | (406) 494-0032 | N | (GMT - 07:00) MOUNTAIN STANDARD | [5 empty] | 79 |  | Jan-April 2026 | [5 empty] | Jacqueline Mathews | Compassus Home Health - Butte MT | None | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Wound care, fresh surgical patient discharging from the hospital and most patients coming out of the hospital. | 1 | L1 No Plan for 2026 |  | 2 new nurses will be training over the next couple of months so it would be best to roll out after they are trained. Also have new PTC who needs to feel more comfortable with her role. | 2 | M2 Some Coaching and Reinforcement |  | Growth, Referral Coordinators | 2 | We need improved referral source relationships so we can generate referrals needed | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | At times the ED will enter the ERR workflow and enter non-admit reason if it hasn't been done timely At time the ED will schedule patients if scheduler is not available. Make welcome calls is growth, readiness calls is scheduling | 2 | ED is also the DCS and BOC is also the scheduler | 2 | Yes | 1 | HCC is responsible for any bedsides, PTC is responsible for welcome call. BOC/scheduler is responsible for readiness calls once referral is complete and ready to be scheduled according to growth team. | 0 | Discussed in daily huddle, make a plan as to when patient can be admitted. | 0 | No | 2 | Administrator on call if needed | 1 | HHCC is new to having PTC, having a hard time relinquishing duties | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 50 | A53 | JACKSONVILLE FL (CC1801) | 7235 BENTLEY RD STE 236 | JACKSONVILLE | FL | (904) 861-2612 | (904) 503-9690 | N | (GMT - 05:00) EASTERN | [5 empty] | 360 |  | Jan-April 2026 | [5 empty] | Daisy | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 53 | A54 | SANTA FE NM (CC4005) | 1692B HOSPITAL DR STE 102 | SANTA FE | NM | (505) 629-4180 | (505) 814-1673 | P | (GMT - 07:00) MOUNTAIN | [5 empty] | 76 | [7 empty] | Raechel Dominguez | Region 53- New Mexico(Albuquerque and Santa Fe) | Albuquerque & Santa Fe | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV ABX, wound vac, ortho | 1 | L1 No Plan for 2026 |  | NA | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Welcome call as soon as referral is received, readiness call is done once referral comes to scheduling prior to assigning to clinician. | 1 | They are flagged and take priority. | 0 | No | 2 | ED | 1 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 50 | A55 | PENSACOLA FL (CC1802) | 1115 E GONZALES ST STE 1001 | PENSACOLA | FL | (850) 266-7235 | (850) 502-5417 | N | (GMT - 05:00) EASTERN | [5 empty] | 275 | [7 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 52 | A56 | SMITHVILLE TX (CC5238) | 150 SETTLEMENT DR STE F2 | BASTROP | TX | (512) 782-0382 | (512) 795-4371 | 67Q9048001 | (GMT - 06:00) CENTRAL | [5 empty] | 109 |  | Feb-June 2026 | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 53 | A57 | GREEN BAY WI (CC5834) | 480 PILGRIM WAY STE 1250 | ASHWAUBENON | WI | (920) 282-9829 | (715) 203-0627 | 52Q7009002 | (GMT - 06:00) CENTRAL | [5 empty] | 88 | [7 empty] | Brenda Lefeber | Green Bay WI | Neenah WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 50 | A58 | PANAMA CITY FL (CC1803) | 2211 S HIGHWAY 77 STE 203A | LYNN HAVEN | FL | (850) 250-1366 | (850) 558-4974 | N | (GMT - 06:00) CENTRAL | [5 empty] | 88 |  | October 2026 - January 2027 | [5 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 53 | A59 | SHEBOYGAN WI (CC5833) | 2124 KOHLER MEMORIAL DR STE 200 | SHEBOYGAN | WI | (920) 547-4126 | (877) 376-3117 | 52Q7187002 | (GMT - 06:00) CENTRAL | [5 empty] | 111 | [7 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A64 | CHIPPEWA FALLS WI (CC5835) | 134 W COLUMBIA ST STE 2 | CHIPPEWA FALLS | WI | (715) 861-8353 | (715) 203-0273 | 52Q7189003 | (GMT - 06:00) CENTRAL | [5 empty] | 130 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 51 | A67 | LAFAYETTE IN (CC2319) | 703 N 36TH ST | LAFAYETTE | IN | (765) 294-2053 | (765) 294-2186 | 15Q7083002 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful | Lafayette IN – close to 100 census with only 1 BOC and DCS in office – BOC specifically had challenges with technology so may need a bit more hand holding | 84 | [7 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 52 | A68 | ALPENA MI (CC3153) | 109 N SECOND AVE STE 202 | ALPENA | MI | (989) 272-8894 | (989) 607-0679 | PENDING | (GMT - 05:00) EASTERN | [5 empty] | 2 | [7 empty] | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
|  | 51 | A74 | CENTERVILLE TN (CC5111) | 135 E SWAN ST | CENTERVILLE | TN | (931) 729-4500 | (931) 729-9000 | N | (GMT - 06:00) CENTRAL |  |  |  | TN – 2 programs – Angie Corman, Nashville ED | Centerville TN – due to size and overall challenge with technology and change – very rural market | 55 | [7 empty] | Brandi Tayloe-Jones | Centerville TN | NA | Strongly Agree |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | Clinical needs and acuity such as IV, wounds, etc. | 1 | M2 2026 GoLive |  | VBE launch in June/July | 1 | M2 Some Coaching and Reinforcement |  | Field Clincians | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | DCS does quite a bit with referral management and no admits | 1 | BOC also performs scheduling functions due to size of program. | 1 | Yes | 1 | After the referral is sent to scheduling. | 1 | The DCS is very active and pushes the referrals through as needed. | 1 | Yes | 1 | There is a regional a scheduling and growth rotation. | 0 | The size of the program can limit functions at times. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A75 | NASHVILLE TN (CC5112) | 402 BNA DR STE 320 | NASHVILLE | TN | (615) 367-1656 | (615) 367-1659 | N | (GMT - 06:00) CENTRAL |  |  |  | TN – 2 programs – Angie Corman, Nashville ED |  | 176 | [7 empty] | Angela Corman | Nashville TN | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | IV antibiotic, Wound Vac, Recent Joint Replacement, LVAD, Cardiac Drip | 1 | M2 2026 GoLive |  | VBE to go live 5/28 currently hiring for increase in referrals | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | Referral Huddles are lead by RC, Scheduler and or ED. Welcome calls are being made by growth, then scheduler/clinicians | 2 | Growth and schedulers work weekend rotations to cover region, ED currently doing large portion of DCS leadership such as payroll etc, all staff under ED. 2 new DCS's have been hired and training all DCS's to take over those responsibilities for clinical team leadership. BOC is cross trained to manage scheduler workflow, Scheduler cross trained to complete some BOC responsibilities. | 1 | Yes | 1 | Growth contacts patient to verify demographics and makes initial welcome call. Clinicians/Scheduler call for readiness. | 1 | Growth informs team of priority admission and intake/scheduler/ED ensure process is completed smoothly | 0 | Yes | 1 | Growth from the region and weekend RCs | 0 | None | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 54 | A76 | GREENVILLE SC (CC4909) | 1836 W GEORGIA RD | SIMPSONVILLE | SC | (864) 233-5300 | (864) 233-4873 | N | (GMT - 05:00) EASTERN | [5 empty] | 371 | [7 empty] | Regina Ervin | Bon Secours Home Care by Compassus - Greenville, SC | None | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H2 Managing but it's tight |  | A patient with high acuity discharging same day(Pleurex patients, IV abx, tube feeds, TPN, etc.) | 1 | H3 Currently on VBE |  | None at this time | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | We have a large Total Ortho Program that we are committed to. We work with this group closely and process referrals quicky to see pateint timely. Some of these patients go home same day of surgery and we try to see patient next day. We are on the hospital committee and have built a strong relationship with this program. We would want to continue to function well for this group. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | RC's complete referral portals and respond to new referrals on the weekend. Readiness calls can be done by growth or scheduling | 1 | RC's complete growth responsibilities on the weekend. There are times DCSs schedules visits on the weekend. | 1 | Yes | 1 | Typically, when growth completes demos | 1 | Discussed during huddle with growth and scheduling to try and get patient seen timely. DCS and EC is on call to discuss barriers. | 0 | No | 2 | RCs & DCSs | 1 | Communication is strong between our team (intake, growth, schedulers, leaders) and we would not want to lose that. | Kimberly Manson | Greenville SC | Greenville SC only | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | Higher acuity patients that would better seen within 24-hour timeframe - his include new oxygen, IV antibiotics, new tube feeds, and TPN patients. | 1 | Intake (NaviHealth/Curaspan);Ensocare;Other;Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Watershed | Referrals are not received directly via all scripts, AIDA, Aidin, or Watershed. | 3 | No - unless faxes will no longer create an ERR within HCHB. There are still referrals that are sent to our branch by fax. | 0 | Humana is one that I am aware of, not sure if there are others. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Referral Coordinators | 1 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCs | 0 | Growth is primary for portals during non-holiday and business hours, Referral Coordinators are responsible for these portals during holiday and non-business hours. Growth typically makes welcome/readiness calls. If they are unable to reach a patient during scheduling, the scheduling team will contact patient. | 1 | None | 0 | Yes | 1 | When Growth has accepted the referral and is calling to verify physician and demographics. This is approximately 24-48 hours prior to admission. | 1 | They are reviewed by Growth and discussed with DCS/ED/scheduling to coordinate care and ensure that the patient is seen within a timely manner and any barriers are discussed as a team. This also happens during huddle calls. | 0 | Yes | 1 | The Referral Coordinators manage referrals and coordinate with the weekend DCS on declining or accepting. They also work with the Sunday scheduler to address any additional needs. | 0 | It would be great to continue to communicate and coordinate care across multiple teams, but ensuring that there is less patient communication via email/Teams would be GREAT.
|  | 54 | A77 | PADUCAH KY (CC2602) | 225 MEDICAL CENTER DR STE 203 | PADUCAH | KY | (270) 415-3600 | (270) 936-8620 | P | (GMT - 06:00) CENTRAL | [5 empty] | 336 | [7 empty] | Renee Wurth | Mercy Health Homecare by Compassus - Paducah, KY | N/A - (submitted for Metropolis IL branch but have not yet received approval) | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | High Priority patients are those that are discharging from acute hospitals, as well as, those who had outpatient orthopedic surgery the day before. We also have many wound vacs/infusion patients who have specific times/needs that are quick turnarounds from referral. | 1 | L1 No Plan for 2026 | 1 | We have applied to have a branch in Metropolis, IL but have not received approval from CMS at this point. Otherwise no major known events. | 1 | M2 Some Coaching and Reinforcement | 2 | Field Staff | 0 | Our orthopedic physicians send referrals early and we have to follow up regularly with them to ensure surgeries remain scheduled and that we are out to see the patient the next day. Vanderbilt and Barnes Jewish often send us requests and it takes days of follow up to get confirmation of patient choosing us (occasionally even after patient is already discharged). We hold spots on our scheduling grid for these patients, requiring a lot of attention and follow up. Multiple local physicians' offices send referrals at the very end of the day making it difficult to process them timely for the referral coordinators. | 3 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Referral Coordinators cover portals on weekends and attend to faxed referrals. RCs and ED/DCS assist with gathering missing referral information as needed. Growth makes welcome calls and Scheduling makes readiness call. Scheduler assists growth in referral huddles with current avialability and episodic percentage of referrals admitted for month to date. | 1 | Referral Coordinators cover weekends for referrals. Administrator on Call (DCS) covers scheduling from Friday at 5pm to Monday at 8 am. | 1 | Yes | 1 | Welcome call is the day the referral is accepted. Readiness call occurs the day before admission (Friday before for Monday admission). | 0 | During office hours, communication comes into DCS/ED and is coordinated by the DCS that is on call for the week. Administrator on call (DCS) coordinates the process to get the patient's chart to the clinician if it is after hours or on the weekends. | 0 | No | 2 | Referral Coordinators manage the referrals and Administrator On Call is the accept/decline decision maker. | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout. | Farrah Gay | Paducah KY | Paducah, KY and we have applied for Metropolis, IL to be a branch. | Neither Agree or Disagee |  | L1 Well Staffed |  | H3 We're stretched thin | 3 | M2 Managing but it's tight |  | Complex, unstable or acute needs requiring urgent intervention to prevent hospitalization, nursing home placement or further decline. | 1 | Epic Carelink;Aidin;Other;Ensocare;Referral Management (All scripts);AIDA;Intake (NaviHealth/Curaspan);Watershed | #5-8 are not | 4 | Not that I am aware of. | 0 | VA - required auth at intake before we can start care. Trisha Curtis is our insurance manager and looking into this if you would like to circle back with her for more information. | 1 | L1 No Plan for 2026 |  | We've requested to make the Metropolis, IL location a branch. The application was submitted in 2024. | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Referral sources seem to understand the universal staffing capacity issue among all healthcare, so they have not verbalized as much frustration recently as they have in the past. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | Make readiness call - completed by scheduling Lead referral huddles - completed by both growth and branch | 0 | RC/intake covers weekend referral management. Administrator on call covers scheduling and accepting/decline. | 0 | Yes | 1 | Welcome call - day the referral is accepted by growth/patient PCC readiness - day prior to start of care except for weekends. | 1 | Notification to administrator on call who then communicated and schedules | 1 | No | 2 | RC/intake and Administrator on call | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout.
|  | 50 | A78 | TAMPA FL (CC1804) | 137 S PEBBLE BEACH BLVD STE 203 | SUN CITY CENTER | FL | (813) 443-5566 | (813) 374-6997 | N | (GMT - 05:00) EASTERN | [5 empty] | 90 | [7 empty] | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 50 | A79 | ST PETERSBURG FL (CC1805) | 11001 ROOSEVELT BLVD N STE 100 | St. Petersburg | FL | (727) 577-7990 | (727) 576-6138 | N | (GMT - 05:00) EASTERN | [5 empty] | 95 | [7 empty] | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 54 | A80 | RICHMOND VA (CC5509) | 2603 NINE MILE RD STE 200 | RICHMOND | VA | (804) 627-5200 | (804) 627-5208 | N | (GMT - 05:00) EASTERN | [5 empty] | 340 | [7 empty] | Allison Bohn | Bon Securs Home Care by Compassus, Richmond VA | NA | Disagree |  | H3 We're stretched thin |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV, LVAD, some surgeries depending on MD, certain wound care | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | Growth | 1 | BSMH Partner creates the most challenges. Expectations to accept all patients are high but in return we are not consistently given first right of refusal if patient has no preference. | 1 | Growth | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Depending on where the referral is coming from, Growth is also responsible for gathering missing referral documents and patient information | 0 | None | 0 | Yes | 1 | Scheduling | 0 | Communication during huddle, in emails and on scheduling grid | 0 | Yes | 1 | Referral Coordinator | 0 | None | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
|  | 54 | A81 | SUFFOLK VA (CC5513) | 7007 HARBOUR VIEW BLVD STE 114 | SUFFOLK | VA | (757) 889-4663 | (757) 393-1348 | P | (GMT - 05:00) EASTERN | [5 empty] | 273 | [7 empty] | Erica Dejesus | Bon Secours with Compassus - Suffolk | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
|  | 54 | A83 | VIRGINIA BEACH VA (CC5515) | 184 BUSINESS PARK DR STE 100 | VIRGINIA BEACH | VA | (757) 889-4663 | (757) 393-1348 | P | (GMT - 05:00) EASTERN | [5 empty] | 99 | [7 empty] | Erica DeJesus | Virginia Beach VA | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
|  | 54 | A84 | LORAIN OH (CC4415) | 3500 KOLBE RD | LORAIN | OH | (440) 960-4000 | (440) 960-3359 | N | (GMT - 05:00) EASTERN | [5 empty] | 182 | [7 empty] | Andrea Faurot | Lorain OH | N/A | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV, Wound, Pleurex or chest tubes, Tube feed, TPN Total Joint patients, nephrostomy, trach patients, New O2, CABG | 1 | L1 No Plan for 2026 |  | CHAP survey pending immediately | 1 | M2 Some Coaching and Reinforcement |  | Unsure | 0 | Yes the Lorain BSMH market needs lots of education on why and they want a smoother process. They oppose change often, but sometimes will come along as long as there is good communication and collaboration. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Growth | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Growth and intake often share responsibilities or cover for each other | 1 | RN Coordinator is also in on call rotation and assists schedulers back up as well as Home Health Admin Assistant | 1 | Yes | 1 | Once sent to scheduling | 0 | escalated to DCS or ED | 0 | No | 2 | Intake & Growth | 0 | Clear expectations of responsibility and throughput diagram. So expectations are clear. Our schedulers are part of a bargaining unit, so any changes that could impact them—such as modifications to their job descriptions or working hours—would need to be reviewed and vetted through the bargaining unit. With negotiations starting next week, it would be helpful to identify any potential changes proactively so we can address them in advance. This will ensure we remain aligned with the bargaining process and avoid any delays. If there is someone else who should be looped in or involved in these discussions, please feel free to connect them. Brian Jackson and Yashica Smith is who we use to review any changes that may impact our bargaining team members we get them included early and often to discuss any potential changes. I have looped in Melissa just for transparency. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 54 | A85 | LIMA OH (CC4418) | 959 W NORTH ST | LIMA | OH | (419) 226-9062 | (419) 226-9281 | N | (GMT - 05:00) EASTERN | [5 empty] | 209 | [7 empty] | Cheryl Bechtel | Mercy Health Homecare by Compassus Lima Ohio 45805 | No | Strongly Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Skilled need IV, Wounds, Drains | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | Insurance Authorization | 1 | No | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Other | 1 | ED/DCS | 0 | n the Lima Market the scheduler is the first person to call the patient to set up a home visit. Would be nice to have the growth team verify information prior to the scheduler. This would save time as the scheduler then has to reach back to the growth team to obtain the information | 0 | DCS will assist with scheduling if scheduler is on PTO Training Clinical RN coordinator to assist with scheduling | 1 | Yes | 1 | When the referral is in the workflow of the scheduler. | 0 | Reviewed by the DCS/ED prior to scheduling if it is known at the time of referral is sent. Growth team doesn't communicate with the intake team sometimes causes problems with priority of the patient needs to be schedule appropriately. | 0 | No | 2 | Growth/Intake | 0 | To improve efficiency and reduce delays in the Start of Care (SOC) process, several opportunities for improvement have been identified within the intake and referral workflow in the Lima market. 1. Growth Team Education on Home Health Qualification and Skilled Need The new Growth Team would benefit from additional and ongoing education regarding: •Qualification criteria for home health services •Identification of skilled need for the patient Currently, referrals are accepted before the clinical skill level and priority of the patient’s needs are fully identified. This can create delays when the patient requires a higher level of clinical prioritization than initially recognized. 2. Insurance Authorization and Verification of Benefits Process Another opportunity for improvement is within the insurance verification and authorization workflow. Currently, delays occur when: •Verification of Benefits is completed, but •The scheduler later needs to re-request insurance authorization, which slows the referral and SOC process. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 54 | A86 | TIFFIN OH (CC4419) | 45 ST LAWRENCE DR | TIFFIN | OH | (419) 455-8180 | (567) 316-2977 | N | (GMT - 05:00) EASTERN | [5 empty] | 73 | [7 empty] | Brandy Fredritz | Mercy Home Care by Compassus Tiffin Ohio | N/A | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day needs, daily needs, IV care, and wound care. | 2 | L1 No Plan for 2026 |  | Hiring full therapy team (versus contracted) in 2026 and adding more nursing staff. Hiring increases started in February 2026 until all positions are filled. | 1 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Schedulers | 2 | When utilizing CarePort, the larger hospitals like OSU and Cleveland Clinic send out "blast referrals" and are poor/slow to respond. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | NA | 0 | Our BOC covers scheduling when our PSC is off. DCS/ED cover scheduling on the weekends. | 1 | Yes | 1 | Varies depending on how quickly the referral is worked and when the SOC is needed. We typically are reactive to our referral process and plot people quickly due to low staffing. Typically, the welcome/readiness call is completed the day before. | 1 | Communication between all Growth/RC/ED/DCS in TEAMS/Email. | 0 | No | 2 | RC/Growth with DCS/ED input | 0 | n/a | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 54 | A87 | YOUNGSTOWN OH (CC4412) | 979 TIBBETTS WICK RD STE A | GIRARD | OH | (330) 480-3776 | (330) 480-4584 | N | (GMT - 05:00) EASTERN | [5 empty] | 373 | [7 empty] | Melanie Boyts | Youngstown OH | NA | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | CABG (open heart), Mitral Valve Replace, Carotid endarterectomry, fem-pop bypass, Infusion patients. orthopedic patients needing same day or next day visit, Enteral/Tub Feed, Trach, wounds/wound vacs, pleurx drains/drains | 1 | L1 No Plan for 2026 |  | Focusing on recruitment and retention. Recruitment in this market has been slow. Starting to make some movement in 2026 but it's really to maintain current operations and not necessarily to support growth. PT/OT/ST extremely difficult to recruit for. Other competitor agencies in area who have established relationships/presence in our JV BSMH hospitals. | 1 | L1 Open to Change Adapt Quickly |  | Growth, Referral Coordinators | 2 | The referral source relationships within the JV BSMH hospitals present operational challenges, particularly within the case management team. A notable issue is the development of relationships with competitor home health agencies within our hospitals, which results in these competitors being prioritized with favorable payors. These dynamics highlight a broader struggle in this market hospital to embrace the joint venture (JV) as a true partnership. From the inception of the JV, the relationships have been challenged, largely tied to efforts in managing payor mix effectively. Several case managers and physicians continue to demonstrate a preference for competitor home health agencies, which undermines the intended collaboration of the JV. While the Area Market Executive in this market has worked diligently to improve relationships and enhance communication around partnerships, significant barriers remain despite these efforts. An additional challenge involves the pressure to accept patients that are often declined by other home health agencies. When explanations are provided about why we cannot accept these patients, resistance frequently arises, escalating the matter to the JV director on the BSMH side. This creates unnecessary friction, adding to the operational complexity. Lastly, the communication dynamic often positions our team as separate from the partnership. This creates the perception that the partnership is one-sided, rather than a true collaborative effort. Addressing these challenges is critical to fostering a unified partnership, optimizing payor relationships, and removing operational inefficiencies. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Confusion from operations team on who is doing what when a referral comes together. Several roles involved in one patient referral. | 0 | scheduling works weekend here. RC's in this market covered growth for a very long time, i think there is still confusion from the operations team on who does what part of a referral when requesting additional information | 1 | Yes | 1 | the scheduler completes this the day before. Done around 330pm when we consider our scheduling grid final. | 0 | Growth team CTC, HHCC and PTC communicate and move patients around on the scheduling grid accordingly. if there is a request to add a patient on outside of what our capacity is DCS and/or ED approve that. | 1 | Yes | 1 | RC & Growth | 0 | The implementation of the new scheduling grid on 12/8/25 has shown promise in aiding payor mix management. However, discharge planning continues to present significant challenges, particularly within the BSMH hospitals. Many patients appear on the scheduling grid for specific discharge dates, but frequently either do not go home as planned or are discharged on unanticipated dates. You expect this if they are discharges planned far in the future but the concern here is you review the patients on the 230pm call set up schedules after 330pm and come in following morning and patient didn't dc. We expect things change and this happens, but it is a more frequent occurrence here. It has been noted that BSMH referrals are sometimes assigned discharge dates that are not definitive, simply to facilitate their acceptance. This creates difficulties in accurately following patients day to day and predicting their actual discharge dates. As a result, we often face situations where patients scheduled for admission do not go home as anticipated. This creates complications in confirming schedules, as clinicians frequently find that patients they planned to admit are not yet discharged. To manage these issues, we attempt to pull other patients forward to fill the vacant spots, though these adjustments often occur too late to avoid disruption. Our clinicians, who operate on a pay-per-visit model, need to begin their day by 8:00 a.m. to maintain productivity and minimize financial impact. To address these ongoing discrepancies, we continue to hold two staffing huddles daily, one in the morning and one in the afternoon. These huddles are essential due to the high rate of unexpected changes in discharge timing and the need for late adjustments. I see an opportunity for improvement in this process by ensuring that patients are added to the schedule once their discharge is confirmed. Concerns with having the necessary attachments and documentation readily available on patient charts. For example, the AVS (After Visit Summary) or DC summaries are frequently requested by SOC clinicians. The DCS often has to pull supporting documentation, such as Face-to-Face supporting documentation, during the coding review process. Addressing these documentation and coordination challenges will be critical to improving the overall efficiency of the referral to scheduling workflow. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 51 | A89 | COLUMBIA MO (CC3437) | 3310 BLUFF CREEK DR STE 106 | COLUMBIA | MO | (573) 370-7577 | (111) 111-1111 | PENDING | (GMT - 06:00) CENTRAL |  |  |  | MO – 1 program – Lisa Walder, Columbia DCS |  | 17 | [7 empty] | Angie Walker | Compassus Columbia MO | NA | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Clinically complex, Increased risk for readmission, timed admission (ex. PICC w/ ABX). | 1 | L1 No Plan for 2026 |  | Leadership changes/staffing changes-current and ongoing | 1 | L1 Open to Change Adapt Quickly |  | ED/DCS | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Interim ED, DCS, RC and HHCC all help monitor referral portal. | 1 | Our BOC is also our scheduler. | 1 | No | 2 | After the referral is considered complete, and before it is scheduled to a clinician. | 0 | That referral gets prioritized and scheduled ahead of a "routine" referral. | 0 | No | 2 | Responsibility shared between our HHCC and the admin on call. | 1 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | None | 0 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 54 | A93 | COLUMBUS OH (CC4424) | 6805 PERIMETER DR FL 1 | DUBLIN | OH | (380) 219-5373 | (380) 219-5374 | P | (GMT - 05:00) EASTERN | [5 empty] | 1468 | [7 empty] | Tabitha Campbell | OHH Columbus OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients new to tube feeds | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Non admits are completed by clinicians-CC- and ED | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 54 | A94 | MANSFIELD OH (CC4426) | 50 INDUSTRIAL DR | LEXINGTON | OH | (419) 484-4688 | (419) 484-4689 | 36Q7615002 | (GMT - 05:00) EASTERN | [5 empty] | 312 | [7 empty] | Tabitha Campbell | Mansfield OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients who have wounds/depending on the severity | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | I do not know who is responsible for entering the Review External Referral Request- possibly intake? | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 54 | A95 | MARION OH (CC4425) | 1713 MARION MOUNT GILEAD RD STE 107 | MARION | OH | (740) 367-3085 | (740) 367-3087 | 36Q7615003 | (GMT - 05:00) EASTERN | [5 empty] | 282 | [7 empty] | Tabitha Campbell | Marion OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients with new ostomy or newer ostomies | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | None | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 54 | A96 | ATHENS OH (CC4427) | 444 W UNION ST STE C | ATHENS | OH | (740) 367-3076 | (740) 367-3093 | P | (GMT - 05:00) EASTERN | [5 empty] | 166 | [7 empty] | Jennifer Frost-Coon | Ohio Health at Home with Compassus - Athens | None | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV patients | 1 | L1 No Plan for 2026 |  | Not that I am aware of at the moment. | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | Yes, we have a few providers who can become challenging with signing the POC/orders/following after they agree to follow. I manage those providers in the moment with education and feedback. | 1 | ED/DCS | 1 | Growth | 0 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | There are three of us in back office that monitor the referral chats and weigh in- it is mostly me that responds. | 1 | With our office being more compact the Scheduler/BOC are the same person in my office and she can schedule patients, she is not clinical. I have a Clinical Coordinator who supports staff and completes and covers for the Scheduler/BOC when she is on PTO. I am the only one in our office who is in the rotation for weekends. | 2 | No | 2 | Specifically I am not so sure- however the welcome call is documented at bedside as well as before the referral is pushed often times. | 1 | Over communication between the HCC and PCC along with back office and ensuring good communication between the patient and the office so that the patient knows the plan too | 0 | No | 2 | The ED and or who is covering in the weekend rotation. A warm hand off is given on Friday going into the weekend with insight into capacity for the weekend and beginning of each week. | 1 | The weekends are the roughest with Intake and communication. Ensure there is good support over a weekend would be my two cents. | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 62 | B01 | Napa Valley CA |  | NAPA | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 150 |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B02 | Humbolt County CA |  | Humbolt | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 129 | [7 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B03 | Sonoma County CA |  | SANTA ROSA | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 141 |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B04 | LA County North CA |  | Burbank | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 500 | [7 empty] | Luiza Chuang | LA North | LA North | Strongly Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | status post hospitalization, IV, TKR, | 1 | H3 Currently on VBE | 3 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Scheduling | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | None | 0 | BOC covers for scheduling if needed | 0 | Yes | 1 | once referral is on schedulers workflow if not if its on MS list | 0 | within 24 hours | 0 | YEs | 1 | Same Team | 0 | we have daily stand downs and we dont see many intake reps joining and we would love to have their presence | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B05 | LA County South CA |  | Torrence | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 364 | [7 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B06 | OC Anaheim CA |  | ANAHEIM | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 600 | [7 empty] | Kathleen Hatfield | PAH with Compassus, OC Anaheim CA | PAH Orange County Mission Viejo | Neither Agree or Disagee |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Tracheostomy care, Infusion, PleurX drain, wound vac, new enteral feedings | 1 | H3 Currently on VBE | 3 | Training of and go live of AI assisted documentation with Nestmed end of March, beginning of April. | 1 | L1 Open to Change Adapt Quickly | 1 | Growth | 1 | we receive incomplete referrals from our community sources outside of Providence (UCI, Memorial Care, Optum, etc.) | 4 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Ed/DCS | 0 | our access teams share responsibility for referrals they receive the access teams are Intake, VBE, and Community Liaisons (growth). | 1 | we do have a weekend team that is supervised by an RN who also works in the field during the week. She and a team of schedulers work normal 8-5 hours on the weekend to perform scheduling, and all 3 OC agencies are supported by this team. The intake and VBE teams also have weekend coverage | 1 | Yes | 1 | the welcome calls are done by our scheduling team. | 0 | DCS/ED are involved and the referral is escalated and pushed. OC agencies also have PM RN to support staffing of same day SOC | 0 | No | 2 | The intake and VBE teams manage the referral, the schedulers who work the weekends are hired specifically for weekends | 1 | we have a centralized intake team Director is Tameia Westby. She is your best contact for this roll out in CA. | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B07 | OC Mission Viejo CA |  | MISSION VIEJO | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 421 | [7 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | Parent agency for B07 is B06 Orange County Anaheim, California | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B08 | High Dester CA |  | HESPERIA | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 213 |  | April-June 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus High Dester CA | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B09 | OC South CA |  | Irvine | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 604 | [7 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | NA | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B10 | Inland Empire CA |  | Pomona | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 340 |  | October-December 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus Inland Empire Pomona california | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 61 | B21 | Snohomish County WA |  | EVERETT | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 899 |  | April-June 2026 | [5 empty] | Mirna Musun | Providence at Home with Compassus HH, Snohomish | NA | Disagree |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | Prescheduled joints, recent DC from hospital, patients from our VBE | 2 | H3 Currently on VBE |  | VBE implementation actively occurring in Region 61- not all have VBE standing up. | 1 | H3 Hesitation and Significant Effort |  | Scheduling;ED/DCS;Referral Coordinators;Growth;Field staff- due to union environment | 4 | yes our Prov facilities , OPTUM and many other providers do not provide verbal orders, or want us to work in EPIC like we used to - | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | VBE supports some of the beside readiness calls and obtaining missing pt information for referrals | 1 | Sometimes our triage nurses may need to assign visits on the weekends | 1 | No | 2 | It happens at program level | 1 | At the program level | 1 | Yes | 1 | Intake | 0 | Schedulders at the location are represented at 2 of my 2 locations | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B22 | Olympia WA |  | LACEY | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 603 |  | October-December 2026 | [5 empty] | Jill Barnhart | Olympia WA | NA | Disagree |  | H3 We're stretched thin |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | Complex wound care, wound vac, PICC line needs, acute ortho | 1 | H3 Currently on VBE |  | CHAP survey planned for Q4, probable location transition to a new space in Q4 | 1 | M2 Some Coaching and Reinforcement |  | Scheduling, ED/DCS | 2 | We receive most of our referrals from our Providence HUB partners with the VBE. We just hired an account manager for the community. We struggle with accurately communicating availability to take on new patients and the referrals to match with multiple referral sources and no one who specifically manages the referrals into the agency with a warm hand off. | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Our centralized Access team manages referrals into the branch and into the scheduler workflow. They don't really fully have a connection with our agency, but work several branches at once and are primarily data entry employees. We don't have a referral coordinator per say, and our growth team is primarily our Providence hospital HUB team. There are a LOT of "pitchers" managing the flow of referrals into the system, but not a lot of attention is placed with managing viable referrals and ensuring important information is gathered timely and truly ushering patients into the agency for care. | 1 | We have 2 triage nurses who assist with adherence to TIC times, particularly assisting with new PSOC dates and transitioning ROCs back on service. | 1 | Yes | 1 | Once the patient is in the PSC workflow | 0 | Usually a TEAMS message comes from the HUB or access team if a patient has a special need, especially wound vacs, PICC line dressing changes or lab draws, ortho patients.. | 0 | No | 2 | Access team in collaboration with the Admin on Call if needed. | 1 | We would really like a referral coordinator who has oversight into the referrals coming in to the agency and helping to manage availability for new business, payor mix, and TIC times. Right now, we have referrals coming in from multiple sources with no regard to what the agency can really admit timely. Our availability is communicated in an antiquated shared spreadsheet that is challenging to read and is ever-changing depending on staffing challenges. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B26 | Seattle WA |  | TUKWILA | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 675 |  | October 2026 - January 2027 | [5 empty] | Jonelle McGee | Seattle, WA/ King County | NA | Agree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Someone who has wound care is considered urgent, as well as other nursing needs. | 1 | H3 Currently on VBE |  | I am a fairly new ED, but we are focused on really turning things around with metrics, EBITDA, census, productivity, STAR ratings, VBP, etc. We are currently recruiting/hiring for growth and there is major education initiatives and rebuilding going on in our ministry. | 0 | M2 Some Coaching and Reinforcement |  | ED/DCSs | 1 | We do accept charity care and also accept Medicaid and payor sources that make it harder to obtain EBITDA targets. As we are hiring for growth, we need to form community relationships with hospitals outside of our VBEs that DC patients to other areas of our territory that our VBEs do not DC patients to. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | The responsible roles listed in #11 above vary. If the referrals are incomplete and make it to scheduling, then more manpower is needed in the ministry to try and complete the referrals. Ideally, this would all happen at intake prior to it entering the scheduling workflow. | 1 | We still need to hire a weekend scheduler. Right now our weekday schedulers are taking turns covering weekends, which creates problems, as they need to take a comp day off, and we are currently short on schedulers. Our DCS team is supposed to be working hand-in-hand with schedulers to ensure clinician productivity is maximized and clinicians have maximum SOC visits assigned as possible. | 1 | No | 2 | When attempting to schedule the SOC visit | 0 | The DCS and/or ED should be notified | 0 | Yes | 1 | schedulers and administrator on call | 1 | We are eager to incorporate anything that could help with the conversion of referral to SOC | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B27 | Spokane WA |  | SPOKANE | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 499 | [7 empty] | Derek Salminen | PAH Spokane WA | N/a | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Those with high needs. New ostomies, wound vacs, IV ABX, ortho patients. | 1 | H3 Currently on VBE |  | For Spokane we are going to be going through a CHAPs Survey. We are looking to expand and are only limited by field clinicians at this time. | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | For all of our referral sources we have to educate that Spokane is no longer a non-profit entity and we have to look at insurance types before accepting. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | N/A | 0 | None | 0 | Yes | 1 | ? | 1 | Operations is notified by the community outreach group. When the referral comes in ED or DCS ensure that the referral is pushed timely through intake and insurance. | 1 | Yes | 1 | We have one dedicated scheduler who works the weekends | 1 | N/A | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B28 | Walla Walla WA |  | WALLA WALLA | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 114 |  | July-September 2026 | [5 empty] | Jessica Dougherty-Burt | Walla Walla, Washington | NA | Agree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV, Wound Vac, Wound, Ortho's | 1 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Our agency would benefit from hospital liason/referral coordinator so that we have complete orders for care at SOC visit. | 0 | We struggle to get POC approval from providers after admit visit. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Referral Coordinators | 1 | ED/DCS | 0 | Referral coordinators are responsible to monitor referral portals/respond to new referrals, but ED monitors pending referral report and clarifies with intake when referrals are not completed timely to see what is causing the delay. | 0 | On the weekends Spokane's scheduler supports Walla Walla. | 0 | Yes | 1 | Referral Coordinator/Intake assessment rep | 1 | ED/DCS pushing to have the referral completed and pushed through. | 1 | No | 2 | Intake | 0 | Patients are pushed to scheduling and intake has not obtained specific orders for the patient care needed. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B29 | Anchorage AK |  | Anchorage | AK |  |  |  | (GMT - 09:00) ALASKA STANDARD | [5 empty] | 187 |  | October -December 20206 | [5 empty] | Stephanie Cabiness | Providence at Home with Compassus Anchorage AK | None | Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | A patient that has discharged from the hospital with wounds or an extended stay. | 1 | H3 Currently on VBE | 3 | Not that I am aware of | 0 | M2 Some Coaching and Reinforcement | 2 | None | 0 | None | 0 | Other | 1 | Referral Coordinators | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | ED/DCS | 0 | None | 0 | I have a separate intake staff because they are union positions and we cannot take them away, so we split the referral between centralized intake and our intake staff | 1 | Yes | 1 | When we are ready to schedule the patient . | 0 | They are moved to the front of the line for admission. | 1 | No | 2 | We don't | 1 | We cannot take away work from my intake team due to a CBA. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
Region 55 - From Sherrod & Holly - Jen Daniels - Vacation week of July 27-Aug 2nd
Note on AO1: Align with pilot high acuity definition = 1 Different from pilot high acuity =2
Note on AS1: 1 for each item listed
Note on AW1: Count
Note on BA1: Growth = 0, anything else = 1
Note on BC1: Growth = 0, anything else = 1
Note on BE1: RC=0, Any other role =1
Note on BG1: RC=0, any other role =1
Note on BK1: Scheduler = 0, anything else =1
Note on BO1: ED/DCS=0, anything else = 1
Note on BQ1: 1 point for each item listed if outside of standard process
Note on BS1: 1 point for each item listed
Note on BU1: YES = 1 NO =2
Note on BW1: 1 point for anything outside of standard process; one point if no process
Note on BY1: 1 point for any process that outside of pilot process
Note on CA1: Yes = 1, No = 2
Note on CC1: Intake/Growth = 0, any other role = 1
Note on CR1: 1 = Aligns with pilot high acuity definition 2 = Different than pilot high acuity definition
Note on CU1: Total portal in #6 (8) minus portals not used in 7
Note on CW1: Count of additonal portals used
Note on CY1: Count of payors listed requiring extra steps
Note on DC1: 1 point for each initiative listed
Note on DG1: Count
Note on DI1: 1 point for each challenge listed
Note on DK1: If Growth = 0, anything else = 1
Note on DM1: If growth = 0, any other role =1
Note on DO1: If RC = 0, any other role = 1
Note on DQ1: RC = 0, any other = 1
Note on DS1: RC=0, any other = 1
Note on DU1: Scheduling = 0, any other = 1
Note on DW1: Scheduling = 0, other = 1
Note on DY1: ED/DCS = 0, other = 1
Note on EA1: 1 point for each item listed if outside standard process of DCS/ED/AME leading huddle
Note on EC1: 1 point for each cross functional role listed
Note on EE1: YES = 1 NO = 2
Note on EG1: 1 point for anything outside of the standard process - 1 point for no process
Note on EI1: 1 point for anyting deviated from pilot processes
Note on EK1: Yes = 1 No = 2
Note on EM1: Intake or Growth = 0, any other roles or no roles = 1

## GoLive Schedule (2) (hidden)
REGION | Branch Code | Branch Name | Street | City | State | ADC | # of 2025 Months <-5% Budget | 2026 CHAP Survey Anticipated | Benefits (25%) | Efforts (25%) | Risks (25%) | Alignment (25%) | Score | ED SURVEY | 1. Program Name | 2. Branches | 3. Manage increase in referrals/admissions with current clinical staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 4. Current Field Clinician Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. VBE Status | 6 SCORE | 7. Major Initiatives | 7 SCORE | 8. Team response to new process or tool | 8 SCORE | 9. Groups requiring more change management | 9 SCORE | 10. Challenging referral source relationships | 10 SCORE | 11. Task "Monitor referral portals & respond to new referrals" | 11 SCORE | 11. Task "Gather missing referral documents & patient information" | 11 SCORE | 11. Task "Create chart in HCHB for new referral" | 11 SCORE | 11. Task "Complete "Review External Referral Request" workflow in HCHB" | 11 SCORE | 11. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 11 SCORE | 11. Task "Schedule patient's SOC visit in HCHB" | 11 SCORE | 11. Task "Make welcomes/readiness calls" | 11 SCORE | 11. Task "Lead referral huddles" | 11 SCORE | 12. Divided duties | 12 SCORE | 13. Cross functional roles | 13 SCORE | 14. Growth team authority to accept referrals with no ED/DCS input | 14 SCORE | 15. When do welcome calls occur? | 15 SCORE | 16. Handling of urgent or high priority referrals? | 16 SCORE | 17. Weekend Schedulers | 17 SCORE | 18. Weekend Referral Management | 18 SCORE | 19. Additional Input | RME/AME Survey | 1. Market Name | HH Locations | 3. Manage increase in referrals/admissions with current growth staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. All Portals Used in Order | 7. Portals NOT used | 6 & 7 SCORE | 8. Portals Used Not Listed in #7 | 8 SCORE | 9. Payors requiring extra op steps | 9 SCORE | 10. VBE Status | 10 SCORE | 11. Major initiatives | 11 SCORE | 12. Team Response to New Process/Tool | 12 SCORE | 13. Groups requiring more change management | 13 SCORE | 14. Referral source creating challenges | 14 SCORE | 15. Task " Monitor referral portals & respond to new referrals" | 15 SCORE | 15. Task "Gather missing referral documents & patient information" | 15 SCORE | 15. Task "Create chart in HCHB for new referral" | 15 SCORE | 15. Task "Complete "Review External Referral Request" workflow in HCHB" | 15 SCORE | 15. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 15 SCORE | 15. Task "Schedule patient's SOC visit in HCHB" | 15 SCORE | 15. Task "Make welcomes/readiness calls " | 15 SCORE | 15. Task "Lead referral huddles" | 15 SCORE | 16. Divided duties | 16 SCORE | 17. Cross functional roles | 17 SCORE | 18. Growth team authority to accept referrals with no ED/DCS input | 18 SCORE | 19. When do welcome calls occur? | 19 SCORE | 20. Handling of urgent or high priority referrals? | 20 SCORE | 21. Weekend Schedulers | 21 SCORE | 22. Weekend Referral Management | 22 SCORE | 23. Additional Input
61 | B29 | Anchorage AK |  | Anchorage | AK |  |  | October -December 20206 | [5 empty] | Stephanie Cabiness | Providence at Home with Compassus Anchorage AK | None | Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | A patient that has discharged from the hospital with wounds or an extended stay. | 1 | H3 Currently on VBE | 3 | Not that I am aware of | 0 | M2 Some Coaching and Reinforcement | 2 | None | 0 | None | 0 | Other | 1 | Referral Coordinators | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | ED/DCS | 0 | None | 0 | I have a separate intake staff because they are union positions and we cannot take them away, so we split the referral between centralized intake and our intake staff | 1 | Yes | 1 | When we are ready to schedule the patient . | 0 | They are moved to the front of the line for admission. | 1 | No | 2 | We don't | 1 | We cannot take away work from my intake team due to a CBA. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
50 | A01 | PELL CITY AL (CC1027) | 2401 STEMLEY BRIDGE RD STE 7 | PELL CITY | AL | [8 empty] | Christina Isbell | Pell City AL | None | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | pt acuity criteria, referral partner consideration, time sensitive care coordination | 1 | H3 Currently on VBE | 3 | Annual Skills check off March 10-11, none other scheduled at this time | 0 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators, Scheduling, Document Specialists | 3 | None at this time | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | ED/DCS | 0 | referral portals- Growth, gather missing info- referral coordinator, non-admit reason in HCHB- DCS/ED, Schedule pt- DCS/ED, Make welcome calls- DCS/ED, Lead referral Huddles- Referral coordinator & Growth management | 3 | We currently have a scheduler on the weekends to assist DCS with schedules, we have RC/Doc specialists managing portals and keying referrals, | 2 | No | 2 | within the first 48 hrs referral received | 0 | management notifies PCC of high priority to schedule urgently | 1 | Yes | 1 | Doc specialists, RC | 0 | None | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
50 | A00 | VESTAVIA AL (CC1028) | 1900 INTERNATIONAL PARK DR STE 250 | BIRMINGHAM | AL | [8 empty] | Kerri Couch | Vestavia AL | No | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Risk for rehospitalization, ORTHO, IV, Wound, New 02 | 1 | L1 No Plan for 2026 | 1 | We currently have 3 new DCS's, 1 on leave and 2 with 6m experience. We have hired over 10 new nurses for the field currently in training. | 1 | L1 Open to Change Adapt Quickly | 1 | Scheduling | 1 | VA Getting Auth Approvals | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Referral Coordinators and DCS will process non-admits, RC will do it if it is done prior to scheduling the patient out to a clinician. We have RN clinical coordinator that will do readiness calls and run the scheduling meeting at 3:30 to triage all of admissions. | 2 | Our Schedulers work a day on the weekend and take a day off during the week, Our DCS take call during the weeknights and on the weekends work at their computers all day Saturday and Sunday. Document Specialist work weekends. | 2 | Yes | 1 | Once the SOC comes to workflow | 0 | growth team member usually gives us a heads up that it is coming in an email so we are prepared. We have a scheduling meeting daily at 3:30. It is on our grid already and we schedule it out once it comes to workflow and it is confirmed. | 1 | Yes | 1 | Document Specialists | 1 | The weekends are the worst for missed referrals and/or slow process for getting them to workflow to assign to the clinicians in the field. We use a excel spreadsheet to put the patients on daily and it could be anywhere from 40-100 patients on that grid depending on the day. So, we get a ton of emails to follow for the patient to enter on that grid. | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
62 | B08 | High Dester CA |  | HESPERIA | CA |  |  | April-June 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus High Dester CA | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B02 | Humbolt County CA |  |  | CA | [8 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B10 | Inland Empire CA |  | Pomona | CA |  |  | October-December 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus Inland Empire Pomona california | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B04 | LA County North CA |  |  | CA | [8 empty] | Luiza Chuang | LA North | LA North | Strongly Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | status post hospitalization, IV, TKR, | 1 | H3 Currently on VBE | 3 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Scheduling | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | None | 0 | BOC covers for scheduling if needed | 0 | Yes | 1 | once referral is on schedulers workflow if not if its on MS list | 0 | within 24 hours | 0 | YEs | 1 | Same Team | 0 | we have daily stand downs and we dont see many intake reps joining and we would love to have their presence | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B05 | LA County South CA |  |  | CA | [8 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B01 | Napa Valley CA |  | NAPA | CA |  |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B06 | OC Anaheim CA |  | ANAHEIM | CA | [8 empty] | Kathleen Hatfield | PAH with Compassus, OC Anaheim CA | PAH Orange County Mission Viejo | Neither Agree or Disagee |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Tracheostomy care, Infusion, PleurX drain, wound vac, new enteral feedings | 1 | H3 Currently on VBE | 3 | Training of and go live of AI assisted documentation with Nestmed end of March, beginning of April. | 1 | L1 Open to Change Adapt Quickly | 1 | Growth | 1 | we receive incomplete referrals from our community sources outside of Providence (UCI, Memorial Care, Optum, etc.) | 4 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Ed/DCS | 0 | our access teams share responsibility for referrals they receive the access teams are Intake, VBE, and Community Liaisons (growth). | 1 | we do have a weekend team that is supervised by an RN who also works in the field during the week. She and a team of schedulers work normal 8-5 hours on the weekend to perform scheduling, and all 3 OC agencies are supported by this team. The intake and VBE teams also have weekend coverage | 1 | Yes | 1 | the welcome calls are done by our scheduling team. | 0 | DCS/ED are involved and the referral is escalated and pushed. OC agencies also have PM RN to support staffing of same day SOC | 0 | No | 2 | The intake and VBE teams manage the referral, the schedulers who work the weekends are hired specifically for weekends | 1 | we have a centralized intake team Director is Tameia Westby. She is your best contact for this roll out in CA. | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B07 | OC Mission Viejo CA |  | MISSION VIEJO | CA | [8 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | Parent agency for B07 is B06 Orange County Anaheim, California | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B09 | OC South CA |  |  | CA | [8 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | NA | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B03 | Sonoma County CA |  | SANTA ROSA | CA |  |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
50 | A53 | JACKSONVILLE FL (CC1801) | 7235 BENTLEY RD STE 236 | JACKSONVILLE | FL |  |  | Jan-April 2026 |  |  |  |  | 11 | Daisy | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A58 | PANAMA CITY FL (CC1803) | 2211 S HIGHWAY 77 STE 203A | LYNN HAVEN | FL |  |  | October 2026 - January 2027 | [5 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A55 | PENSACOLA FL (CC1802) | 1115 E GONZALES ST STE 1001 | PENSACOLA | FL | [8 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A79 | ST PETERSBURG FL (CC1805) | 11001 ROOSEVELT BLVD N STE 100 | St. Petersburg | FL | [7 empty] | 11 | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A78 | TAMPA FL (CC1804) | 137 S PEBBLE BEACH BLVD STE 203 | SUN CITY CENTER | FL | [7 empty] | 11 | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
51 | A20 | ANDERSON IN (CC2311) | 600 CORPORATION DR STE 104 | PENDLETON | IN |  |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A24 | Bloomingham IN (Bedford) | 1324 K ST STE 150 | BLOOMINGTON | IN | [8 empty] | Darla Bell |  | Bloomington (managed by Darla)is actually branch of Idianapolis managed by Suchi | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A26 | EVANSVILLE IN (CC2313) | 7321 EAGLE CREST BLVD STE A | EVANSVILLE | IN |  |  | Jan-April 2026 | [5 empty] | Darla Bell |  | None | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | We are in the CHAP window in Evansville 1st quarter. | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A22 | INDIANAPOLIS IN (CC2314) | 8909 PURDUE RD STE 107 | INDIANAPOLIS | IN | [8 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A21 | KOKOMO IN (CC2315) | 2626 S WEBSTER RD STE B | KOKOMO | IN |  |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A67 | LAFAYETTE IN (CC2319) | 703 N 36TH ST | LAFAYETTE | IN | [8 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A25 | NORTH VERNON IN (CC2316) | 2337 NICHOLAS CT STE C | SEYMOUR | IN | [8 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
52 | A28 | PITTSBURG KS (CC2503) | 200 E CENTENNIAL DR STE 13 | PITTSBURG | KS | [8 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
52 | A27 | WICHITA KS (CC2504) | 301 N MAIN ST STE 950 | WICHITA | KS | [8 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
54 | A77 | PADUCAH KY (CC2602) | 225 MEDICAL CENTER DR STE 203 | PADUCAH | KY | [8 empty] | Renee Wurth | Mercy Health Homecare by Compassus - Paducah, KY | N/A - (submitted for Metropolis IL branch but have not yet received approval) | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | High Priority patients are those that are discharging from acute hospitals, as well as, those who had outpatient orthopedic surgery the day before. We also have many wound vacs/infusion patients who have specific times/needs that are quick turnarounds from referral. | 1 | L1 No Plan for 2026 | 1 | We have applied to have a branch in Metropolis, IL but have not received approval from CMS at this point. Otherwise no major known events. | 1 | M2 Some Coaching and Reinforcement | 2 | Field Staff | 0 | Our orthopedic physicians send referrals early and we have to follow up regularly with them to ensure surgeries remain scheduled and that we are out to see the patient the next day. Vanderbilt and Barnes Jewish often send us requests and it takes days of follow up to get confirmation of patient choosing us (occasionally even after patient is already discharged). We hold spots on our scheduling grid for these patients, requiring a lot of attention and follow up. Multiple local physicians' offices send referrals at the very end of the day making it difficult to process them timely for the referral coordinators. | 3 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Referral Coordinators cover portals on weekends and attend to faxed referrals. RCs and ED/DCS assist with gathering missing referral information as needed. Growth makes welcome calls and Scheduling makes readiness call. Scheduler assists growth in referral huddles with current avialability and episodic percentage of referrals admitted for month to date. | 1 | Referral Coordinators cover weekends for referrals. Administrator on Call (DCS) covers scheduling from Friday at 5pm to Monday at 8 am. | 1 | Yes | 1 | Welcome call is the day the referral is accepted. Readiness call occurs the day before admission (Friday before for Monday admission). | 0 | During office hours, communication comes into DCS/ED and is coordinated by the DCS that is on call for the week. Administrator on call (DCS) coordinates the process to get the patient's chart to the clinician if it is after hours or on the weekends. | 0 | No | 2 | Referral Coordinators manage the referrals and Administrator On Call is the accept/decline decision maker. | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout. | Farrah Gay | Paducah KY | Paducah, KY and we have applied for Metropolis, IL to be a branch. | Neither Agree or Disagee |  | L1 Well Staffed |  | H3 We're stretched thin | 3 | M2 Managing but it's tight |  | Complex, unstable or acute needs requiring urgent intervention to prevent hospitalization, nursing home placement or further decline. | 1 | Epic Carelink;Aidin;Other;Ensocare;Referral Management (All scripts);AIDA;Intake (NaviHealth/Curaspan);Watershed | #5-8 are not | 4 | Not that I am aware of. | 0 | VA - required auth at intake before we can start care. Trisha Curtis is our insurance manager and looking into this if you would like to circle back with her for more information. | 1 | L1 No Plan for 2026 |  | We've requested to make the Metropolis, IL location a branch. The application was submitted in 2024. | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Referral sources seem to understand the universal staffing capacity issue among all healthcare, so they have not verbalized as much frustration recently as they have in the past. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | Make readiness call - completed by scheduling Lead referral huddles - completed by both growth and branch | 0 | RC/intake covers weekend referral management. Administrator on call covers scheduling and accepting/decline. | 0 | Yes | 1 | Welcome call - day the referral is accepted by growth/patient PCC readiness - day prior to start of care except for weekends. | 1 | Notification to administrator on call who then communicated and schedules | 1 | No | 2 | RC/intake and Administrator on call | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout.
52 | A02 | PORTAGE MI (CC3146) | 5136 LOVERS LN STE 200A | PORTAGE | MI | [8 empty] | Stephanie Watkins | Compassus Home Health - Portage MI | NA | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Infusion, Tube Feeding, Chest Tubes, Pleurx or Aspira drains, Chole Tubes, Nephrostomy Tubes, Tracheostomy, new to Self Catheterization, some wound care patients as they all may need same day care and education. | 1 | L1 No Plan for 2026 |  | We are actually just starting our Commure Pilot, Realignment of agency activities and trainings to standardize across the company in April and May. | 0 | M2 Some Coaching and Reinforcement |  | Growth, Scheduling, ED/DCS | 3 | Beacon Hospitals just went online with a new EMR and referral portal of Ensocare but they are not functioning efficiently in those platforms at this time impacting timeliness of referral updates, orders and even notification of discharges. They have no current format to write home care orders in their EMR and using a paper form and faxing but frequently forget, they are not routinely confirming assignment of referrals to agency in Ensocare and are not utilizing the system for updates or communication. Previously when they were Ascension facilities, we had access in the version of Cerner being used and could assist their Care Management and Discharge Planning teams in getting the necessary information to agency timely. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | Referral Coordinators also monitor referral portals and respond to new referrals on the weekends. ED/DCS assist with assigning patient's SOC visit in HCHB on weekends or afterhours, Scheduling assists Growth PTC with welcome and readiness calls. | 0 | As above we have no weekend scheduling so ED/DCS covering the Administrator on Call role assigns out needed SOC/ROC visits for weekend and Mondays. Will also sometimes work to track down referral information but does not have access to all needed portals or EMRs as growth does. The Admin on Call also responds to the referral emails if agency is unable to accept a referral for follow up by the referral coordinators/growth team. | 1 | Yes | 1 | When the discharge is confirmed and the referral is complete. | 0 | Growth notifies the team when received with anticipated DC date and location to confirm branch can safely accept and admit. | 0 | No | 2 | Referral Coordinators, occasionally growth will assist if they are expecting information on the weekends who then email th | 0 | None | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
52 | A04 | WARREN MI (CC3144) | 28120 DEQUINDRE RD | WARREN | MI |  |  | November 2026-February 2027 |  |  |  |  | 11 | Cynthia Voelker | [55 empty] | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
52 | A68 | ALPENA MI (CC3153) | 109 N SECOND AVE STE 202 | ALPENA | MI | [7 empty] | 11 | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
52 | A03 | GRAND BLANC MI (CC3145) | 5445 ALI DR DEPT 500 | GRAND BLANC | MI | [7 empty] | 11 | Cynthia Voelker | [55 empty] | Ronald Boggia
52 | A06 | TAWAS CITY MI (CC3147) | 808 W CEDAR ST BLDG A | STANDISH | MI | [7 empty] | 11 | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
51 | A89 | COLUMBIA MO (CC3437) | 3310 BLUFF CREEK DR STE 106 | COLUMBIA | MO | [8 empty] | Angie Walker | Compassus Columbia MO | NA | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Clinically complex, Increased risk for readmission, timed admission (ex. PICC w/ ABX). | 1 | L1 No Plan for 2026 |  | Leadership changes/staffing changes-current and ongoing | 1 | L1 Open to Change Adapt Quickly |  | ED/DCS | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Interim ED, DCS, RC and HHCC all help monitor referral portal. | 1 | Our BOC is also our scheduler. | 1 | No | 2 | After the referral is considered complete, and before it is scheduled to a clinician. | 0 | That referral gets prioritized and scheduled ahead of a "routine" referral. | 0 | No | 2 | Responsibility shared between our HHCC and the admin on call. | 1 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | None | 0 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
53 | A51 | BILLINGS MT (CC3506) | 490 N 31ST ST STE 130B | BILLINGS | MT | [8 empty] | Joanne Wirtjes | Billings MT | NA | Strongly Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | ortho pts, IV abx pts, cardiac pts | 1 | L1 No Plan for 2026 |  | New ED in 1/2026, new DCS in 3/26, rapid growth over last couple of months - plan on continuing growth, added 6 new clinicians in 2 months. | 2 | L1 Open to Change Adapt Quickly |  | None | 0 | VA - awaiting auth for SOC of pts and bundled and non-bundled for patients. | 1 | Growth | 0 | Referral Coordinators | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | EDDCS | 1 | Referral Coordinators | 1 | not sure whose task to build the hchb chart | 0 | NA | 0 | Yes | 1 | Ideally prior to chart getting pushed to scheduling | 0 | discussed in daily huddle/referral meeting and via TEAMS | 0 | No | 2 | AC Team | 0 | None | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A52 | BUTTE MT (CC3508) | 19 DISCOVERY DR | BUTTE | MT |  |  | Jan-April 2026 | [5 empty] | Jacqueline Mathews | Compassus Home Health - Butte MT | None | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Wound care, fresh surgical patient discharging from the hospital and most patients coming out of the hospital. | 1 | L1 No Plan for 2026 |  | 2 new nurses will be training over the next couple of months so it would be best to roll out after they are trained. Also have new PTC who needs to feel more comfortable with her role. | 2 | M2 Some Coaching and Reinforcement |  | Growth, Referral Coordinators | 2 | We need improved referral source relationships so we can generate referrals needed | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | At times the ED will enter the ERR workflow and enter non-admit reason if it hasn't been done timely At time the ED will schedule patients if scheduler is not available. Make welcome calls is growth, readiness calls is scheduling | 2 | ED is also the DCS and BOC is also the scheduler | 2 | Yes | 1 | HCC is responsible for any bedsides, PTC is responsible for welcome call. BOC/scheduler is responsible for readiness calls once referral is complete and ready to be scheduled according to growth team. | 0 | Discussed in daily huddle, make a plan as to when patient can be admitted. | 0 | No | 2 | Administrator on call if needed | 1 | HHCC is new to having PTC, having a hard time relinquishing duties | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A50 | ALBUQUERQUE NM (CC4004) | 7770 JEFFERSON ST NE STE 110 | ALBUQUERQUE | NM | [7 empty] | 13 | Raechel Dominguez | [55 empty] | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A54 | SANTA FE NM (CC4005) | 1692B HOSPITAL DR STE 102 | SANTA FE | NM | [7 empty] | 13 | Raechel Dominguez | [55 empty] | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
54 | A85 | LIMA OH (CC4418) | 959 W NORTH ST | LIMA | OH | [8 empty] | Cheryl Bechtel | Mercy Health Homecare by Compassus Lima Ohio 45805 | No | Strongly Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Skilled need IV, Wounds, Drains | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | Insurance Authorization | 1 | No | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Other | 1 | ED/DCS | 0 | n the Lima Market the scheduler is the first person to call the patient to set up a home visit. Would be nice to have the growth team verify information prior to the scheduler. This would save time as the scheduler then has to reach back to the growth team to obtain the information | 0 | DCS will assist with scheduling if scheduler is on PTO Training Clinical RN coordinator to assist with scheduling | 1 | Yes | 1 | When the referral is in the workflow of the scheduler. | 0 | Reviewed by the DCS/ED prior to scheduling if it is known at the time of referral is sent. Growth team doesn't communicate with the intake team sometimes causes problems with priority of the patient needs to be schedule appropriately. | 0 | No | 2 | Growth/Intake | 0 | To improve efficiency and reduce delays in the Start of Care (SOC) process, several opportunities for improvement have been identified within the intake and referral workflow in the Lima market. 1. Growth Team Education on Home Health Qualification and Skilled Need The new Growth Team would benefit from additional and ongoing education regarding: •Qualification criteria for home health services •Identification of skilled need for the patient Currently, referrals are accepted before the clinical skill level and priority of the patient’s needs are fully identified. This can create delays when the patient requires a higher level of clinical prioritization than initially recognized. 2. Insurance Authorization and Verification of Benefits Process Another opportunity for improvement is within the insurance verification and authorization workflow. Currently, delays occur when: •Verification of Benefits is completed, but •The scheduler later needs to re-request insurance authorization, which slows the referral and SOC process. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A84 | LORAIN OH (CC4415) | 3500 KOLBE RD | LORAIN | OH | [8 empty] | Andrea Faurot | Lorain OH | N/A | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV, Wound, Pleurex or chest tubes, Tube feed, TPN Total Joint patients, nephrostomy, trach patients, New O2, CABG | 1 | L1 No Plan for 2026 |  | CHAP survey pending immediately | 1 | M2 Some Coaching and Reinforcement |  | Unsure | 0 | Yes the Lorain BSMH market needs lots of education on why and they want a smoother process. They oppose change often, but sometimes will come along as long as there is good communication and collaboration. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Growth | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Growth and intake often share responsibilities or cover for each other | 1 | RN Coordinator is also in on call rotation and assists schedulers back up as well as Home Health Admin Assistant | 1 | Yes | 1 | Once sent to scheduling | 0 | escalated to DCS or ED | 0 | No | 2 | Intake & Growth | 0 | Clear expectations of responsibility and throughput diagram. So expectations are clear. Our schedulers are part of a bargaining unit, so any changes that could impact them—such as modifications to their job descriptions or working hours—would need to be reviewed and vetted through the bargaining unit. With negotiations starting next week, it would be helpful to identify any potential changes proactively so we can address them in advance. This will ensure we remain aligned with the bargaining process and avoid any delays. If there is someone else who should be looped in or involved in these discussions, please feel free to connect them. Brian Jackson and Yashica Smith is who we use to review any changes that may impact our bargaining team members we get them included early and often to discuss any potential changes. I have looped in Melissa just for transparency. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A86 | TIFFIN OH (CC4419) | 45 ST LAWRENCE DR | TIFFIN | OH | [8 empty] | Brandy Fredritz | Mercy Home Care by Compassus Tiffin Ohio | N/A | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day needs, daily needs, IV care, and wound care. | 2 | L1 No Plan for 2026 |  | Hiring full therapy team (versus contracted) in 2026 and adding more nursing staff. Hiring increases started in February 2026 until all positions are filled. | 1 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Schedulers | 2 | When utilizing CarePort, the larger hospitals like OSU and Cleveland Clinic send out "blast referrals" and are poor/slow to respond. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | NA | 0 | Our BOC covers scheduling when our PSC is off. DCS/ED cover scheduling on the weekends. | 1 | Yes | 1 | Varies depending on how quickly the referral is worked and when the SOC is needed. We typically are reactive to our referral process and plot people quickly due to low staffing. Typically, the welcome/readiness call is completed the day before. | 1 | Communication between all Growth/RC/ED/DCS in TEAMS/Email. | 0 | No | 2 | RC/Growth with DCS/ED input | 0 | n/a | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A87 | YOUNGSTOWN OH (CC4412) | 979 TIBBETTS WICK RD STE A | GIRARD | OH | [8 empty] | Melanie Boyts | Youngstown OH | NA | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | CABG (open heart), Mitral Valve Replace, Carotid endarterectomry, fem-pop bypass, Infusion patients. orthopedic patients needing same day or next day visit, Enteral/Tub Feed, Trach, wounds/wound vacs, pleurx drains/drains | 1 | L1 No Plan for 2026 |  | Focusing on recruitment and retention. Recruitment in this market has been slow. Starting to make some movement in 2026 but it's really to maintain current operations and not necessarily to support growth. PT/OT/ST extremely difficult to recruit for. Other competitor agencies in area who have established relationships/presence in our JV BSMH hospitals. | 1 | L1 Open to Change Adapt Quickly |  | Growth, Referral Coordinators | 2 | The referral source relationships within the JV BSMH hospitals present operational challenges, particularly within the case management team. A notable issue is the development of relationships with competitor home health agencies within our hospitals, which results in these competitors being prioritized with favorable payors. These dynamics highlight a broader struggle in this market hospital to embrace the joint venture (JV) as a true partnership. From the inception of the JV, the relationships have been challenged, largely tied to efforts in managing payor mix effectively. Several case managers and physicians continue to demonstrate a preference for competitor home health agencies, which undermines the intended collaboration of the JV. While the Area Market Executive in this market has worked diligently to improve relationships and enhance communication around partnerships, significant barriers remain despite these efforts. An additional challenge involves the pressure to accept patients that are often declined by other home health agencies. When explanations are provided about why we cannot accept these patients, resistance frequently arises, escalating the matter to the JV director on the BSMH side. This creates unnecessary friction, adding to the operational complexity. Lastly, the communication dynamic often positions our team as separate from the partnership. This creates the perception that the partnership is one-sided, rather than a true collaborative effort. Addressing these challenges is critical to fostering a unified partnership, optimizing payor relationships, and removing operational inefficiencies. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Confusion from operations team on who is doing what when a referral comes together. Several roles involved in one patient referral. | 0 | scheduling works weekend here. RC's in this market covered growth for a very long time, i think there is still confusion from the operations team on who does what part of a referral when requesting additional information | 1 | Yes | 1 | the scheduler completes this the day before. Done around 330pm when we consider our scheduling grid final. | 0 | Growth team CTC, HHCC and PTC communicate and move patients around on the scheduling grid accordingly. if there is a request to add a patient on outside of what our capacity is DCS and/or ED approve that. | 1 | Yes | 1 | RC & Growth | 0 | The implementation of the new scheduling grid on 12/8/25 has shown promise in aiding payor mix management. However, discharge planning continues to present significant challenges, particularly within the BSMH hospitals. Many patients appear on the scheduling grid for specific discharge dates, but frequently either do not go home as planned or are discharged on unanticipated dates. You expect this if they are discharges planned far in the future but the concern here is you review the patients on the 230pm call set up schedules after 330pm and come in following morning and patient didn't dc. We expect things change and this happens, but it is a more frequent occurrence here. It has been noted that BSMH referrals are sometimes assigned discharge dates that are not definitive, simply to facilitate their acceptance. This creates difficulties in accurately following patients day to day and predicting their actual discharge dates. As a result, we often face situations where patients scheduled for admission do not go home as anticipated. This creates complications in confirming schedules, as clinicians frequently find that patients they planned to admit are not yet discharged. To manage these issues, we attempt to pull other patients forward to fill the vacant spots, though these adjustments often occur too late to avoid disruption. Our clinicians, who operate on a pay-per-visit model, need to begin their day by 8:00 a.m. to maintain productivity and minimize financial impact. To address these ongoing discrepancies, we continue to hold two staffing huddles daily, one in the morning and one in the afternoon. These huddles are essential due to the high rate of unexpected changes in discharge timing and the need for late adjustments. I see an opportunity for improvement in this process by ensuring that patients are added to the schedule once their discharge is confirmed. Concerns with having the necessary attachments and documentation readily available on patient charts. For example, the AVS (After Visit Summary) or DC summaries are frequently requested by SOC clinicians. The DCS often has to pull supporting documentation, such as Face-to-Face supporting documentation, during the coding review process. Addressing these documentation and coordination challenges will be critical to improving the overall efficiency of the referral to scheduling workflow. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A96 | ATHENS OH (CC4427) | 444 W UNION ST STE C | ATHENS | OH | [8 empty] | Jennifer Frost-Coon | Ohio Health at Home with Compassus - Athens | None | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV patients | 1 | L1 No Plan for 2026 |  | Not that I am aware of at the moment. | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | Yes, we have a few providers who can become challenging with signing the POC/orders/following after they agree to follow. I manage those providers in the moment with education and feedback. | 1 | ED/DCS | 1 | Growth | 0 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | There are three of us in back office that monitor the referral chats and weigh in- it is mostly me that responds. | 1 | With our office being more compact the Scheduler/BOC are the same person in my office and she can schedule patients, she is not clinical. I have a Clinical Coordinator who supports staff and completes and covers for the Scheduler/BOC when she is on PTO. I am the only one in our office who is in the rotation for weekends. | 2 | No | 2 | Specifically I am not so sure- however the welcome call is documented at bedside as well as before the referral is pushed often times. | 1 | Over communication between the HCC and PCC along with back office and ensuring good communication between the patient and the office so that the patient knows the plan too | 0 | No | 2 | The ED and or who is covering in the weekend rotation. A warm hand off is given on Friday going into the weekend with insight into capacity for the weekend and beginning of each week. | 1 | The weekends are the roughest with Intake and communication. Ensure there is good support over a weekend would be my two cents. | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
54 | A93 | COLUMBUS OH (CC4424) | 6805 PERIMETER DR FL 1 | DUBLIN | OH | [8 empty] | Tabitha Campbell | OHH Columbus OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients new to tube feeds | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Non admits are completed by clinicians-CC- and ED | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
54 | A94 | MANSFIELD OH (CC4426) | 50 INDUSTRIAL DR | LEXINGTON | OH | [8 empty] | Tabitha Campbell | Mansfield OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients who have wounds/depending on the severity | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | I do not know who is responsible for entering the Review External Referral Request- possibly intake? | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
54 | A95 | MARION OH (CC4425) | 1713 MARION MOUNT GILEAD RD STE 107 | MARION | OH | [8 empty] | Tabitha Campbell | Marion OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients with new ostomy or newer ostomies | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | None | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
52 | A30 | BARTLESVILLE OK (CC4513) | 3061 SE WASHINGTON BLVD | BARTLESVILLE | OK |  |  | Feb-June 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
52 | A29 | TULSA OK (CC4514) | 4612 S HARVARD AVE STE C | TULSA | OK |  |  | April-July 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | St John's Tulsa- unhappy with not being in network with patient's insurance | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
54 | A76 | GREENVILLE SC (CC4909) | 1836 W GEORGIA RD | SIMPSONVILLE | SC | [8 empty] | Regina Ervin | Bon Secours Home Care by Compassus - Greenville, SC | None | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H2 Managing but it's tight |  | A patient with high acuity discharging same day(Pleurex patients, IV abx, tube feeds, TPN, etc.) | 1 | H3 Currently on VBE |  | None at this time | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | We have a large Total Ortho Program that we are committed to. We work with this group closely and process referrals quicky to see pateint timely. Some of these patients go home same day of surgery and we try to see patient next day. We are on the hospital committee and have built a strong relationship with this program. We would want to continue to function well for this group. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | RC's complete referral portals and respond to new referrals on the weekend. Readiness calls can be done by growth or scheduling | 1 | RC's complete growth responsibilities on the weekend. There are times DCSs schedules visits on the weekend. | 1 | Yes | 1 | Typically, when growth completes demos | 1 | Discussed during huddle with growth and scheduling to try and get patient seen timely. DCS and EC is on call to discuss barriers. | 0 | No | 2 | RCs & DCSs | 1 | Communication is strong between our team (intake, growth, schedulers, leaders) and we would not want to lose that. | Kimberly Manson | Greenville SC | Greenville SC only | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | Higher acuity patients that would better seen within 24-hour timeframe - his include new oxygen, IV antibiotics, new tube feeds, and TPN patients. | 1 | Intake (NaviHealth/Curaspan);Ensocare;Other;Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Watershed | Referrals are not received directly via all scripts, AIDA, Aidin, or Watershed. | 3 | No - unless faxes will no longer create an ERR within HCHB. There are still referrals that are sent to our branch by fax. | 0 | Humana is one that I am aware of, not sure if there are others. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Referral Coordinators | 1 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCs | 0 | Growth is primary for portals during non-holiday and business hours, Referral Coordinators are responsible for these portals during holiday and non-business hours. Growth typically makes welcome/readiness calls. If they are unable to reach a patient during scheduling, the scheduling team will contact patient. | 1 | None | 0 | Yes | 1 | When Growth has accepted the referral and is calling to verify physician and demographics. This is approximately 24-48 hours prior to admission. | 1 | They are reviewed by Growth and discussed with DCS/ED/scheduling to coordinate care and ensure that the patient is seen within a timely manner and any barriers are discussed as a team. This also happens during huddle calls. | 0 | Yes | 1 | The Referral Coordinators manage referrals and coordinate with the weekend DCS on declining or accepting. They also work with the Sunday scheduler to address any additional needs. | 0 | It would be great to continue to communicate and coordinate care across multiple teams, but ensuring that there is less patient communication via email/Teams would be GREAT.
51 | A74 | CENTERVILLE TN (CC5111) | 135 E SWAN ST | CENTERVILLE | TN | [8 empty] | Brandi Tayloe-Jones | Centerville TN | NA | Strongly Agree |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | Clinical needs and acuity such as IV, wounds, etc. | 1 | M2 2026 GoLive |  | VBE launch in June/July | 1 | M2 Some Coaching and Reinforcement |  | Field Clincians | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | DCS does quite a bit with referral management and no admits | 1 | BOC also performs scheduling functions due to size of program. | 1 | Yes | 1 | After the referral is sent to scheduling. | 1 | The DCS is very active and pushes the referrals through as needed. | 1 | Yes | 1 | There is a regional a scheduling and growth rotation. | 0 | The size of the program can limit functions at times. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A75 | NASHVILLE TN (CC5112) | 402 BNA DR STE 320 | NASHVILLE | TN | [8 empty] | Angela Corman | Nashville TN | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | IV antibiotic, Wound Vac, Recent Joint Replacement, LVAD, Cardiac Drip | 1 | M2 2026 GoLive |  | VBE to go live 5/28 currently hiring for increase in referrals | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | Referral Huddles are lead by RC, Scheduler and or ED. Welcome calls are being made by growth, then scheduler/clinicians | 2 | Growth and schedulers work weekend rotations to cover region, ED currently doing large portion of DCS leadership such as payroll etc, all staff under ED. 2 new DCS's have been hired and training all DCS's to take over those responsibilities for clinical team leadership. BOC is cross trained to manage scheduler workflow, Scheduler cross trained to complete some BOC responsibilities. | 1 | Yes | 1 | Growth contacts patient to verify demographics and makes initial welcome call. Clinicians/Scheduler call for readiness. | 1 | Growth informs team of priority admission and intake/scheduler/ED ensure process is completed smoothly | 0 | Yes | 1 | Growth from the region and weekend RCs | 0 | None | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
52 | A17 | AUSTIN TX (CC5235) | 9430 RESEARCH BLVD STE II310 | AUSTIN | TX |  |  | May-August |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A16 | BURNET TX (CC5233) | 309 INDUSTRIAL BLVD STE 2 | BURNET | TX |  |  | May-August |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A18 | KYLE TX (CC5234) | 1300 DACY LN STE 170 | KYLE | TX |  |  | Feb-June 2026 |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A56 | SMITHVILLE TX (CC5238) | 150 SETTLEMENT DR STE F2 | BASTROP | TX |  |  | Feb-June 2026 |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A19 | WACO TX (CC5236) | 510 N VALLEY MILLS DR STE 504 | WACO | TX |  |  | April-July 2026 |  |  |  |  | 13 | Wendi Pack | Ascension at Home Waco TX | NA | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Immediate skilled needs such as wound care, IV, or Ortho patients. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Once the chart has been green tagged. | 1 | Growth member lets the DCS and schedulers know | 0 | No | 2 | Intake checks the portals and the DCS on call monitors the emails/ schedules out the admissions. | 0 | NA
54 | A80 | RICHMOND VA (CC5509) | 2603 NINE MILE RD STE 200 | RICHMOND | VA | [8 empty] | Allison Bohn | Bon Securs Home Care by Compassus, Richmond VA | NA | Disagree |  | H3 We're stretched thin |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV, LVAD, some surgeries depending on MD, certain wound care | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | Growth | 1 | BSMH Partner creates the most challenges. Expectations to accept all patients are high but in return we are not consistently given first right of refusal if patient has no preference. | 1 | Growth | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Depending on where the referral is coming from, Growth is also responsible for gathering missing referral documents and patient information | 0 | None | 0 | Yes | 1 | Scheduling | 0 | Communication during huddle, in emails and on scheduling grid | 0 | Yes | 1 | Referral Coordinator | 0 | None | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
54 | A81 | SUFFOLK VA (CC5513) | 7007 HARBOUR VIEW BLVD STE 114 | SUFFOLK | VA | [8 empty] | Erica Dejesus | Bon Secours with Compassus - Suffolk | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
54 | A83 | VIRGINIA BEACH VA (CC5515) | 184 BUSINESS PARK DR STE 100 | VIRGINIA BEACH | VA | [8 empty] | Erica DeJesus | Virginia Beach VA | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
61 | B22 | Olympia WA |  | LACEY | WA |  |  | October-December 2026 |  |  |  |  | 15 | [56 empty] | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B26 | Seattle WA |  | TUKWILA | WA |  |  | October 2026 - January 2027 | [5 empty] | Jonelle McGee | Seattle, WA/ King County | NA | Agree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Someone who has wound care is considered urgent, as well as other nursing needs. | 1 | H3 Currently on VBE |  | I am a fairly new ED, but we are focused on really turning things around with metrics, EBITDA, census, productivity, STAR ratings, VBP, etc. We are currently recruiting/hiring for growth and there is major education initiatives and rebuilding going on in our ministry. | 0 | M2 Some Coaching and Reinforcement |  | ED/DCSs | 1 | We do accept charity care and also accept Medicaid and payor sources that make it harder to obtain EBITDA targets. As we are hiring for growth, we need to form community relationships with hospitals outside of our VBEs that DC patients to other areas of our territory that our VBEs do not DC patients to. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | The responsible roles listed in #11 above vary. If the referrals are incomplete and make it to scheduling, then more manpower is needed in the ministry to try and complete the referrals. Ideally, this would all happen at intake prior to it entering the scheduling workflow. | 1 | We still need to hire a weekend scheduler. Right now our weekday schedulers are taking turns covering weekends, which creates problems, as they need to take a comp day off, and we are currently short on schedulers. Our DCS team is supposed to be working hand-in-hand with schedulers to ensure clinician productivity is maximized and clinicians have maximum SOC visits assigned as possible. | 1 | No | 2 | When attempting to schedule the SOC visit | 0 | The DCS and/or ED should be notified | 0 | Yes | 1 | schedulers and administrator on call | 1 | We are eager to incorporate anything that could help with the conversion of referral to SOC | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B21 | Snohomish County WA |  | EVERETT | WA |  |  | April-June 2026 |  |  |  |  | 15 | Mirna Musun | [55 empty] | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B27 | Spokane WA |  | SPOKANE | WA | [8 empty] | Derek Salminen | PAH Spokane WA | N/a | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Those with high needs. New ostomies, wound vacs, IV ABX, ortho patients. | 1 | H3 Currently on VBE |  | For Spokane we are going to be going through a CHAPs Survey. We are looking to expand and are only limited by field clinicians at this time. | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | For all of our referral sources we have to educate that Spokane is no longer a non-profit entity and we have to look at insurance types before accepting. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | N/A | 0 | None | 0 | Yes | 1 | ? | 1 | Operations is notified by the community outreach group. When the referral comes in ED or DCS ensure that the referral is pushed timely through intake and insurance. | 1 | Yes | 1 | We have one dedicated scheduler who works the weekends | 1 | N/A | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B28 | Walla Walla WA |  | WALLA WALLA | WA |  |  | July-September 2026 |  |  |  |  | 15 | Jessica Dougherty-Burt | [55 empty] | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
53 | A12 | RHINELANDER WI (CC5827) | 111 E DAVENPORT ST STE 101 | RHINELANDER | WI | [8 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A64 | CHIPPEWA FALLS WI (CC5835) | 134 W COLUMBIA ST STE 2 | CHIPPEWA FALLS | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A57 | GREEN BAY WI (CC5834) | 480 PILGRIM WAY STE 1250 | ASHWAUBENON | WI | [8 empty] | Brenda Lefeber | Green Bay WI | Neenah WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A09 | MARSHFIELD WI (CC5822) | 303 W UPHAM ST STE 208 | MARSHFIELD | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A14 | MILWAUKEE WI (CC5823) | 135 S 84TH ST STE 150 | MILWAUKEE | WI | [8 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A07 | NEENAH WI (CC5824) | 816 W WINNECONNE AVE | NEENAH | WI | [8 empty] | Brenda Lefeber | Neenah Wi | Green Bay WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A10 | PLOVER WI (CC5825) | 1840 POST RD STE 5 | PLOVER | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A15 | RACINE WI (CC5826) | 13200 GLOBE DR STE 228 | MOUNT PLEASANT | WI | [8 empty] | Melissa Steger | Racine | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H1 Well Staffed |  | Episodic, infusion, ortho, wound | 2 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | No | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | HHCC and CTC make welcome calls. PTC monitors referral portals and gather info as needed. | 1 | If schedulers are unable to contact patients, our PTC will sometimes assist with contacting. | 1 | No | 2 | Once the referral is 'pushed to scheduling' and is in our scheduler's workflow, the scheduler will make the readiness call. The growth team members make their welcome calls prior to this step. | 1 | ED and AME involvement as needed | 0 | Yes | 1 | RC team, AOC, and scheduler | 0 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A13 | ARBOR VITAE WI (CC5821) | 1571 HIGHWAY 51 N STE C | ARBOR VITAE | WI | [8 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A59 | SHEBOYGAN WI (CC5833) | 2124 KOHLER MEMORIAL DR STE 200 | SHEBOYGAN | WI | [8 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A08 | STURGEON BAY WI (CC5828) | 231 KEEL CT | STURGEON BAY | WI | [8 empty] | Marla Wills | AAH w/Compassus Sturgeon Bay | N/A | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | IV patient, pleurex, CHF/COPD | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | NA | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Referral Coordinators | 1 | Ed/DCS | 0 | NA | 0 | NA | 0 | No | 2 | After Intake | 0 | By Ed Direction | 0 | No | 2 | Admin on Call | 1 | N/A | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A11 | WAUSAU WI (CC5829) | 2600 STEWART AVE STE 160 | WAUSAU | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
DeNovos
Denver CO
Colorado Springs
Note on AD1: Align with pilot high acuity definition = 1 Different from pilot high acuity =2
Note on AH1: 1 for each item listed
Note on AL1: Count
Note on AP1: Growth = 0, anything else = 1
Note on AR1: Growth = 0, anything else = 1
Note on AT1: RC=0, Any other role =1
Note on AV1: RC=0, any other role =1
Note on AZ1: Scheduler = 0, anything else =1
Note on BD1: ED/DCS=0, anything else = 1
Note on BF1: 1 point for each item listed if outside of standard process
Note on BH1: 1 point for each item listed
Note on BJ1: YES = 1 NO =2
Note on BL1: 1 point for anything outside of standard process; one point if no process
Note on BN1: 1 point for any process that outside of pilot process
Note on BP1: Yes = 1, No = 2
Note on BR1: Intake/Growth = 0, any other role = 1
Note on CG1: 1 = Aligns with pilot high acuity definition 2 = Different than pilot high acuity definition
Note on CJ1: Total portal in #6 (8) minus portals not used in 7
Note on CL1: Count of additonal portals used
Note on CN1: Count of payors listed requiring extra steps
Note on CR1: 1 point for each initiative listed
Note on CV1: Count
Note on CX1: 1 point for each challenge listed
Note on CZ1: If Growth = 0, anything else = 1
Note on DB1: If growth = 0, any other role =1
Note on DD1: If RC = 0, any other role = 1
Note on DF1: RC = 0, any other = 1
Note on DH1: RC=0, any other = 1
Note on DJ1: Scheduling = 0, any other = 1
Note on DL1: Scheduling = 0, other = 1
Note on DN1: ED/DCS = 0, other = 1
Note on DP1: 1 point for each item listed if outside standard process of DCS/ED/AME leading huddle
Note on DR1: 1 point for each cross functional role listed
Note on DT1: YES = 1 NO = 2
Note on DV1: 1 point for anything outside of the standard process - 1 point for no process
Note on DX1: 1 point for anyting deviated from pilot processes
Note on DZ1: Yes = 1 No = 2
Note on EB1: Intake or Growth = 0, any other roles or no roles = 1

## List (hidden)
Phase | Overall Categories
Discovery | Governance | Governance
Pre-Pilot Development | Project Team/OpEx | Project Team
UAT | Team Member Experience Plan + Recognition | Org Communication
Active Pilot | Training, Materials & Ambassadors | Team Member Experience Plan + Recognition
Enterprise Rollout | Measurement - Analytics & Feedback | Training
Solution Extensions | Shared Services | Analytics & Engagement
Ongoing Management | Workforce | IT
| Communications | Contracting
Workforce
Status
Not Started
Predecessor Required
In Process
Need Assist
Complete
At Risk
Past Due
On Hold
Not Applicable