## Approach — 10 Steps
HH Scheduling & Capacity Management — How We Got This Initiative Off The Ground
Ten steps. Steps 1 and 10 are endpoints; steps 2–6 are a LOOP that ran three times; step 7 (business case) runs in PARALLEL from the first loop pass; step 8 feeds back into the loop because half of what it finds is a new variable.
Step | The step | What it answers | How we ran it | What came out of it | Passes | Status | What it hands forward
1 | Meetings | What actually happens, and where does it get stuck? | Four distinct meeting types, never interchangeable: discovery (blank page), SME download (one expert, uninterrupted), validation (a DRAFT brought to be corrected), decision (someone who can decide, in the room). Verbatim record kept and line-numbered so every later citation resolves. | Discovery session record · line-numbered transcript · whiteboard record with DE-01…DE-10 · five role-perspective briefs · glossary | 6 sessions | Complete | A vocabulary, a cast of actors, a process spine, and the numbers people said out loud — every one carried forward LABELLED as an estimate.
2 | Developing the variable list | For one visit to happen, what must all be true at once? | Built BEFORE the current-state map, deliberately — a map drawn first only contains what the mapper already thinks about. Grouped into four ID families, then filled each exhaustively. IDs are the join key to every document downstream and are never renumbered. | Variable Inventory — 79 scored rows (76 numbered + 3 unnumbered) · The Concepts That Matter (15-factor distillation) · Big Picture (plain-language) · variable backlog | 3 | Complete | A checklist the current-state map has to be drawn AGAINST, and something for the bottleneck findings to attach to.
3 | Mapping current state | How does the work actually run today? | Design system fixed and written down BEFORE drawing. Split into separate flows rather than one monster. Generated from source scripts so a correction costs a minute, not an afternoon. Colour = actor, and the person beats the system. | Eight current-state flow sheets · four illustrative scenario sheets · process-facts file (the upstream source every sheet draws from) | 3 | Complete | A picture specific enough to be wrong in public — so the people who know better can point at a box and correct it.
4 | Bottlenecks & significant pain points | Where is the energy, and separately, where is the money? | Kept the two apart deliberately. A pain point is what people complain about; a bottleneck is what constrains throughput — and here they were NOT the same. Classified every constraint by CHANGEABILITY, not severity: severity says what hurts, changeability says what to do. | Constraint register CN-01…CN-51 · twelve ranked bottleneck dossiers (7 fields each) · connection points CP-1…CP-10 · failure catalogue | 2 | Complete | The build case (9 immovable constraints), the fast track (4 we own ourselves), and the mechanism behind every business-case lever.
5 | Modifying the list & prioritising | Which of these actually matter, and what do we still not know? | Closed the loop back to step 2 — the list was now three documents old. Re-cut against the map's corrections, the bottleneck weightings and the connection points. Then SCORED, so priority is reproducible from columns rather than remembered from a meeting. | Re-cut scored inventory (weight · gating · conflict risk) · the nine open questions, published in dependency order | 2 | Complete | Derived priority, a knockout list for vendor evaluation, and the #1 open question that gates everything downstream.
6 | Updating the flows as it evolved | Does the picture still match what we now know? | A maintenance discipline, not an event. Corrections land in the process-facts file first, then propagate to the sheets. Anything not yet stable is switched OFF on the sheets — better blank than wrong. Deferrals recorded as scope boundaries. | Redraw assessment §1–26 (every correction, who raised it, what changed) · regenerated flow sheets · the reusable flow-map tooling | 26 rounds | Complete | A current-state baseline nobody argues with — the precondition for drawing any target state.
7 | Business case — opened in PARALLEL | If this works, what changes, in what unit, that someone could count? | Opened at the first loop pass, NOT at the end. Late, it gets built backwards from a number somebody wants to hear; early, it tells you which variables are worth building for. Learned the payment mechanics first — two of the findings turned out to be data-model requirements. | Payer & episode economics reference · 7-part sourced research corpus · house-format capture · business case register (7 families, 5 tiers, anti-double-counting rules, missing-input table, 'must never claim' list) | parallel | In Process | Which variables carry a lever and how big — the third filter on the MVP scope. NOTE: fed a flow sheet and a variable set back INTO the loop.
8 | What feeds the initiative | Does the data we are designing against actually exist? | Three separate instruments, not one: the landscape map (what touches this, and is it real-time), the source war-list (per element: exact report, owner, refresh, exists-today Y/Partial/N), and the coverage scan (what the design assumes exists that does not). | Technology landscape · data index (domains A–J) · source war-list (.md + .csv working instrument) · as-built data spec · ecosystem coverage scan | 2 | In Process | What is buildable in v1 vs. what needs a data programme first — the single biggest determinant of MVP scope. Everything N/Partial is the build backlog.
9 | MVP spec sheet with priorities | What exactly are we building first, and what will it NOT do? | A projection of the variable list through three filters, not a fresh invention — if it needs invention, one of steps 2/5/7/8 is incomplete. Layer, then MVP-required, then sourceable, then a phase-1 posture override. | MVP spec sheet — 19 of 79 variables in scope, 11 gating, every exclusion carrying a reason and a re-entry trigger | 1 | At Risk | The scope the target state gets phased against. AT RISK: QA found a readiness/pending-auth gap and an overstated value claim — see Open Items.
10 | Target / future state | Where are we going, and what is still undecided? | Deliberately deferred until current state stopped moving — a target state drawn earlier encodes your assumptions instead of the organisation's reality. Drawn in the same visual language so current and target lay side by side. | Target-state sheet — every box marked with its release and its automation posture, plus an OPEN panel naming what was deliberately NOT drawn | 1 | At Risk | The phasing conversation. AT RISK: QA found actors missing and a compliance step absent; the sheet has had zero correction rounds — see Open Items.
THE TWO THINGS THAT SHAPED EVERYTHING
1. We refused the presented problem until it was tested. "Scheduling is broken" was wrong — schedulers are administrators, and capacity and scheduling were two functions being run through one spreadsheet. The reframe was the single highest-value output of the initiative, and it is why capacity is phase 1.
2. We sorted the vendor's constraints from the regulator's. Of 51 catalogued constraints only NINE cannot be toggled — those nine are the entire case for building. Four of the loudest pain points turned out to be our own policy and needed no new system at all.

## Document Register
Document Register — every artifact, the step that made it, and what went into it
If a step produced nothing, it did not happen. Use this as the deliverable list when running the ten steps on a new initiative.
# | Document | Step | What went into it | Where it lives | Status
STEP 1 — MEETINGS
1 | Discovery session record | 1 | The full-day cross-functional session. Structured into what schedulers actually do, the end-to-end workflow chain, capacity vs scheduling, clinician dynamics, the tooling landscape, patient engagement, four named processes and a glossary | knowledge/ | Complete
2 | Line-numbered transcript | 1 | The raw whiteboard session recording, numbered so every [T:###] citation resolves eight weeks later | knowledge/source/ | Complete
3 | Whiteboard session record | 1 | The 13 Aug on-site session: executive summary, decisions DE-01…DE-10, named bottlenecks, adoption constraints, the post-session correction, and the deferrals | knowledge/ | Complete
4 | Five role-perspective briefs | 1 | Role-by-role working sessions — Branch ED, DCS/Clinical Manager, Senior Scheduler, Field RN/SOC nurse, Workforce Strategist. Seeded hypotheses to validate, not settled truth | sme/perspectives/ | Complete
5 | Scheduler insight session agenda | 1 | A question bank for the frontline layer of discovery | sme/sessions/ | Drafted — session NOT yet run
6 | Glossary | 1 | Terms collected across every session — SOC, ROC, DCS, TIC, POC, LUPA, buddy codes, points, Shift Finder, POSFC | knowledge/ | Complete
STEP 2 — VARIABLE LIST
7 | Variable Inventory ★ the spine | 2 | Meetings + the disciplines + the constraints people complained about + the generating question 'what must all be true at once'. 79 scored rows across four ID families | Workbook (Drive) — authoritative | Complete
8 | The Concepts That Matter | 2 | A 15-factor distillation of the inventory — the version for people who will never open the full list | Workbook tab | Complete
9 | Big Picture (plain-language) | 2 | Six groupings — Workforce, Capacity, Demand, Scheduling, Coordination, Results — with primary variables under each | Workbook tab | Complete
10 | Variable backlog | 2 | Variables surfaced but not yet numbered. Three gating-level ones arrived from the 13 Aug session alone | artifacts/ | In Process
STEP 3 — CURRENT STATE
11 | Eight current-state flow sheets | 3 | Meetings + the variable list + 26 correction rounds. Primary map, detailed composite, SOC/ROC, routine visits, authorization, recert & discharge, DCS/scheduler handoff, payer economics | artifacts/ | Complete
12 | Four illustrative scenario sheets | 3 | The variable model rendered as worked days — fictional patients and figures, real decision logic | artifacts/ | Complete
13 | Process-facts file | 3, 6 | The distilled source-confirmed current-state truths plus the binding drawing conventions. Upstream of every sheet | knowledge/ | Complete
STEP 4 — BOTTLENECKS & PAIN
14 | Constraint register CN-01…CN-51 | 4 | The flow sheets + the meetings + the system-of-record SME. Each constraint classified by CHANGEABILITY: regulatory / payer / vendor-configurable / vendor product limit / our own policy / cultural / labour agreement | knowledge/ | Complete
15 | Bottleneck dossiers (12, ranked) | 4 | Same sources, ranked by leverage. Seven fields each: mechanism, evidence, downstream effects, what to measure, candidate remedies, open questions, rank | knowledge/ | Complete
16 | Connection points CP-1…CP-10 | 4 | Derived from the capacity/scheduling split — the seams where a manual system loses information | knowledge/ | Complete
17 | Failure catalogue | 4 | Every named failure grouped by domain: capacity, scheduling, workforce, patient | knowledge/ | Complete
STEP 5 — RE-CUT & PRIORITISE
18 | Re-cut scored inventory | 5 | Step 2 list + the map's corrections + bottleneck weightings + connection-point variables. Scored for weight, GATING (a knockout) and conflict risk | Workbook (Drive) | Complete
19 | The nine open questions | 5 | Everything the first four steps could not resolve, ordered by dependency so answering one unblocks the next. #1 is the point system | knowledge/ | Complete — #1 still unowned
STEP 6 — UPDATING THE FLOWS
20 | Redraw assessment §1–26 | 6 | Every correction, who raised it and what changed; the conversational decisions; each sheet's build notes | artifacts/ | Complete
21 | Flow-map tooling | 6 | Palette, drawing primitives, build script, collision checklist — captured so the conventions survive between sessions and people | skills/ | Complete
STEP 7 — BUSINESS CASE (PARALLEL)
22 | Payer & episode economics | 7 | How payment works, the payer classes, the floors and ceilings, the authorisation object | knowledge/ | Complete
23 | Research corpus (7 parts) | 7 | Sourced and dated external research: rate mechanics, managed care, commercial & Medicaid, utilisation & margin, cost & labour, authorisation ops, value-based & policy | artifacts/reimbursement-research/ | Complete
24 | House business-case format | 7 | An internal case the organisation has already APPROVED, transcribed for its layout, conventions and the revenue anchors finance has blessed | knowledge/ | Complete
25 | Business case register ★ | 7 | Bottleneck dossiers + economics + discovery quantities. Seven families, five tiers, a sizing formula per case, anti-double-counting rules, the missing-input table and the 'must never claim' list | artifacts/ | Complete
26 | Reimbursement-linked variables | 7 → fed back to 5 | What reimbursement ADDS to the variable list | artifacts/ | Complete
27 | Payer-economics flow sheet | 7 → fed back to 3 | The economics rendered onto the process — became the eighth flow sheet | artifacts/ | Complete
STEP 8 — WHAT FEEDS THE WORK
28 | Technology landscape | 8 | The discovery session — each system, its role, and crucially whether it is real-time. Flagged the integrations that exist but are switched OFF | knowledge/ | Complete
29 | Data index (domains A–J) | 8 | The full data dictionary for field-level planning | artifacts/ | Complete
30 | Source war-list (.md + .csv) | 8 | Every data element as a row to be SOURCED: candidate source (a hypothesis), confirmed system, exact report/table/screen, owner, refresh cadence, exists-today Y/Partial/N. Everything N or Partial is the build backlog | artifacts/ | Instrument ready — session not run
31 | As-built data spec | 8 | What the built tool's data model actually is, versus what was specified | artifacts/ | Complete
32 | Ecosystem coverage scan | 8 | The data index diffed against the discovery. Tiered into structural gaps that change the answer, versus extensions | artifacts/ | Complete
STEP 9 — MVP SPEC
33 | MVP spec sheet | 9 | Scored inventory + source war-list + business case register + DE-02/03/04/09. Three filters leaving 19 of 79 variables in scope, 11 gating | artifacts/ | At Risk — QA defects open
STEP 10 — TARGET STATE
34 | Target-state sheet | 10 | Current-state sheets + constraint register + connection points + MVP spec + the decisions register. Every box marked release and posture; six questions deliberately left undrawn | artifacts/ | At Risk — QA defects open
ACROSS ALL STEPS
35 | Drive index | all | Every file in the working folder mapped to where it lives, with nothing unaccounted for | knowledge/ | Complete
36 | Decisions register DE-01…DE-10 | 1, 5 | Registered in-session on 13 Aug. Numbered, quotable, never renumbered | knowledge/ | Complete

## Open Items
Open Items — what must close before this goes to a steering committee or a vendor
BLOCKERS are decisions or defects that make a deliverable wrong or unbuildable. GATES are validations never performed. Findings from a five-specialist QA review, 22 Aug 2026.
ID | Type | Step | The item | Why it matters | Owner | Status
OI-01 | BLOCKER | 5, 8 | Define the point system and the productivity target/ceiling | The MVP's entire output — committed load, remaining capacity, week open room and assessing capacity — is computed from these two. Until they are decided the release has nothing to display. Not a delay; a null release. Open and unowned since 17 Aug. | TBD | Not Started
OI-02 | BLOCKER | 9 | Add pending-authorisation work to committed load, or flag the distortion | Committed load computed from assigned visits alone excludes every pending-auth visit — so 'open room', the MVP's core view, reads HIGH by exactly the work the branch has already accepted. Our own constraint register calls this the single clearest capacity-measurement defect in the current state. The tool would show green while admissions stall upstream. | TBD | Not Started
OI-03 | BLOCKER | 7, 9 | Recompute the MVP value capture lever by lever | The 60% assumption was modelled over an MVP defined as visibility PLUS LUPA flagging PLUS call-out ranking. This scope delivers one of the three, so the quoted figure contains value the same document says v1 cannot produce. Honest range for this cut is roughly 20-50%. | TBD | Not Started
OI-04 | DEFECT | 9 | Fix the arithmetic and the internal contradiction in the MVP spec | Exclusion table sums to 55 against a stated 57; C-10 and C-11 labels swapped; C-04 appears both in-scope and out-of-scope; the sourceability split is not derivable from the document's own table; the Clinician Safety variable is excluded with no reason or re-entry trigger. A document claiming 'derived, not asserted' cannot carry these. | TBD | Not Started
OI-05 | DEFECT | 10 | Restore the DCS and the scheduler as actors on the target state | The DCS appears in the legend and in zero boxes; the scheduler disappears after phase 2, contradicting DE-10 which preserves the role at reduced scale. A clinical manager at this wall sheet sees their colour in the key and their role nowhere in the future. | Colin | Not Started
OI-06 | DEFECT | 10 | Add the 48-hour MD missed-visit notification and the LUPA/30-day period | The sheet shows 'Miss' as a disposition and drops the Medicare obligation behind it. It also models only the 60-day cert period, so it cannot see the payment cliff. A target state that quietly drops a compliance window is a liability. | Colin | Not Started
OI-07 | DEFECT | 10 | Downgrade automated patient confirmation from CONTROL to ASSIST | The workbook scores day-before confirmation as Assist, not Control. Washington/Providence requires a human safety script — a corrective-action commitment, not a preference — and California robocall treatment is an unresolved legal question. The sheet also asserts the answer in a block while listing the same question as open. | Colin | Not Started
OI-08 | GATE | 1, 6 | Run the frontline validation session | The 26 correction rounds came from the map's author and the system-of-record SME. No scheduler or field clinician has ever corrected a sheet. The stated exit test for current state has never been attempted, and the target state was drawn on that unverified precondition. | TBD | Not Started
OI-09 | GATE | 8 | Run the source war-list session | The instrument is built. Until it runs, no displayed number has a named report, a named owner or a stated refresh cadence — which is an acceptance criterion for the MVP. | TBD | Not Started
OI-10 | GATE | 7 | Obtain the pay-model split | Decides whether the capacity number converts to margin at all, and it inverts by model. The named pilot candidates are per-visit offices: best for adoption, worst for proving a margin case. Resolve deliberately in the pilot charter, not at readout. | TBD | Not Started
OI-11 | DECISION | 10 | Close the six questions the target sheet deliberately left undrawn | Where the capacity tool sits relative to Commure; whether we accept the risk of turning off DCS order approval; whether the capacity read is a gate or advice; who owns the capacity number day to day; whether automated confirmation replaces the day-before call. Two are already on record as executive decisions carried elsewhere. | Evan | Not Started

## Timeline (hidden)
March | April | May | June
Analytics | Onboard FL, MI, TX | Onboard & Go-Lives | Onboard & Go-Lives
Contracting | Engage Sarah's DBOS HH Team
Survey Distributed & Returned | Engage Zach Underwood (Growth Training)
IT Review | Finalize Go-Live Schedule
Build People Engagement/Comms/Training Plans | Finalize People Engagement/Comms/Training Plans
Culture Discovery | Identify, Train Ambassadors
Adoption & Behavior Maturity Matrix | Provisoning for Users | Provisoning for Users | Provisoning for Users
Build Ambassador Model | AllScripts Sunset Plan | AllScripts Sunset Plan | AllScripts Sunset Plan
| Additional BOT identification, accounts & provisoning | Additional BOT identification, accounts & provisoning | Additional BOT identification, accounts & provisoning

## Action Issue Tracker (hidden)
Commure Rollout - Action Item Tracker
| TOTAL |  | NOT STARTED | IN PROCESS | AT RISK | COMPLETE | NO LONGER NEEDED
ID | Action or Issue? | Date Ticket Submitted | Action Item / Issue | Description / Details | Owner | Date Identified | Target Date | Status | Notes
1 | Action |  | Partner Referral Lists to Commure |  | Luke/Michael |  |  | Complete | Is this still needed?
2 | Action |  | RVP Update Emails |  | Paige |  |  | No Longer Needed
3 | Action |  | User Guide for All roles | Add other role content to updated Growth Guide | Paige |  |  | Complete | Draft sent to Michael on 6/18
4 | Action |  | Distribute Q&A | Send updated Q&A to all leaders live on Commure | Paige |  |  | Complete | Review by Michael in process
5 | Action |  | DL Creation for Commure Updates |  | Paige/Sara |  |  | Not Started | Explore current options with David/Bassam
6 | Action |  | Static Doc Teams Folder | Create Teams folder & place all static files |  |  |  | Not Started
7 | Action |  | Monthly Intake Agenda for Jodie |  | Paige | 2026-06-17 |  | Complete | Paige/Jodie meeting on 6/18
8 | Action |  | Leader Launch Slides Wk 3 Revisions | Add Role Responsibility Slides | Paige | 2026-06-10 |  | Complete
9 | Action |  | New Hire Education Transition to ED Team | Begin conversation with HH Education Leaders to include Commure training in new hire onboarding | Paige/Sara | 2026-06-11 |  | Not Started
10 | Action |  | Create Partnership Assessment Survey |  | Paige | 2026-06-17 |  | Complete
11 | Action |  | Commure Contractor Requests |  | Paige |  |  | Complete | DOBs received 6/17
12 | Issue |  | Do Not Readmit | Patient on DNR not captured in Commure | Paige/Sara | 2026-06-18 |  | Complete | F/U with Dany, Bre, Piecka - are patients being flagged as Do not readmit
13 | Action |  | 20 Additional Service Accounts | . | Paige | 2026-06-17 |  | Complete | Credential email to Mustafa Commure email on 6/18
14 | Action |  | General Commure UAT Login/Password |  | Paige |  |  | No Longer Needed
15 | Issue |  | IN Ensocare Referrals | Per Lorissa email 6/18, no IN referrals in Ensocare |  |  |  | Complete
16 | Issue |  | Growth Team Auto Assign |  |  |  |  | In Process
17 | Issue |  | Contribution Margin Indicator |  |  |  |  | Complete
18 | Issue |  | CarePort Referral |  |  |  |  | Complete
19 | Issue |  | Sporadic FL Ensocare Issue | Commure not talking back to Ensocare and marking patients in needs review. |  | 2026-06-17 |  | Complete
20 | Action |  | Asana for OpEx |  | Paige | 2026-06-18 |  | No Longer Needed
21 | Action |  | Get all Job Aids from Bre/Holly/Dany/Piecka/Rakcsha |  | Paige | 2026-06-18 |  | Complete | Emails sent to request on 6/18
22 | Action |  | Q&A added to User Guide - remove job related questions |  | Paige | 2026-06-18 |  | Complete
23
24
25
26
27
28
29
30
31
32

## Date Tracking Legend (hidden)
Date Tracking - Calculation Logic
Activity | Calculation (relative to Launch / Go-Live)
Go-Live Intro Email to Leaders | 6 weeks before go-live (GL minus 42 days) - heads-up of launch and what to expect
Teams Channel Created | 4 weeks before go-live (GL minus 28 days)
Pre-Launch Mtg #1 | Thursday ~4 weeks before GL (Thu-before-GL minus 21)
Pre-Launch Mtg #2 | Thursday 3 weeks before GL
Pre-Launch Mtg #3 | Thursday 2 weeks before GL
Pre-Launch Mtg #4 (Last) | Thursday immediately before GL
Pre-Launch Momentum Survey | 2 weeks before GL (GL minus 14)
BOC/BOM/ED Email - Lunch & Materials | 2 weeks before GL (GL minus 14)
Leader Talking Points #1 | 2 weeks before GL (GL minus 14)
Email to Leaders - Go-Live Specifics | 1 week before GL (GL minus 7)
Teams Access - Leaders | 1 week before GL (GL minus 7)
Technical Training | Friday immediately before GL
Leader Talking Points #2 | Friday before GL (with Tech Training)
Teams Access - All Users | Friday before GL (day of Tech Training)
GO-LIVE | Day of go-live - both Remote and In-Person appointments
Leader Talking Points #3 | Monday of go-live week
All-Day Office Hours | Day after go-live (GL + 1)
Office Hours - Daily | Begins 2 days after GL; runs every weekday for 2 weeks
Momentum Survey #1 - Leaders | 3 days after GL
Growth & Ops Session #1 | 1 week after GL (GL + 7)
Leader Session #1 | 1 week after GL (GL + 7)
Insurance & Intake Session | 1 week after GL - first launch in state ONLY
User Survey #1 | 1 weeks after GL
Momentum Survey #2 - Leaders | 2 weeks after GL
Office Hours - 3x/Week | Starts ~Week 3 (GL + 16); runs for 2 weeks
Leader Talking Points #4 | 3 weeks after GL
User Survey #2 | 4 weeks after GL
Momentum Survey #3 - Leaders | 4 weeks after GL
Growth & Ops Session #2 | 30 days after GL
Leader Session #2 | 30 days after GL
Office Hours - 1x/Week | Starts ~Week 5 (GL + 30); runs 2 weeks; huddles transition
Leader Talking Points #5 | 5 weeks after GL
Momentum Survey #4 - Leaders | 6 weeks after GL
Intake Huddles Begin | ~Week 7 (GL + 44) - led by Intake Directors
Leader Talking Points #6 | 7 weeks after GL
User Survey #3 | 8 weeks after GL
Momentum Survey #5 - Final | 8 weeks after GL

## Overall Project
HH Scheduling & Capacity Management |  |  | Key Milestones
Organised by the ten-step approach — see the 'Approach — 10 Steps' tab. Category, Phase and Status use the house vocabularies on the 'List' tab.
Item# | Category | Phase | Task Description | OpEx Owner | Due Date | Status | Date Complete | Notes/Decision
STEP 1 · MEETINGS
1 | Project Team/OpEx | Discovery | Run the full-day cross-functional discovery session (scheduling ops, clinical, technology/data) | Colin | 2026-07-24 | Complete | 2026-07-24 | Primary ground truth. Produced the end-to-end chain, the tooling landscape and the Next Steps list.
2 | Project Team/OpEx | Discovery | Capture the operator SME download into a capacity strategy foundation | Colin | 2026-07-24 | Complete | 2026-07-24 | The capacity stack: staffing caps territory caps day-to-day; culture multiplies all three.
3 | Project Team/OpEx | Discovery | Work the five role perspectives separately | Colin | 2026-07-24 | Complete | 2026-07-24 | Branch ED, DCS/Clinical Manager, Senior Scheduler, Field RN/SOC nurse, Workforce Strategist.
4 | Governance | Discovery | Hold the on-site validation session — map author + system-of-record SME + executive who can decide | Colin / Laci / Evan | 2026-08-13 | Complete | 2026-08-13 | Three seats chosen deliberately. The decision-maker in the room is why ten decisions landed in one day instead of ten email threads.
5 | Governance | Discovery | Register decisions DE-01 through DE-10 in-session | Colin | 2026-08-13 | Complete | 2026-08-13 | Numbered, quotable, never renumbered. Deferrals recorded with the same discipline.
6 | Project Team/OpEx | Discovery | Keep a line-numbered verbatim record so every citation resolves | Colin | 2026-08-13 | Complete | 2026-08-13 | What makes a claim auditable eight weeks on.
7 | Project Team/OpEx | Discovery | Run the scheduler insight session and observe end-of-day workflow |  |  | Not Started |  | THE FRONTLINE LAYER OF DISCOVERY IS STILL OPEN. Agenda and question bank drafted 7/24.
STEP 2 · DEVELOPING THE VARIABLE LIST
8 | Measurement - Analytics & Feedback | Discovery | Build the variable inventory — 'for one visit to happen, what must all be true at once?' | Colin / Laci | 2026-08-13 | Complete | 2026-08-13 | Built BEFORE the map, deliberately. 79 scored rows = 76 numbered + 3 unnumbered.
9 | Measurement - Analytics & Feedback | Discovery | Establish the four ID families (SH- / C- / S- / CO-) as the join key |  | 2026-08-13 | Complete | 2026-08-13 | Never renumbered. Every downstream document cites these.
10 | Measurement - Analytics & Feedback | Discovery | Score each row for constraint class, MVP requirement and AUTOMATION POSTURE |  | 2026-08-13 | Complete | 2026-08-13 | Posture recorded before meeting any product — it is what later turned a high vendor score into a visible fit problem.
11 | Communications | Discovery | Produce the 15-factor distillation and the plain-language six-group view |  | 2026-08-13 | Complete | 2026-08-13 | For everyone who will never open the full list.
12 | Measurement - Analytics & Feedback | Discovery | Keep a backlog of variables surfaced but not yet numbered |  |  | In Process |  | Three gating-level ones arrived from the 13 Aug session alone. Work it down at each inventory update.
STEP 3 · MAPPING CURRENT STATE
13 | Project Team/OpEx | Discovery | Fix the drawing design system before drawing anything | Colin | 2026-08-17 | Complete | 2026-08-17 | Palette, block semantics, legend — captured as reusable tooling so conventions are never re-derived.
14 | Project Team/OpEx | Discovery | Draw current state as separate flows, generated from source | Colin | 2026-08-18 | Complete | 2026-08-18 | Eight sheets. A correction costs a minute, not an afternoon.
15 | Project Team/OpEx | Discovery | Apply the colour rule: colour = actor, and the person beats the system | Colin | 2026-08-18 | Complete | 2026-08-18 | DE-07. The corrected legend showed genuine automation in HCHB is approximately nil. The colour rule IS the finding.
16 | Communications | Discovery | Build worked scenario sheets so the variables feel like a real day | Colin | 2026-08-12 | Complete | 2026-08-12 | Registers do not convince anyone. A worked day does.
STEP 4 · BOTTLENECKS & SIGNIFICANT PAIN POINTS
17 | Governance | Discovery | Build the constraint register CN-01…CN-51, classified by CHANGEABILITY | Colin | 2026-08-17 | Complete | 2026-08-17 | Severity says what hurts; changeability says what to do.
18 | Governance | Discovery | Isolate the nine constraints that cannot be toggled — the case for building | Colin | 2026-08-17 | Complete | 2026-08-17 | CN-22…CN-30. These nine are the entire argument for a new platform.
19 | Finish the Job Priorities | Discovery | Isolate the four constraints we own ourselves — the fast track | Colin | 2026-08-17 | Complete | 2026-08-17 | CN-18, CN-31, CN-32, CN-33. No vendor dependency, no waiting.
20 | Project Team/OpEx | Discovery | Write twelve bottleneck dossiers, ranked by leverage | Colin | 2026-08-17 | Complete | 2026-08-17 | Seven fields each so they compare rather than merely list.
21 | Measurement - Analytics & Feedback | Discovery | Map the ten connection points CP-1…CP-10 |  | 2026-08-17 | Complete | 2026-08-17 | The seams. CP-3 governs growth, CP-4 governs waste, CP-5 underlies both and was undefined.
22 | Governance | Discovery | Separate the loudest pain point from the binding constraint |  | 2026-08-17 | Complete | 2026-08-17 | They were not the same. Auth noise is the loudest; SOC-capable availability is the constraint.
STEP 5 · MODIFYING THE LIST & PRIORITISING
23 | Measurement - Analytics & Feedback | Discovery | Re-cut the inventory against the map's corrections and the bottleneck weightings |  | 2026-08-17 | Complete | 2026-08-17 | The list was three documents old. Closing the loop back to step 2.
24 | Measurement - Analytics & Feedback | Discovery | Derive weight, GATING flag and conflict risk from the columns |  | 2026-08-17 | Complete | 2026-08-17 | Priority reproducible from columns — nobody has to remember a meeting. Gating is a knockout, not a weighting.
25 | Governance | Discovery | Publish the nine open questions in dependency order |  | 2026-08-17 | Complete | 2026-08-17 | Ordering by dependency is the trick. An unordered list of unknowns produces parallel flailing.
26 | Measurement - Analytics & Feedback | Discovery | DEFINE THE POINT SYSTEM — open question #1 |  |  | Need Assist |  | The shared currency of both capacity and scheduling. Referenced everywhere, defined nowhere. Gates most downstream specification AND the MVP. Unowned since 17 Aug.
STEP 6 · UPDATING THE FLOWS AS THE CONVERSATION EVOLVED
27 | Project Team/OpEx | Discovery | Run corrections to ground — 26 numbered rounds, retained | Colin | 2026-08-18 | Complete | 2026-08-18 | Done when a session produces no new corrections, not when the drawing looks good.
28 | Project Team/OpEx | Discovery | Keep one process-facts file upstream of every sheet | Colin | 2026-08-18 | Complete | 2026-08-18 | Corrections land there first, then propagate.
29 | Governance | Discovery | Record the deferrals as scope boundaries | Colin | 2026-08-18 | Complete | 2026-08-18 | A deferral you recorded is a boundary. One you didn't is a surprise in month four.
30 | Project Team/OpEx | Discovery | Validate current state with frontline schedulers and field clinicians |  |  | Not Started |  | THE 26 ROUNDS CAME FROM THE MAP'S AUTHOR AND THE SYSTEM SME — never from people who do the work daily. This is a gate before the steering committee.
STEP 7 · BUSINESS CASE — RUN IN PARALLEL, NOT AT THE END
31 | Measurement - Analytics & Feedback | Discovery | Learn how the money actually works before sizing anything | Colin | 2026-08-19 | Complete | 2026-08-19 | Payment is per 30-day period, not per cert period. There is a ceiling as well as a floor. Several levers invert by payer class.
32 | Governance | Discovery | Find and match the house business-case format before drafting | Colin | 2026-08-21 | Complete | 2026-08-21 | Copy the layout, conventions and the revenue anchors finance has already blessed.
33 | Governance | Discovery | Write the business case register — mechanism, evidence, formula, tier, missing input | Colin | 2026-08-21 | Complete | 2026-08-21 | Seven families, five tiers. Includes the anti-double-counting rules and the 'must never claim' list.
34 | Measurement - Analytics & Feedback | Discovery | Build the assumptions model that feeds the two-panel output |  |  | Not Started |  | One sheet of named editable inputs, so the case is argued at the assumption level not the conclusion level.
35 | Workforce | Discovery | Obtain the pay-model split across the estate |  |  | Need Assist |  | THE HIGHEST-VALUE SINGLE INPUT. For per-visit clinicians cost is linear and optimisation cannot create margin; for salaried the marginal visit is near-free.
36 | Measurement - Analytics & Feedback | Discovery | Obtain the remaining finance and ops inputs that convert modelled cases to committed |  |  | Need Assist |  | Scheduler loaded cost, contract/per-diem/overtime baselines, turnover and replacement cost, mileage baseline.
37 | Governance | Discovery | Correct the MVP capture assumption flagged in QA |  |  | At Risk |  | See Open Items OI-02. The 60% was computed over a wider MVP definition; honest range for this scope cut is ~20-50%.
STEP 8 · WHAT FEEDS THE INITIATIVE — PLATFORMS, PROCESSES, WHERE DATA LIVES
38 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Map the system landscape with each system's real-time status |  |  | In Process |  | HCHB (manual sync), Commure, NestMed (real-time), Pulse, Workday, external coding vendor, Circadia.
39 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Flag every integration that exists but is switched off |  |  | In Process |  | Workday-to-HCHB PTO is the found one. Free, immediate, and it delivers a gating variable.
40 | Measurement - Analytics & Feedback | Discovery | Run the source war-list session — exact report, owner, refresh, exists-today per element |  |  | Not Started |  | The instrument is built and ready. Everything returning N or Partial becomes the build backlog.
41 | Measurement - Analytics & Feedback | Discovery | Settle the P0 policy decisions the war-list surfaced |  |  | Need Assist |  | Point-earning rules, expected-points derivation, productivity thresholds. Policy decisions wearing data clothing.
42 | Measurement - Analytics & Feedback | Discovery | Run the coverage scan — what the design assumes exists that does not |  | 2026-08-21 | Complete | 2026-08-21 | Found the readiness gauntlet, the missing economic layer, and the quality/compliance guardrails.
43 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Activate the Workday-to-HCHB PTO integration |  |  | Not Started |  | Exists and is off. Removes manual entry and prevents five of seven nurses being approved off the same day.
44 | Shared Services (IT, Contracting, Marketing, Legal) | Discovery | Legal review — robocall/TCPA, consent timing, regional safety scripting | Colin |  | Not Started |  | Consents not signed until SOC. California robocall treatment. Washington/Providence safety script. Gates any automated outreach.
STEP 9 · MVP SPEC SHEET WITH PRIORITIES
45 | Governance | Discovery | Derive the MVP scope through three filters over the variable list |  | 2026-08-22 | Complete | 2026-08-22 | Layer, then MVP-required, then sourceable, then the phase-1 posture override. 19 of 79 in scope.
46 | Governance | Discovery | Identify the gating subset and state what the MVP will NOT do |  | 2026-08-22 | Complete | 2026-08-22 | 11 gating. 'The MVP does not build the schedule — it makes capacity measurable.'
47 | Governance | Discovery | Close the QA defects on the MVP spec |  |  | At Risk |  | See Open Items OI-01 through OI-04. The readiness/pending-auth gap is the serious one.
STEP 10 · TARGET / FUTURE STATE
48 | Project Team/OpEx | Discovery | Draw the target state, every box marked with release and posture | Colin | 2026-08-22 | Complete | 2026-08-22 | Deferred until current state stopped moving. Six design questions deliberately left undrawn rather than guessed.
49 | Project Team/OpEx | Discovery | Close the QA defects on the target-state sheet |  |  | At Risk |  | See Open Items OI-05 through OI-07.
50 | Project Team/OpEx | Discovery | Walk the target state with the operator and system-of-record SME |  |  | Not Started |  | Current state earned its authority through 26 correction rounds. The target sheet has had zero.

## GoLive Wave Tawas Portage (hidden)
HH Intake Application Launch Tawas City/Alpena/Portage MI |  | Key Milestones
|  | Go-Live Date: 3/11 for Tawas/Alpena & 3/12 for Portage |  | 1:33
|  | In-Person Training Date: 3/11 for Tawas/Alpena & 3/12 for Portage |  | Join
|  | Technical Training Date: 3/6/26 |  | Mike Davis joined the conversation.
Item# | Phase | Task Description | Owner/Resources | Due Date | Status | Date Complete | Notes/Decision
Leadership & Planning
| Leadership & Planning | 4-week meeting series prior to launch date with formal go/no-go on week 4 |  |  | Complete
| Leadership & Planning | Go-Live Readiness checklist |  |  | Complete
| Leadership & Planning | Confirm launch date alignment with vendor |  |  | Complete
| Leadership & Planning | Confirm go-live schedule with RVP/RME |  |  | Complete
| Leadership & Planning | Obtain go-live date alignment with IT/Reporting/Operations (competing launches/pilots?) |  |  | Complete
| Leadership & Planning | Leadership participates in daily huddles during launch period |  |  | Complete
| Leadership & Planning | Manage wave-based action register |  |  | Complete
| Leadership & Planning | Support lead attend tiered escalation huddle (daily) with OpEx/Vendor team |  |  | Complete
| Leadership & Planning | Transition wave huddle to product manager |  |  | Complete
| Leadership & Planning | Distribute Leader Talking Points for 1 week pre-Launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for Go-Live Day | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 1-2 weeks post-launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 3-4 weeks post-launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 5-6 weeks post-launch | Paige |  | Not Applicable
| Leadership & Planning | Distribute Leader Talking Points for 7-8 weeks post-launch | Paige |  | Not Applicable
Pre-Go-Live
| >4 Weeks Pre-Go-Live | Invites for 4 weekly pre-go live huddles sent + welcome communication sent |  |  | Complete
| >4 Weeks Pre-Go-Live | Completion of any market/agency specific platform modifications by vendor (payor, portals, etc.) |  |  | Complete
| 4 weeks Pre-Go-Live | Meeting 1 content: overview deck, review timeline, validate nuances/portals captured in survey, & identify local champions |  |  | Complete
| 4 weeks Pre-Go-Live | Request for data delivery from Compassus to application (Add location to existing feeds/files + AC/growth list) |  |  | Complete
| 4 weeks Pre-Go-Live | Submit request for new production/BOT accounts (if needed) |  |  | Complete
| 4 weeks Pre-Go-Live | Valiadate partnered & growth member assignment in HCHB |  |  | Complete
| 4 weeks Pre-Go-Live | Validate ZIP code master & confirm update in PowerBI |  |  | Complete |  | Issue being investigated
| 4 weeks Pre-Go-Live | Identify referral sources with auto patient placement after portal acceptance |  |  | Not Applicable |  | No partner referral sources in MI
| 4 weeks Pre-Go-Live | Request full user list with email & user category |  |  | Complete
| 3 weeks Pre-Go-Live | Meeting 2 content: Explore in tool, discuss VBE if applicable, validate week 1 requests & show early results |  |  | Complete
| 3 weeks Pre-Go-Live | Provision users & BOTs to platform/HCHB and Compassus SSO for both UAT & PROD (Compasus email, hospicecom.com email, User Group, Branch Codes Needing Access to) |  |  | Complete
| 3 weeks Pre-Go-Live | Submit ticket for DL creation per HCHB Branch ID (note single vs multi branch DLs & exceptions) |  |  | Not Applicable
| 3 weeks Pre-Go-Live | Request date to sever portal feeds to HCHB (including Forcura) |  |  | Complete
| 2 weeks Pre-Go-Live | Meeting 3 content: Go-live logistics, on-site planning, review baseline metrics |  |  | Complete
| 2 weeks Pre-Go-Live | Request revenue (insurance) grant BOT access to Availity, etc. as needed |  |  | Complete
| 2 weeks Pre-Go-Live | Assess need for updates to user guides and/or training decks |  |  | Complete
| 1 week Pre-Go-Live | Meeting 4 content: GO/No-GO decision, final prep, go-live expectations, path forward |  |  | Complete
| 1 week Pre-Go-Live | Establish pre & post -go-live leader huddles |  |  | Complete
| 1 week Pre-Go-Live | Send Office Hours invitations |  |  | Complete
| 1 week Pre-Go-Live | Referral Source Notification (Specifically referral partners) |  |  | Complete
| 1 week Pre-Go-Live | Set-up Teams site or channel for go-live wave |  |  | Complete
| 1 week Pre-Go-Live | Create action register for go-live wave + add to Teams site/channel |  |  | Complete
Training
| Training | Identify trainers & ambassadors for Growth/Intake/Insurance |  |  | Complete
| Training | Provide ambassadors with standaridzed tool-kit |  |  | Complete
| Training | Develop ambassador deployment plan |  |  | Complete
| Training | Develop DBOS deployment plan |  |  | Not Applicable
| Training | Arrange room & lunches for in-person training |  |  | Complete
| Training | Request BOC/BOM to print user guides for training |  |  | Complete
| Training | Send Technical Training Invite (remote) |  |  | Complete
| Training | Send Go-Live Session Invites (one remote/one in-person) |  |  | Complete
| Training | Provide user guides and tip sheets (via email & in trainiing) |  |  | Complete
| Training | Complete training deck revisions |  |  | Complete
| Training | Complete user guide revisions |  |  | Complete
| Training | Grant access to applicable Teams folder |  |  | Complete
| Training | Schedule post-go live breakout sessions for each user group |  |  | Complete
| Training | Distribute testimonial video |  |  | Not Applicable
Go-Live
| Final Readiness Check | Confirm SSO for identified users |  |  | Complete
| Final Readiness Check | Complete readiness checklist |  |  | Complete
| Final Readiness Check | Confirm portal feeds ready for cutover |  |  | Complete
| Final Readiness Check | Confirm go-live time with vendor/agency |  |  | Complete
| Go-Live Day | Distribute go-live communication (or day before?) |  |  | Complete
| Go-Live Day | Confirm portal cutover executed |  |  | Complete
| Go-Live Day | Monitor first referral intake |  |  | Complete
| Go-Live Day | Validate HCHB writebacks |  |  | Complete
| Go-Live Day | Validate eligilility/insurance |  |  | Complete
| Go-Live Day | Provide all-day office hours support & ambassador on-site day of go-live. |  |  | Complete
| Go-Live Day | Validate all users have access to Teams chat for wave |  |  | Complete
| Week 1-2 | Assess need for all-day office hours/support for day after go-live. Send Teams invite. |  |  | Complete
| Week 1-2 | Hold twice-daily office hours for 2 weeks |  |  | Complete
| Week 1-2 | Conduct week 1 breakout sessions & send invitations | Mike |  | Complete
| Week 1-2 | Distribute user surveys bi-weekly for for week 1 | Paige |  | Complete
| Week 3-4 | Distribute user surveys |  |  | Complete
| Week 3-4 | Review user surveys |  |  | Complete
| Week 3-4 | Coach based off of user surveys |  |  | Complete
| Week 3-4 | Capture testiminals from surveys |  |  | Complete
| Week 3-4 | ED/AME/RME Coaching |  |  | Complete
| Week 3-4 | Initial maturity |  |  | Not Applicable
| Week 3-4 | Behavior establishment |  |  | Not Applicable
| Week 5-6 | Distribute user surveys |  |  | Complete
| Week 5-6 | Review user surveys |  |  | Complete
| Week 5-6 | Coach based off of user surveys |  |  | Complete
| Week 5-6 | Capture testiminals from surveys |  |  | Complete
| Week 7-8 | Distribute user surveys |  |  | Complete
| Week 7-8 | Review user surveys |  |  | Complete
| Week 7-8 | Coach based off of user surveys |  |  | Complete
| Week 7-8 | Capture testiminals from surveys |  |  | Complete
| Week 7-8 | Distribute rewards |  |  | Not Applicable |  | Thank you message sent
Stabilization & Optimization
| Stabilization & Optimization | Transition ownership to business owner |  |  | Complete
| Stabilization & Optimization | Confirm & communicate on-going support model |  |  | Complete
| Stabilization & Optimization | Capture Lessons Learned post 30-day go-live (including leaders, ambassadors, opex) |  |  |  |  | Captured in regional huddles
| Stabilization & Optimization | Track & prioritize optimization/enhancement requests |  |  | Complete
| Stabilization & Optimization | Track & Trend Weekly/Monthly Intake Metrics |  |  | In Process
| Stabilization & Optimization | Provide weekly executive snapshot report to market/region leaders |  |  | Complete
| Stabilization & Optimization | Conduct daily/weekly huddles with market leadership for feedback/support |  |  | Complete
| Stabilization & Optimization | Meet with Frontline teams to root cause issues |  |  | Complete
| Week 5-6 | Begin role/title changes |  |  | Not Applicable

## GoLive Market Template
HH Scheduling <Market> Launch |  | Key Milestones
Item# | Phase | Task Description | Owner/Resources | Due Date | Status | Date Complete | Notes/Decision
Pre-Wave Planning
Pre-Go-Live
Training
Go-Live
Stabilization & Optimization
Sunsetting AutomationEdge

## Rollout Schedule (hidden)
HH Intake Platform Rollout Schedule 2026 — Compassus Operational Excellence
TX: Waco+Austin May 12, Kyle+Burnet+Bastrop May 13 ¦ FL: Jax Apr 28, Pen+PC+Tampa+St Pete Apr 29 ¦ KY Jun 2 ¦ OH Wk1 Jun 2-3 (Lorain/Youngstown/Lima/Tiffin), Wk2 Jun 9-10 (Columbus/Mansfield/Marion/Athens) ¦ TN Jun 16 ¦ IN Jun 23-24 ¦ KS+MO Jul 14 ¦ WI Jul 21-22 ¦ OK+MT+NM Jul 28-29 ¦ AL Aug 4 ¦ CA Aug 25-Sep 30 ¦ WA+AK Oct 6-13 ¦ Oregon Oct 20 ¦ Complete Oct 20, 2026
Wave | Month(s) | State(s) | Top 2 Portals | Portal Trigger | # Locs | # Amb | Tue Wk 1 | Wed Wk 1 | Tue Wk 2 | Wed Wk 2 | CHAP Notes | Rollout Notes
Wave 1 | Apr 28–29 | FL | Ensocare #1 Epic CareLink #2 | Ensocare live May | 5 | 2 | 4/28 Tue FL-A: Jacksonville FL | 4/29 Wed FL-A: Pensacola FL FL-B: Panama City FL FL-C: Tampa FL FL-D: St Pete FL | — | — | —
Wave 1 | May 12–13 | TX | AllScripts #1 Epic CareLink #2 | AllScripts ✓ CarePort ✓ | 5 | 2 | 5/12 Tue TX-A: Waco TX TX-B: Austin TX | 5/13 Wed TX-A: Kyle TX TX-B: Burnet TX TX-C: Bastrop TX | — | — | CHAP Feb–Aug (Austin)
Wave 2 | Jun 23–24 | IN | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 8 | 4 | 6/23 Tue IN-A: Anderson IN IN-B: Kokomo IN IN-C: Evansville IN | 6/24 Wed IN-A: Indianapolis IN IN-B: Lafayette IN IN-C: Bloomington IN IN-D: N. Vernon IN IN-D: Veedersburg IN | — | — | CHAP Jan–Apr (past ✓)
Wave 2 | 2026-06-16 | KY | Epic CareLink #1 Aidin #2 | Aidin live Jun | 1 | 1 | 6/2 Tue KY-A: Paducah KY | — | — | — | —
Wave 2 | Jun 9–10 (Wk 2) | OH 1 | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 4 | 2 | 6/9 Tue OH-A: Lorain OH OH-B: Youngstown OH | 6/10 Wed OH-A: Lima OH OH-B: Tiffin OH | — | — | —
Wave 2 | Jun 2–3 (Wk 1) | OH 2 | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 4 | 2 | 6/2 Tue OH-A: Columbus OH OH-B: Mansfield OH | 6/3 Wed OH-A: Marion OH OH-B: Athens OH | — | — | —
Wave 2 | Jun 16 | TN | AllScripts #1 Epic CareLink #2 | AllScripts ✓ + Epic Jul | 2 | 1 | 6/16 Tue TN-A: Centerville TN TN-B: Nashville TN | — | — | — | CHAP May–Jul (past ✓)
Wave 3 | Jul 14 | KS | Ensocare #1 Epic CareLink #2 | Ensocare live May | 2 | 2 | 7/14 Tue KS-A: Pittsburg KS KS-B: Wichita KS | — | — | — | —
Wave 3 | Jul 14 | MO | AllScripts #1 Epic CareLink #2 | AllScripts ✓ live | 1 | 1 | 7/14 Tue MO-A: Columbia MO | — | — | — | —
Wave 3 | Jul 28–29 | MT + NM | Epic CareLink #1 NaviHealth #2 | Epic + NaviHealth Jul | 4 | 2 | 7/28 Tue MT-A: Butte MT NM-A: Santa Fe NM | 7/29 Wed MT-A: Billings MT NM-A: Albuquerque NM | — | — | MT: CHAP Jan–Apr (past ✓)
Wave 3 | Jul 28 | OK | Ensocare #1 Epic CareLink #2 | Ensocare live May | 2 | 2 | 7/28 Tue OK-A: Bartlesville OK OK-B: Tulsa OK | — | — | — | CHAP Feb–Jul
Wave 3 | Jul 14 | SC | NaviHealth #1 Ensocare #2 | NaviHealth live Jul | 1 | 1 | 7/14 Tue SC-A: Greenville SC | — | — | — | —
Wave 3 | Jul 14–15 | VA | NaviHealth #1 Epic CareLink #2 | NaviHealth + Epic Jul | 4 | 2 | 7/14 Tue VA-A: Richmond VA VA-B: Suffolk VA | 7/15 Wed VA-A: Newport News VA VA-B: Virginia Beach VA | — | — | —
Wave 3 | Jul 21–22 (all 12 locs) | WI | Epic CareLink #1 NaviHealth #2 | Epic + NaviHealth Jul | 12 | 6 | 7/21 Tue WI-A: Arbor Vitae WI WI-B: Rhinelander WI WI-C: Sturgeon Bay WI WI-D: Green Bay WI WI-E: Neenah WI | 7/22 Wed WI-A: Racine WI WI-B: Sheboygan WI WI-C: Chippewa Falls WI WI-D: Marshfield WI WI-E: Wausau WI WI-F: Milwaukee WI WI-G: Plover WI | — | — | — | All 12 WI in 1 week with 6 ambassadors. Moved from Aug 4-5 per revised timeline.
Wave 4 | Aug 4 | AL | WATERSHED #1 AllScripts #2 | Watershed live Aug | 2 | 1 | 8/4 Tue AL-A: Pell City AL AL-B: Vestavia AL | — | — | — | —
Wave 4 | Aug 25– Sep 30 | CA (10 locs, slow roll) | AIDA #1 Epic CareLink #2 | AIDA live Sep | 10 | 2 | 8/25: LA North CA 9/8: Inland Empire CA 9/15: Humboldt Co. CA 9/22: Napa Valley CA 9/29: OC Mission Viejo CA | 8/26: High Desert CA 9/9: OC Anaheim CA 9/16: LA South CA 9/23: Sonoma Co. CA 9/30: OC South CA | — | — | CHAP Apr–Jun past Oct–Dec: monitor | CA slow roll 2 locs/wk. Begins Aug 25, completes Sep 30.
Wave 4 | Oct 20 | OR (placeholder) | AIDA #1 | AIDA live Sep | 1 | 1 | 10/20 Tue OR-A: Oregon Launch (TBD) | — | — | — | — | Oregon placeholder. Dates/locations TBD. Added after all other locs complete.
Wave 4 | Oct 6–13 | WA + AK | AIDA #1 Epic CareLink #2 | AIDA live Sep (after CA done) | 6 | 2 | 10/6 Tue WA-A: Spokane WA WA-B: Olympia WA | 10/7 Wed WA-A: Seattle WA WA-B: Snohomish Co. WA AK-A: Anchorage AK | 10/13 Tue WA-A: Walla Walla WA | — | WA: CHAP Apr–Dec (buffer applied) | WA+AK after CA completes. 2 amb. AK shares Wed Oct 7.

## GoLive (hidden)
HH Intake Application Launch |  | Key Milestones
Item# | Phase | Task Description | Owner/Resources | Due Date | Status | Date Complete | Notes/Decision
Pre-Wave Planning
| Leadership & Planning | Establish 4-week meeting series prior to launch date with formal go/no-go on week 4
| Leadership & Planning | Establish go-live window
| Leadership & Planning | Obtain go-live date alignment with IT/Reporting/Operations (competing launches/pilots?)
| Leadership & Planning | Establish operating model to include transition from local to regional on--going support
| Leadership & Planning | Ambassador identification & alignment
| Leadership & Planning | Distribute Leader Talking Points for 1 week pre-Launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for Go-Live Day | Paige
| Leadership & Planning | Distribute Leader Talking Points for 1-2 weeks post-launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for 3-4 weeks post-launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for 5-6 weeks post-launch | Paige
| Leadership & Planning | Distribute Leader Talking Points for 7-8 weeks post-launch | Paige
Pre-Go-Live
| >4 Weeks Pre-Go-Live | Invites for 4 weekly pre-go live huddles sent + welcome communication sent
| >4 Weeks Pre-Go-Live | Completion of any market/agency specific platform modifications by vendor (payor, portals, etc.)
| 4 weeks Pre-Go-Live | Confirm go-live schedule with RVP/RME
| 4 weeks Pre-Go-Live | Meeting 1 content: overview deck, review timeline, validate nuances/portals captured in survey, & identify local champions
| 4 weeks Pre-Go-Live | Request for data delivery from Compassus to application (Add location to existing feeds/files + AC/growth list)
| 4 weeks Pre-Go-Live | Submit request for new production/BOT accounts (if needed)
| 4 weeks Pre-Go-Live | Valiadate partnered & growth member assignment in HCHB
| 4 weeks Pre-Go-Live | Validate ZIP code master & confirm update in PowerBI
| 4 weeks Pre-Go-Live | Identify referral sources with auto patient placement after portal acceptance
| 4 weeks Pre-Go-Live | Request full user list with email & user category
| 3 weeks Pre-Go-Live | Meeting 2 content: Explore in tool, discuss VBE if applicable, validate week 1 requests & show early results
| 3 weeks Pre-Go-Live | Confirm launch date alignment with vendor
| 3 weeks Pre-Go-Live | Provision users & BOTs to platform/HCHB and Compassus SSO for both UAT & PROD (Compasus email, hospicecom.com email, User Group, Branch Codes Needing Access to)
| 3 weeks Pre-Go-Live | Submit ticket for DL creation per HCHB Branch ID (note single vs multi branch DLs & exceptions)
| 3 weeks Pre-Go-Live | Request date to sever portal feeds to HCHB (including Forcura)
| 2 weeks Pre-Go-Live | Meeting 3 content: Go-live logistics, on-site planning, review baseline metrics
| 2 weeks Pre-Go-Live | Request revenue (insurance) grant BOT access to Availity, etc. as needed |  |  |  |  | No need for additional access per Natalia & Kitty
| 2 weeks Pre-Go-Live | Assess need for updates to user guides and/or training decks
| 1 week Pre-Go-Live | Meeting 4 content: GO/No-GO decision, final prep, go-live expectations, path forward
| 1 week Pre-Go-Live | Establish pre & post -go-live leader huddles
| 1 week Pre-Go-Live | Send Office Hours invitations
| 1 week Pre-Go-Live | Referral Source Notification (Specifically referral partners) |  |  |  |  | Add to week 3 deck
| 1 week Pre-Go-Live | Set-up Teams site or channel for go-live wave
| 1 week Pre-Go-Live | Create action register for go-live wave + add to Teams site/channel
| Pre-Go-Live Testing | Enable and validate portal feeds in Commure by the Friday prior to go/no-go decisions | Sara
| Pre-Go-Live Testing | Confirm testing readiness, including user access, test scenarios, insurance configurations, ZIP routing, and Facilitate writeback functionality. | OpEx Team
| Pre-Go-Live Testing | Conduct payer map / audit review (1:1 Home Care Home Base payer map check) | Sara
| Pre-Go-Live Testing | 1:1 payor match for state confirmed before go-live | Sara
| Pre-Go-Live Testing | Confirm referrals are flowing to Commure PROD for go-live branches and accessible to users for pre-launch testing | OpEx / IT
| Pre-Go-Live Testing | On Monday/Tuesday of go/no-go week, conduct extensive end-to-end testing for insurance workflows, ZIP code routing, referral processing, and writebacks, including pushing test referrals to validate operational workflows and system performance. | Intake Supervisor, Intake SME, Insurance Supervisor
| Pre-Go-Live Testing | Track and resolve identified issues, review testing outcomes, and provide readiness recommendations for final go/no-go decisions | OpEx Team
| Pre-Go-Live Testing | Build at-risk technical connection / integration items list for weekly IT call | OpEx Team
Training
| Training | Identify trainers & ambassadors for Growth/Intake/Insurance
| Training | Provide ambassadors with standaridzed tool-kit
| Training | Develop ambassador deployment plan
| Training | Develop DBOS deployment plan
| Training | Arrange room & lunches for in-person training
| Training | Request BOC/BOM to print user guides for training
| Training | Send Technical Training Invite (remote)
| Training | Send Go-Live Session Invites (one remote/one in-person)
| Training | Provide user guides and tip sheets (via email & in trainiing)
| Training | Complete training deck revisions
| Training | Complete user guide revisions
| Training | Grant access to applicable Teams folder
| Training | Schedule post-go live breakout sessions for each user group
| Training | Distribute testimonial video
Go-Live
| Final Readiness Check | Confirm SSO for identified users
| Final Readiness Check | Complete readiness checklist
| Final Readiness Check | Confirm portal feeds ready for cutover
| Final Readiness Check | Confirm go-live time with vendor/agency
| Go-Live Day | Distribute go-live communication (or day before?)
| Go-Live Day | Confirm portal cutover executed
| Go-Live Day | Monitor first referral intake
| Go-Live Day | Validate HCHB writebacks
| Go-Live Day | Validate eligilility/insurance
| Go-Live Day | Provide all-day office hours support & ambassador on-site day of go-live.
| Go-Live Day | Validate all users have access to Teams chat for wave
| Week 1-2 | Assess need for all-day office hours/support for day after go-live. Send Teams invite.
| Week 1-2 | Hold twice-daily office hours for 2 weeks
| Week 1-2 | Conduct week 1 breakout sessions & send invitations | Mike
| Week 1-2 | Distribute user surveys bi-weekly for for week 1 | Paige
| Week 1-2 | Distribute rewards
| Week 3-4 | Distribute user surveys
| Week 3-4 | Review user surveys
| Week 3-4 | Coach based off of user surveys
| Week 3-4 | Capture testiminals from surveys
| Week 3-4 | ED/AME/RME Coaching
| Week 3-4 | Initial maturity
| Week 3-4 | Behavior establishment
| Week 5-6 | Distribute user surveys
| Week 5-6 | Review user surveys
| Week 5-6 | Coach based off of user surveys
| Week 5-6 | Capture testiminals from surveys
| Week 5-6 | Begin role/title changes
| Week 7-8 | Distribute user surveys
| Week 7-8 | Review user surveys
| Week 7-8 | Coach based off of user surveys
| Week 7-8 | Capture testiminals from surveys
| Week 7-8 | Distribute rewards
| Week 7-9 | Transition wave huddle to regional intake director (regional intake huddle)
Stabilization & Optimization
| Stabilization & Optimization | Transition ownership to business owner
| Stabilization & Optimization | Confirm & communicate on-going support model
| Stabilization & Optimization | Capture Lessons Learned post 30-day go-live (including leaders, ambassadors, opex)
| Stabilization & Optimization | Track & prioritize optimization/enhancement requests
| Stabilization & Optimization | Track & Trend Weekly/Monthly Intake Metrics
| Stabilization & Optimization | Provide weekly executive snapshot report to market/region leaders
| Stabilization & Optimization | Conduct daily/weekly huddles with market leadership for feedback/support
| Stabilization & Optimization | Meet with Frontline teams to root cause issues
| Stabilization & Optimization | Test all enhancements/changes in test environment and validate before promoting to production | OpEx Team

## Monthly View (hidden)
Month-by-Month Rollout 2026 — HH Intake Platform ¦ Apr 28 – Oct 20, 2026
April 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 1 | FL – Jacksonville FL | Apr 28 (Tue) — FL-A solo | Ensocare
Wave 1 | FL – Pensacola, Panama City, Tampa, St. Pete | Apr 29 (Wed) — FL-A,B,C,D | Ensocare
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 1 | TX – Waco + Austin TX | May 12 (Tue) — TX-A + TX-B + TX-C | AllScripts ✓
Wave 1 | TX – Kyle + Burnet + Bastrop TX | May 13 (Wed) — TX-A (Kyle) + TX-B (Burnet) + TX-C (Bastrop) ✓ ALL TX done by May 13 | AllScripts ✓
⛔ SKIP | Memorial Day week | Week of May 25 — NO LAUNCHES | Holiday blackout
June 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 2 | TN – Centerville TN + Nashville TN | Jun 16 (Tue) — TN-A + TN-B (same day) | AllScripts + Epic; CHAP May–Jul
Wave 2 | KY – Paducah KY | Jun 16 (Tue) — KY-A | Aidin live Jun
Wave 2 | OH Wk2 – Lorain, Youngstown, Lima, Tiffin | Jun 9 (Tue) + Jun 10 (Wed) — OH-A + OH-B | AllScripts ✓ live
Wave 2 | OH Wk1 – Columbus, Mansfield, Marion, Athens | Jun 2 (Tue) + Jun 3 (Wed) — OH-A + OH-B | AllScripts ✓
Wave 2 | IN (all 8) | Jun 23 (Tue) + Jun 24 (Wed) — 4 ambassadors (IN-A/B/C/D) | AllScripts ✓ — CHAP Jan–Apr past
⛔ SKIP | Independence Day week | Week of Jun 29 — NO LAUNCHES | Holiday blackout
July 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
⛔ SKIP | Jul 7 (Tuesday) | Jul 7 — NO LAUNCH (holiday) | Holiday blackout
Wave 3 | SC – Greenville SC ¦ KS – Pittsburg + Wichita ¦ MO – Columbia MO | Jul 14 (Tue) — SC-A + KS-A/B + MO-A | NaviHealth (SC) · Ensocare (KS) · AllScripts (MO)
Wave 3 | VA – Richmond, Suffolk, Newport News, Virginia Beach | Jul 14 (Tue) + Jul 15 (Wed) — VA-A + VA-B | NaviHealth + Epic Jul
Wave 3 | CA PILOT – California (1 location TBD) | 📍 START PILOT IN CALIFORNIA Jul 14 (Tue) — length TBD | TBD
Wave 3 | WI – All 12 locations (Tue: Arbor Vitae, Rhinelander, Sturgeon Bay, Green Bay, Neenah · Wed: Racine, Sheboygan, Chippewa Falls, Marshfield, Wausau, Milwaukee, Plover) | Jul 21 (Tue) + Jul 22 (Wed) — 6 ambassadors (WI-A/B/C/D/E/F) | Epic + NaviHealth
Wave 3 | OK – Bartlesville + Tulsa ¦ MT – Butte MT + Billings MT ¦ NM – Santa Fe NM + Albuquerque NM | Jul 28 (Tue) — OK-A/B + MT-A + NM-A Jul 29 (Wed) — MT-A (Billings) + NM-A (Albuquerque) | Ensocare (OK) · Epic+NaviHealth (MT/NM)
August 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 3 | AL – Pell City + Vestavia (all locations same day) | Aug 4 (Tue) — AL-A + AL-B | Watershed (AL)
Wave 4 | CA – LA North CA (slow roll begins) | Aug 25 (Tue) — CA-A | AIDA live Sep — 2 locs/wk pace
September 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
⛔ SKIP | Sept 7 (Tuesday) | Jul 7 — NO LAUNCH (holiday) | Holiday blackout
Wave 4 | CA – Inland Empire + OC Anaheim | Sep 8 (Tue) + Sep 9 (Wed) — CA-A + CA-B | AIDA
Wave 4 | CA – Humboldt Co. + LA South | Sep 15 (Tue) + Sep 16 (Wed) — CA-A + CA-B | AIDA
Wave 4 | CA – Napa Valley + Sonoma Co. | Sep 22 (Tue) + Sep 23 (Wed) — CA-A + CA-B | AIDA
October 2026
Wave | State(s) / Location | Launch / Duration | Portal Context
Wave 4 | WA – Spokane + Olympia | Oct 6 (Tue) — WA-A + WA-B | AIDA
Wave 4 | WA – Seattle + Snohomish Co. ¦ AK – Anchorage | Oct 7 (Wed) — WA-A + WA-B + AK-A | AIDA
Wave 4 | WA – Walla Walla WA | Oct 13 (Tue) — WA-A ✓ WA+AK COMPLETE Oct 13 | AIDA
Wave 4 | OR – Oregon Launch (TBD) 📍 | Oct 20 (Tue) — OR-A (PLACEHOLDER) ✓ ALL ROLLOUTS COMPLETE | AIDA / Tango

## Timeline View (hidden)
2026 Rollout Timeline — Home Health Intake Platform ¦ Apr 28 – Oct 20, 2026
State (Wave) | Apr/May | June | July | Aug | Sep | Oct | Additional Project Team Support
FL (Wave 1) | Apr 28 (Tue): Jacksonville FL Apr 29 (Wed): Pensacola + Panama City + Tampa & St. Pete | [5 empty] | James or Paige go to Panama City
TX (Wave 1) | May 12 (Tue): Waco + Austin May 13 (Wed): Kyle + Burnet + Bastrop | [5 empty] | Michael/Luke
KY (Wave 2) |  | Jun 16 (Tue): Paducah KY
OH (Wave 2) |  | Jun 9-10: Wk1 (Lorain, Youngstown, Lima, Tiffin) Jun 2-3: Wk2 (Columbus, Mansfield, Marion, Athens) |  |  |  |  | All available support
TN (Wave 2) |  | Jun 16 (Tue): Centerville + Nashville |  |  |  |  | Paige/James
IN (Wave 2) |  | Jun 23–24: All 8 locs (4 ambassadors) |  |  |  |  | TBD to Indianapolis + Evansville + Anderson
KS (Wave 3) |  |  | Jul 14 (Tue): Pittsburg + Wichita (2 ambassadors)
MO (Wave 3) |  |  | Jul 14 (Tue): Columbia MO
CA PILOT (Wave 3) |  |  | 📍 START PILOT IN CALIFORNIA Jul 14 (Tue) — length TBD
SC (Wave 3) |  |  | Jul 14 (Tue): Greenville SC
VA (Wave 3) |  |  | Jul 14 (Tue) + Jul 15 (Wed): Richmond, Suffolk, Newport News, Virginia Beach
WI (Wave 3) |  |  | Jul 21 (Tue) + Jul 22 (Wed): All 12 locs (6 ambassadors) |  |  |  | TBD to Milwaukee; Neenah; Racine
OK (Wave 3) |  |  | Jul 28 (Tue): Bartlesville + Tulsa (2 ambassadors)
MT (Wave 3) |  |  | Jul 28 (Tue): Butte MT Jul 29 (Wed): Billings MT
NM (Wave 3) |  |  | Jul 28 (Tue): Santa Fe NM Jul 29 (Wed): Albuquerque NM
AL (Wave 3) |  |  |  | Aug 4 (Tue): Pell City + Vestavia (all locations same day) |  |  | Paige & James
CA (Wave 4) |  |  |  | Aug 25 (Tue): slow roll begins (2 locs/wk) | Sep 8–30: Continued slow roll ✓ Done Sep 30 |  | TBD
WA (Wave 4) | [5 empty] | Oct 6 (Tue): Spokane + Olympia Oct 7 (Wed): Seattle + Snohomish Co. Oct 13 (Tue): Walla Walla | TBD
AK (Wave 4) | [5 empty] | Oct 7 (Wed): Anchorage AK | TBD
OR (Wave 4) | [5 empty] | Oct 20 (Tue): Oregon (placeholder) 📍 TBD — COMPLETE | TBD
⛔ NO LAUNCHES: Week of May 25 (Memorial Day) · Week of Jun 29 (Independence Day) · Week of Jul 6 (week after Jul 4) · Jul 7 is a Tuesday — no launch
Wave 1 — Apr/May ¦ FL · TX |  | Wave 2 — June ¦ KY · TN · OH · IN |  | Wave 3 — July ¦ KS · MO · SC · VA · WI · OK · MT · NM · AL |  | Wave 4 — Aug–Oct ¦ CA · WA · AK · OR

## Legend (hidden)
Launch Date Reference — HH Intake Platform Rollout 2026 ¦ Complete by Oct 20, 2026
Wave | State | # Locs | First Launch | Last Launch
Wave 1 | FL | 5 | Tue Apr 28, 2026 | Wed Apr 29, 2026
Wave 1 | TX | 5 | Tue May 12, 2026 | Wed May 13, 2026
Wave 2 | KY | 1 | Tue Jun 16, 2026 | Tue Jun 16, 2026
Wave 2 | OH | 8 | Tue Jun 2, 2026 | Wed Jun 10, 2026
Wave 2 | TN | 2 | Tue Jun 16, 2026 | Tue Jun 16, 2026
Wave 2 | IN | 8 | Tue Jun 23, 2026 | Wed Jun 24, 2026
Wave 3 | KS | 2 | Tue Jul 14, 2026 | Tue Jul 14, 2026
Wave 3 | MO | 1 | Tue Jul 14, 2026 | Tue Jul 14, 2026
Wave 3 | SC | 1 | Tue Jul 14, 2026 | Tue Jul 14, 2026
Wave 3 | VA | 4 | Tue Jul 14, 2026 | Wed Jul 15, 2026
Wave 3 | WI | 12 | Tue Jul 21, 2026 | Wed Jul 22, 2026
Wave 3 | OK | 2 | Tue Jul 28, 2026 | Tue Jul 28, 2026
Wave 3 | MT | 2 | Tue Jul 28, 2026 | Wed Jul 29, 2026
Wave 3 | NM | 2 | Tue Jul 28, 2026 | Wed Jul 29, 2026
Wave3 | AL | 2 | Tue Aug 4, 2026 | Tue Aug 4, 2026
Wave 4 | CA | 10 | Tue Aug 25, 2026 | Wed Sep 30, 2026
Wave 4 | WA | 5 | Tue Oct 6, 2026 | Tue Oct 13, 2026
Wave 4 | AK | 1 | Wed Oct 7, 2026 | Wed Oct 7, 2026
Wave 4 | OR | 1 | Tue Oct 20, 2026 (placeholder) | Tue Oct 20, 2026

## Discovery Survey Results (hidden)
ED Survey Received | RME/AME Survey Received | REGION | Branch Code | Branch Name | Street | City | State | Phone | Fax | Home Health Branch ID (M0016) | Time Zone ID | Tech Training | Breakout Training | GO-LIVE | RVP/RME/ED Rollout Notes | Require Extra Attention | Feb 2026 | # of 2025 Months <-5% Budget | 2026 CHAP Survey Anticipated | Benefits (25%) | Efforts (25%) | Risks (25%) | Alignment (25%) | Score | ED SURVEY | 1. Program Name | 2. Branches | 3. Manage increase in referrals/admissions with current clinical staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 4. Current Field Clinician Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. VBE Status | 6 SCORE | 7. Major Initiatives | 7 SCORE | 8. Team response to new process or tool | 8 SCORE | 9. Groups requiring more change management | 9 SCORE | 10. Challenging referral source relationships | 10 SCORE | 11. Task "Monitor referral portals & respond to new referrals" | 11 SCORE | 11. Task "Gather missing referral documents & patient information" | 11 SCORE | 11. Task "Create chart in HCHB for new referral" | 11 SCORE | 11. Task "Complete "Review External Referral Request" workflow in HCHB" | 11 SCORE | 11. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 11 SCORE | 11. Task "Schedule patient's SOC visit in HCHB" | 11 SCORE | 11. Task "Make welcomes/readiness calls" | 11 SCORE | 11. Task "Lead referral huddles" | 11 SCORE | 12. Divided duties | 12 SCORE | 13. Cross functional roles | 13 SCORE | 14. Growth team authority to accept referrals with no ED/DCS input | 14 SCORE | 15. When do welcome calls occur? | 15 SCORE | 16. Handling of urgent or high priority referrals? | 16 SCORE | 17. Weekend Schedulers | 17 SCORE | 18. Weekend Referral Management | 18 SCORE | 19. Additional Input | RME/AME Survey | 1. Market Name | HH Locations | 3. Manage increase in referrals/admissions with current growth staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. All Portals Used in Order | 7. Portals NOT used | 6 & 7 SCORE | 8. Portals Used Not Listed in #7 | 8 SCORE | 9. Payors requiring extra op steps | 9 SCORE | 10. VBE Status | 10 SCORE | 11. Major initiatives | 11 SCORE | 12. Team Response to New Process/Tool | 12 SCORE | 13. Groups requiring more change management | 13 SCORE | 14. Referral source creating challenges | 14 SCORE | 15. Task " Monitor referral portals & respond to new referrals" | 15 SCORE | 15. Task "Gather missing referral documents & patient information" | 15 SCORE | 15. Task "Create chart in HCHB for new referral" | 15 SCORE | 15. Task "Complete "Review External Referral Request" workflow in HCHB" | 15 SCORE | 15. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 15 SCORE | 15. Task "Schedule patient's SOC visit in HCHB" | 15 SCORE | 15. Task "Make welcomes/readiness calls " | 15 SCORE | 15. Task "Lead referral huddles" | 15 SCORE | 16. Divided duties | 16 SCORE | 17. Cross functional roles | 17 SCORE | 18. Growth team authority to accept referrals with no ED/DCS input | 18 SCORE | 19. When do welcome calls occur? | 19 SCORE | 20. Handling of urgent or high priority referrals? | 20 SCORE | 21. Weekend Schedulers | 21 SCORE | 22. Weekend Referral Management | 22 SCORE | 23. Additional Input
|  | 50 | A00 | VESTAVIA AL (CC1028) | 1900 INTERNATIONAL PARK DR STE 250 | BIRMINGHAM | AL | (205) 313-2800 | (205) 313-2801 | N | (GMT - 06:00) CENTRAL | [5 empty] | 1021 | [7 empty] | Kerri Couch | Vestavia AL | No | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Risk for rehospitalization, ORTHO, IV, Wound, New 02 | 1 | L1 No Plan for 2026 | 1 | We currently have 3 new DCS's, 1 on leave and 2 with 6m experience. We have hired over 10 new nurses for the field currently in training. | 1 | L1 Open to Change Adapt Quickly | 1 | Scheduling | 1 | VA Getting Auth Approvals | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Referral Coordinators and DCS will process non-admits, RC will do it if it is done prior to scheduling the patient out to a clinician. We have RN clinical coordinator that will do readiness calls and run the scheduling meeting at 3:30 to triage all of admissions. | 2 | Our Schedulers work a day on the weekend and take a day off during the week, Our DCS take call during the weeknights and on the weekends work at their computers all day Saturday and Sunday. Document Specialist work weekends. | 2 | Yes | 1 | Once the SOC comes to workflow | 0 | growth team member usually gives us a heads up that it is coming in an email so we are prepared. We have a scheduling meeting daily at 3:30. It is on our grid already and we schedule it out once it comes to workflow and it is confirmed. | 1 | Yes | 1 | Document Specialists | 1 | The weekends are the worst for missed referrals and/or slow process for getting them to workflow to assign to the clinicians in the field. We use a excel spreadsheet to put the patients on daily and it could be anywhere from 40-100 patients on that grid depending on the day. So, we get a ton of emails to follow for the patient to enter on that grid. | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
|  | 50 | A01 | PELL CITY AL (CC1027) | 2401 STEMLEY BRIDGE RD STE 7 | PELL CITY | AL | (205) 884-7202 | (205) 313-2801 | N | (GMT - 06:00) CENTRAL | [5 empty] | 666 | [7 empty] | Christina Isbell | Pell City AL | None | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | pt acuity criteria, referral partner consideration, time sensitive care coordination | 1 | H3 Currently on VBE | 3 | Annual Skills check off March 10-11, none other scheduled at this time | 0 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators, Scheduling, Document Specialists | 3 | None at this time | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | ED/DCS | 0 | referral portals- Growth, gather missing info- referral coordinator, non-admit reason in HCHB- DCS/ED, Schedule pt- DCS/ED, Make welcome calls- DCS/ED, Lead referral Huddles- Referral coordinator & Growth management | 3 | We currently have a scheduler on the weekends to assist DCS with schedules, we have RC/Doc specialists managing portals and keying referrals, | 2 | No | 2 | within the first 48 hrs referral received | 0 | management notifies PCC of high priority to schedule urgently | 1 | Yes | 1 | Doc specialists, RC | 0 | None | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
|  | 52 | A02 | PORTAGE MI (CC3146) | 5136 LOVERS LN STE 200A | PORTAGE | MI | (269) 459-3700 | (855) 384-1890 | N | (GMT - 05:00) EASTERN | [5 empty] | 367 | [7 empty] | Stephanie Watkins | Compassus Home Health - Portage MI | NA | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Infusion, Tube Feeding, Chest Tubes, Pleurx or Aspira drains, Chole Tubes, Nephrostomy Tubes, Tracheostomy, new to Self Catheterization, some wound care patients as they all may need same day care and education. | 1 | L1 No Plan for 2026 |  | We are actually just starting our Commure Pilot, Realignment of agency activities and trainings to standardize across the company in April and May. | 0 | M2 Some Coaching and Reinforcement |  | Growth, Scheduling, ED/DCS | 3 | Beacon Hospitals just went online with a new EMR and referral portal of Ensocare but they are not functioning efficiently in those platforms at this time impacting timeliness of referral updates, orders and even notification of discharges. They have no current format to write home care orders in their EMR and using a paper form and faxing but frequently forget, they are not routinely confirming assignment of referrals to agency in Ensocare and are not utilizing the system for updates or communication. Previously when they were Ascension facilities, we had access in the version of Cerner being used and could assist their Care Management and Discharge Planning teams in getting the necessary information to agency timely. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | Referral Coordinators also monitor referral portals and respond to new referrals on the weekends. ED/DCS assist with assigning patient's SOC visit in HCHB on weekends or afterhours, Scheduling assists Growth PTC with welcome and readiness calls. | 0 | As above we have no weekend scheduling so ED/DCS covering the Administrator on Call role assigns out needed SOC/ROC visits for weekend and Mondays. Will also sometimes work to track down referral information but does not have access to all needed portals or EMRs as growth does. The Admin on Call also responds to the referral emails if agency is unable to accept a referral for follow up by the referral coordinators/growth team. | 1 | Yes | 1 | When the discharge is confirmed and the referral is complete. | 0 | Growth notifies the team when received with anticipated DC date and location to confirm branch can safely accept and admit. | 0 | No | 2 | Referral Coordinators, occasionally growth will assist if they are expecting information on the weekends who then email th | 0 | None | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
|  | 52 | A03 | GRAND BLANC MI (CC3145) | 5445 ALI DR DEPT 500 | GRAND BLANC | MI | (800) 922-5220 | (844) 552-6193 | N | (GMT - 05:00) EASTERN | [5 empty] | 443 | [7 empty] | Cynthia Voelker | [55 empty] | Ronald Boggia
|  | 52 | A04 | WARREN MI (CC3144) | 28120 DEQUINDRE RD | WARREN | MI | (586) 913-0345 | (844) 526-5624 | P | (GMT - 05:00) EASTERN | [5 empty] | 557 |  | November 2026-February 2027 | [5 empty] | Cynthia Voelker | [55 empty] | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
|  | 52 | A06 | TAWAS CITY MI (CC3147) | 808 W CEDAR ST BLDG A | STANDISH | MI | (989) 310-4003 | (844) 445-7729 | N | (GMT - 05:00) EASTERN | [5 empty] | 294 | [7 empty] | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
|  | 53 | A07 | NEENAH WI (CC5824) | 816 W WINNECONNE AVE | NEENAH | WI | (920) 727-2000 | (844) 887-0047 | P | (GMT - 06:00) CENTRAL | [5 empty] | 595 | [7 empty] | Brenda Lefeber | Neenah Wi | Green Bay WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A08 | STURGEON BAY WI (CC5828) | 231 KEEL CT | STURGEON BAY | WI | (920) 695-3150 | (844) 887-0706 | N | (GMT - 06:00) CENTRAL | [5 empty] | 118 | [7 empty] | Marla Wills | AAH w/Compassus Sturgeon Bay | N/A | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | IV patient, pleurex, CHF/COPD | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | NA | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Referral Coordinators | 1 | Ed/DCS | 0 | NA | 0 | NA | 0 | No | 2 | After Intake | 0 | By Ed Direction | 0 | No | 2 | Admin on Call | 1 | N/A | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A09 | MARSHFIELD WI (CC5822) | 303 W UPHAM ST STE 208 | MARSHFIELD | WI | (715) 301-7260 | (844) 887-0042 | P | (GMT - 06:00) CENTRAL | [5 empty] | 375 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A10 | PLOVER WI (CC5825) | 1840 POST RD STE 5 | PLOVER | WI | (715) 301-7260 | (844) 887-0042 | 52Q7189001 | (GMT - 06:00) CENTRAL | [5 empty] | 243 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A11 | WAUSAU WI (CC5829) | 2600 STEWART AVE STE 160 | WAUSAU | WI | (715) 301-7260 | (844) 887-0042 | 52Q7189002 | (GMT - 06:00) CENTRAL | [5 empty] | 247 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A12 | RHINELANDER WI (CC5827) | 111 E DAVENPORT ST STE 101 | RHINELANDER | WI | (715) 301-7210 | (844) 887-0049 | P | (GMT - 06:00) CENTRAL | [5 empty] | 137 | [7 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A13 | ARBOR VITAE WI (CC5821) | 1571 HIGHWAY 51 N STE C | ARBOR VITAE | WI | (715) 301-7200 | (844) 885-3825 | 52Q7218001 | (GMT - 06:00) CENTRAL | [5 empty] | 112 | [7 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A14 | MILWAUKEE WI (CC5823) | 135 S 84TH ST STE 150 | MILWAUKEE | WI | (414) 455-9500 | (844) 887-8721 | P | (GMT - 06:00) CENTRAL | [5 empty] | 458 | [7 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A15 | RACINE WI (CC5826) | 13200 GLOBE DR STE 228 | MOUNT PLEASANT | WI | (262) 417-9393 | (844) 887-8721 | 52Q7187001 | (GMT - 06:00) CENTRAL | [5 empty] | 346 | [7 empty] | Melissa Steger | Racine | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H1 Well Staffed |  | Episodic, infusion, ortho, wound | 2 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | No | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | HHCC and CTC make welcome calls. PTC monitors referral portals and gather info as needed. | 1 | If schedulers are unable to contact patients, our PTC will sometimes assist with contacting. | 1 | No | 2 | Once the referral is 'pushed to scheduling' and is in our scheduler's workflow, the scheduler will make the readiness call. The growth team members make their welcome calls prior to this step. | 1 | ED and AME involvement as needed | 0 | Yes | 1 | RC team, AOC, and scheduler | 0 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 52 | A16 | BURNET TX (CC5233) | 309 INDUSTRIAL BLVD STE 2 | BURNET | TX | (512) 756-7511 | (512) 756-8046 | P | (GMT - 06:00) CENTRAL | [5 empty] | 140 |  | May-August | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 52 | A17 | AUSTIN TX (CC5235) | 9430 RESEARCH BLVD STE II310 | AUSTIN | TX | (512) 863-3842 | (844) 809-2238 | 67Q7154001 | (GMT - 06:00) CENTRAL | [5 empty] | 332 |  | May-August | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 52 | A18 | KYLE TX (CC5234) | 1300 DACY LN STE 170 | KYLE | TX | (512) 549-3490 | (888) 529-6396 | P | (GMT - 06:00) CENTRAL | [5 empty] | 173 |  | Feb-June 2026 | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 52 | A19 | WACO TX (CC5236) | 510 N VALLEY MILLS DR STE 504 | WACO | TX | (254) 523-6970 | (844) 308-5076 | P | (GMT - 06:00) CENTRAL | [5 empty] | 394 |  | April-July 2026 | [5 empty] | Wendi Pack | Ascension at Home Waco TX | NA | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Immediate skilled needs such as wound care, IV, or Ortho patients. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Once the chart has been green tagged. | 1 | Growth member lets the DCS and schedulers know | 0 | No | 2 | Intake checks the portals and the DCS on call monitors the emails/ schedules out the admissions. | 0 | NA | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 51 | A20 | ANDERSON IN (CC2311) | 600 CORPORATION DR STE 104 | PENDLETON | IN | (765) 203-2616 | (844) 724-7537 | P | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 210 |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A21 | KOKOMO IN (CC2315) | 2626 S WEBSTER RD STE B | KOKOMO | IN | (765) 252-1600 | (844) 724-7537 | 15Q7059001 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 327 |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A22 | INDIANAPOLIS IN (CC2314) | 8909 PURDUE RD STE 107 | INDIANAPOLIS | IN | (317) 829-2122 | (844) 724-7536 | P | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 319 | [7 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A24 | Bloomingham IN (Bedford) | 1324 K ST STE 150 | BLOOMINGTON | IN | (812) 578-3260 | (812) 276-1244 | 15Q7083004 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful | Bedford IN – smaller program with only 1 DCS and BOC in the office – DCS in partN Vernon IN – smaller program with only 1 DCS and BOC I the office – tend to have challenges when new technology is introducedicular is more resistive to change and they have been resistant in the past to changing anything with referral management | 89 | [7 empty] | Darla Bell | Evansville/Bloomington | Bloomington (managed by Darla)is actually branch of Idianapolis managed by Suchi | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A25 | NORTH VERNON IN (CC2316) | 2337 NICHOLAS CT STE C | SEYMOUR | IN | (812) 953-4120 | (812) 346-9889 | 15Q7083003 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 43 | [7 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A26 | EVANSVILLE IN (CC2313) | 7321 EAGLE CREST BLVD STE A | EVANSVILLE | IN | (812) 774-9760 | (812) 475-1739 | N | (GMT - 06:00) CENTRAL |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful |  | 298 |  | Jan-April 2026 | [5 empty] | Darla Bell | Evansville/Bloomington | None | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | We are in the CHAP window in Evansville 1st quarter. | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 52 | A27 | WICHITA KS (CC2504) | 301 N MAIN ST STE 950 | WICHITA | KS | (316) 268-8588 | (316) 264-1265 | N | (GMT - 06:00) CENTRAL | [5 empty] | 517 | [7 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 52 | A28 | PITTSBURG KS (CC2503) | 200 E CENTENNIAL DR STE 13 | PITTSBURG | KS | (620) 231-3088 | (844) 724-7530 | N | (GMT - 06:00) CENTRAL | [5 empty] | 111 | [7 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 52 | A29 | TULSA OK (CC4514) | 4612 S HARVARD AVE STE C | TULSA | OK | (918) 747-7901 | (844) 724-7540 | N | (GMT - 06:00) CENTRAL | [5 empty] | 300 |  | April-July 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | St John's Tulsa- unhappy with not being in network with patient's insurance | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 52 | A30 | BARTLESVILLE OK (CC4513) | 3061 SE WASHINGTON BLVD | BARTLESVILLE | OK | (918) 907-3010 | (844) 721-8184 | P | (GMT - 06:00) CENTRAL | [5 empty] | 146 |  | Feb-June 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
|  | 53 | A50 | ALBUQUERQUE NM (CC4004) | 7770 JEFFERSON ST NE STE 110 | ALBUQUERQUE | NM | (505) 881-0425 | (505) 349-3363 | P | (GMT - 07:00) MOUNTAIN | [5 empty] | 244 | [7 empty] | Raechel Dominguez | Region 53- New Mexico(Albuquerque and Santa Fe) | Albuquerque & Santa Fe | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV ABX, wound vac, ortho | 1 | L1 No Plan for 2026 |  | NA | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Welcome call as soon as referral is received, readiness call is done once referral comes to scheduling prior to assigning to clinician. | 1 | They are flagged and take priority. | 0 | No | 2 | ED | 1 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A51 | BILLINGS MT (CC3506) | 490 N 31ST ST STE 130B | BILLINGS | MT | (406) 652-8883 | (406) 652-8879 | N | (GMT - 07:00) MOUNTAIN STANDARD | [5 empty] | 205 | [7 empty] | Joanne Wirtjes | Billings MT | NA | Strongly Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | ortho pts, IV abx pts, cardiac pts | 1 | L1 No Plan for 2026 |  | New ED in 1/2026, new DCS in 3/26, rapid growth over last couple of months - plan on continuing growth, added 6 new clinicians in 2 months. | 2 | L1 Open to Change Adapt Quickly |  | None | 0 | VA - awaiting auth for SOC of pts and bundled and non-bundled for patients. | 1 | Growth | 0 | Referral Coordinators | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | EDDCS | 1 | Referral Coordinators | 1 | not sure whose task to build the hchb chart | 0 | NA | 0 | Yes | 1 | Ideally prior to chart getting pushed to scheduling | 0 | discussed in daily huddle/referral meeting and via TEAMS | 0 | No | 2 | AC Team | 0 | None | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A52 | BUTTE MT (CC3508) | 19 DISCOVERY DR | BUTTE | MT | (406) 494-0039 | (406) 494-0032 | N | (GMT - 07:00) MOUNTAIN STANDARD | [5 empty] | 79 |  | Jan-April 2026 | [5 empty] | Jacqueline Mathews | Compassus Home Health - Butte MT | None | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Wound care, fresh surgical patient discharging from the hospital and most patients coming out of the hospital. | 1 | L1 No Plan for 2026 |  | 2 new nurses will be training over the next couple of months so it would be best to roll out after they are trained. Also have new PTC who needs to feel more comfortable with her role. | 2 | M2 Some Coaching and Reinforcement |  | Growth, Referral Coordinators | 2 | We need improved referral source relationships so we can generate referrals needed | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | At times the ED will enter the ERR workflow and enter non-admit reason if it hasn't been done timely At time the ED will schedule patients if scheduler is not available. Make welcome calls is growth, readiness calls is scheduling | 2 | ED is also the DCS and BOC is also the scheduler | 2 | Yes | 1 | HCC is responsible for any bedsides, PTC is responsible for welcome call. BOC/scheduler is responsible for readiness calls once referral is complete and ready to be scheduled according to growth team. | 0 | Discussed in daily huddle, make a plan as to when patient can be admitted. | 0 | No | 2 | Administrator on call if needed | 1 | HHCC is new to having PTC, having a hard time relinquishing duties | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 50 | A53 | JACKSONVILLE FL (CC1801) | 7235 BENTLEY RD STE 236 | JACKSONVILLE | FL | (904) 861-2612 | (904) 503-9690 | N | (GMT - 05:00) EASTERN | [5 empty] | 360 |  | Jan-April 2026 | [5 empty] | Daisy | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 53 | A54 | SANTA FE NM (CC4005) | 1692B HOSPITAL DR STE 102 | SANTA FE | NM | (505) 629-4180 | (505) 814-1673 | P | (GMT - 07:00) MOUNTAIN | [5 empty] | 76 | [7 empty] | Raechel Dominguez | Region 53- New Mexico(Albuquerque and Santa Fe) | Albuquerque & Santa Fe | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV ABX, wound vac, ortho | 1 | L1 No Plan for 2026 |  | NA | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Welcome call as soon as referral is received, readiness call is done once referral comes to scheduling prior to assigning to clinician. | 1 | They are flagged and take priority. | 0 | No | 2 | ED | 1 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 50 | A55 | PENSACOLA FL (CC1802) | 1115 E GONZALES ST STE 1001 | PENSACOLA | FL | (850) 266-7235 | (850) 502-5417 | N | (GMT - 05:00) EASTERN | [5 empty] | 275 | [7 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 52 | A56 | SMITHVILLE TX (CC5238) | 150 SETTLEMENT DR STE F2 | BASTROP | TX | (512) 782-0382 | (512) 795-4371 | 67Q9048001 | (GMT - 06:00) CENTRAL | [5 empty] | 109 |  | Feb-June 2026 | [5 empty] | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources | Sheila Davis | Texas | Austin, Burnet, Kyle, Bastrop, and Waco Texas | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Any patient at high risk for rehospitalization | 2 | Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Watershed;Other;AIDA | AIDA | 6 | NA | 0 | Blue Cross Blue Shield and TriWest VA | 2 | H3 Currently on VBE |  | VBE implementation in Austin market | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | We maintain open and transparent relationships with our referral partners, using clear and consistent communication as a key tool to ensure our partnerships remain strong and in good standing. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Scheduling | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In the Texas market, our top priority is ensuring patients are seen in a timely manner. I marked the primary person responsible but if anyone on the team has capacity and approved access to complete a task, you are empowered to do so—allowing us to move quickly and deliver the care our patients need without delay. | 0 | Patient Care Transition (PCT): Responsible for making welcome calls on all community referrals to ensure early engagement and a smooth start to care. VBE Patient Care Transition (VBE PCT): Will provide weekend coverage beginning April 1st to support continuity of care and ensure timely patient onboarding | 2 | Yes | 1 | After patient is green tagged and in progress on PCC workflow. | 0 | Urgent and high-priority admissions are flagged immediately and escalated to the appropriate team members for rapid response. While a primary owner is identified, any team member with the access and authorization is empowered to act to prevent delays. Tasks are completed concurrently, with clinicians and scheduling aligning to ensure patients are seen as quickly as possible. | 0 | No | 2 | Weekend referrals are primarily managed by the Weekend AC and the on-call DCS. Additional support is provided as needed by the ED, CLM and AME to ensure timely processing and patient access. | 0 | A successful rollout depends on clearly explaining the “why,” defining roles and responsibilities, and establishing a workflow that sets clear expectations for the team.
|  | 53 | A57 | GREEN BAY WI (CC5834) | 480 PILGRIM WAY STE 1250 | ASHWAUBENON | WI | (920) 282-9829 | (715) 203-0627 | 52Q7009002 | (GMT - 06:00) CENTRAL | [5 empty] | 88 | [7 empty] | Brenda Lefeber | Green Bay WI | Neenah WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 50 | A58 | PANAMA CITY FL (CC1803) | 2211 S HIGHWAY 77 STE 203A | LYNN HAVEN | FL | (850) 250-1366 | (850) 558-4974 | N | (GMT - 06:00) CENTRAL | [5 empty] | 88 |  | October 2026 - January 2027 | [5 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 53 | A59 | SHEBOYGAN WI (CC5833) | 2124 KOHLER MEMORIAL DR STE 200 | SHEBOYGAN | WI | (920) 547-4126 | (877) 376-3117 | 52Q7187002 | (GMT - 06:00) CENTRAL | [5 empty] | 111 | [7 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 53 | A64 | CHIPPEWA FALLS WI (CC5835) | 134 W COLUMBIA ST STE 2 | CHIPPEWA FALLS | WI | (715) 861-8353 | (715) 203-0273 | 52Q7189003 | (GMT - 06:00) CENTRAL | [5 empty] | 130 | [7 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
|  | 51 | A67 | LAFAYETTE IN (CC2319) | 703 N 36TH ST | LAFAYETTE | IN | (765) 294-2053 | (765) 294-2186 | 15Q7083002 | (GMT - 05:00) EASTERN |  |  |  | IN – needs 2 for 7 programs – Suchi Modi, Indianapolis/Lafayette/N Vernon ED and Jennifer Baxter, Evansville PCC – we thought some PCC perspective may be insightful and impactful | Lafayette IN – close to 100 census with only 1 BOC and DCS in office – BOC specifically had challenges with technology so may need a bit more hand holding | 84 | [7 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 52 | A68 | ALPENA MI (CC3153) | 109 N SECOND AVE STE 202 | ALPENA | MI | (989) 272-8894 | (989) 607-0679 | PENDING | (GMT - 05:00) EASTERN | [5 empty] | 2 | [7 empty] | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
|  | 51 | A74 | CENTERVILLE TN (CC5111) | 135 E SWAN ST | CENTERVILLE | TN | (931) 729-4500 | (931) 729-9000 | N | (GMT - 06:00) CENTRAL |  |  |  | TN – 2 programs – Angie Corman, Nashville ED | Centerville TN – due to size and overall challenge with technology and change – very rural market | 55 | [7 empty] | Brandi Tayloe-Jones | Centerville TN | NA | Strongly Agree |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | Clinical needs and acuity such as IV, wounds, etc. | 1 | M2 2026 GoLive |  | VBE launch in June/July | 1 | M2 Some Coaching and Reinforcement |  | Field Clincians | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | DCS does quite a bit with referral management and no admits | 1 | BOC also performs scheduling functions due to size of program. | 1 | Yes | 1 | After the referral is sent to scheduling. | 1 | The DCS is very active and pushes the referrals through as needed. | 1 | Yes | 1 | There is a regional a scheduling and growth rotation. | 0 | The size of the program can limit functions at times. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 51 | A75 | NASHVILLE TN (CC5112) | 402 BNA DR STE 320 | NASHVILLE | TN | (615) 367-1656 | (615) 367-1659 | N | (GMT - 06:00) CENTRAL |  |  |  | TN – 2 programs – Angie Corman, Nashville ED |  | 176 | [7 empty] | Angela Corman | Nashville TN | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | IV antibiotic, Wound Vac, Recent Joint Replacement, LVAD, Cardiac Drip | 1 | M2 2026 GoLive |  | VBE to go live 5/28 currently hiring for increase in referrals | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | Referral Huddles are lead by RC, Scheduler and or ED. Welcome calls are being made by growth, then scheduler/clinicians | 2 | Growth and schedulers work weekend rotations to cover region, ED currently doing large portion of DCS leadership such as payroll etc, all staff under ED. 2 new DCS's have been hired and training all DCS's to take over those responsibilities for clinical team leadership. BOC is cross trained to manage scheduler workflow, Scheduler cross trained to complete some BOC responsibilities. | 1 | Yes | 1 | Growth contacts patient to verify demographics and makes initial welcome call. Clinicians/Scheduler call for readiness. | 1 | Growth informs team of priority admission and intake/scheduler/ED ensure process is completed smoothly | 0 | Yes | 1 | Growth from the region and weekend RCs | 0 | None | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 54 | A76 | GREENVILLE SC (CC4909) | 1836 W GEORGIA RD | SIMPSONVILLE | SC | (864) 233-5300 | (864) 233-4873 | N | (GMT - 05:00) EASTERN | [5 empty] | 371 | [7 empty] | Regina Ervin | Bon Secours Home Care by Compassus - Greenville, SC | None | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H2 Managing but it's tight |  | A patient with high acuity discharging same day(Pleurex patients, IV abx, tube feeds, TPN, etc.) | 1 | H3 Currently on VBE |  | None at this time | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | We have a large Total Ortho Program that we are committed to. We work with this group closely and process referrals quicky to see pateint timely. Some of these patients go home same day of surgery and we try to see patient next day. We are on the hospital committee and have built a strong relationship with this program. We would want to continue to function well for this group. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | RC's complete referral portals and respond to new referrals on the weekend. Readiness calls can be done by growth or scheduling | 1 | RC's complete growth responsibilities on the weekend. There are times DCSs schedules visits on the weekend. | 1 | Yes | 1 | Typically, when growth completes demos | 1 | Discussed during huddle with growth and scheduling to try and get patient seen timely. DCS and EC is on call to discuss barriers. | 0 | No | 2 | RCs & DCSs | 1 | Communication is strong between our team (intake, growth, schedulers, leaders) and we would not want to lose that. | Kimberly Manson | Greenville SC | Greenville SC only | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | Higher acuity patients that would better seen within 24-hour timeframe - his include new oxygen, IV antibiotics, new tube feeds, and TPN patients. | 1 | Intake (NaviHealth/Curaspan);Ensocare;Other;Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Watershed | Referrals are not received directly via all scripts, AIDA, Aidin, or Watershed. | 3 | No - unless faxes will no longer create an ERR within HCHB. There are still referrals that are sent to our branch by fax. | 0 | Humana is one that I am aware of, not sure if there are others. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Referral Coordinators | 1 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCs | 0 | Growth is primary for portals during non-holiday and business hours, Referral Coordinators are responsible for these portals during holiday and non-business hours. Growth typically makes welcome/readiness calls. If they are unable to reach a patient during scheduling, the scheduling team will contact patient. | 1 | None | 0 | Yes | 1 | When Growth has accepted the referral and is calling to verify physician and demographics. This is approximately 24-48 hours prior to admission. | 1 | They are reviewed by Growth and discussed with DCS/ED/scheduling to coordinate care and ensure that the patient is seen within a timely manner and any barriers are discussed as a team. This also happens during huddle calls. | 0 | Yes | 1 | The Referral Coordinators manage referrals and coordinate with the weekend DCS on declining or accepting. They also work with the Sunday scheduler to address any additional needs. | 0 | It would be great to continue to communicate and coordinate care across multiple teams, but ensuring that there is less patient communication via email/Teams would be GREAT.
|  | 54 | A77 | PADUCAH KY (CC2602) | 225 MEDICAL CENTER DR STE 203 | PADUCAH | KY | (270) 415-3600 | (270) 936-8620 | P | (GMT - 06:00) CENTRAL | [5 empty] | 336 | [7 empty] | Renee Wurth | Mercy Health Homecare by Compassus - Paducah, KY | N/A - (submitted for Metropolis IL branch but have not yet received approval) | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | High Priority patients are those that are discharging from acute hospitals, as well as, those who had outpatient orthopedic surgery the day before. We also have many wound vacs/infusion patients who have specific times/needs that are quick turnarounds from referral. | 1 | L1 No Plan for 2026 | 1 | We have applied to have a branch in Metropolis, IL but have not received approval from CMS at this point. Otherwise no major known events. | 1 | M2 Some Coaching and Reinforcement | 2 | Field Staff | 0 | Our orthopedic physicians send referrals early and we have to follow up regularly with them to ensure surgeries remain scheduled and that we are out to see the patient the next day. Vanderbilt and Barnes Jewish often send us requests and it takes days of follow up to get confirmation of patient choosing us (occasionally even after patient is already discharged). We hold spots on our scheduling grid for these patients, requiring a lot of attention and follow up. Multiple local physicians' offices send referrals at the very end of the day making it difficult to process them timely for the referral coordinators. | 3 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Referral Coordinators cover portals on weekends and attend to faxed referrals. RCs and ED/DCS assist with gathering missing referral information as needed. Growth makes welcome calls and Scheduling makes readiness call. Scheduler assists growth in referral huddles with current avialability and episodic percentage of referrals admitted for month to date. | 1 | Referral Coordinators cover weekends for referrals. Administrator on Call (DCS) covers scheduling from Friday at 5pm to Monday at 8 am. | 1 | Yes | 1 | Welcome call is the day the referral is accepted. Readiness call occurs the day before admission (Friday before for Monday admission). | 0 | During office hours, communication comes into DCS/ED and is coordinated by the DCS that is on call for the week. Administrator on call (DCS) coordinates the process to get the patient's chart to the clinician if it is after hours or on the weekends. | 0 | No | 2 | Referral Coordinators manage the referrals and Administrator On Call is the accept/decline decision maker. | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout. | Farrah Gay | Paducah KY | Paducah, KY and we have applied for Metropolis, IL to be a branch. | Neither Agree or Disagee |  | L1 Well Staffed |  | H3 We're stretched thin | 3 | M2 Managing but it's tight |  | Complex, unstable or acute needs requiring urgent intervention to prevent hospitalization, nursing home placement or further decline. | 1 | Epic Carelink;Aidin;Other;Ensocare;Referral Management (All scripts);AIDA;Intake (NaviHealth/Curaspan);Watershed | #5-8 are not | 4 | Not that I am aware of. | 0 | VA - required auth at intake before we can start care. Trisha Curtis is our insurance manager and looking into this if you would like to circle back with her for more information. | 1 | L1 No Plan for 2026 |  | We've requested to make the Metropolis, IL location a branch. The application was submitted in 2024. | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Referral sources seem to understand the universal staffing capacity issue among all healthcare, so they have not verbalized as much frustration recently as they have in the past. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | Make readiness call - completed by scheduling Lead referral huddles - completed by both growth and branch | 0 | RC/intake covers weekend referral management. Administrator on call covers scheduling and accepting/decline. | 0 | Yes | 1 | Welcome call - day the referral is accepted by growth/patient PCC readiness - day prior to start of care except for weekends. | 1 | Notification to administrator on call who then communicated and schedules | 1 | No | 2 | RC/intake and Administrator on call | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout.
|  | 50 | A78 | TAMPA FL (CC1804) | 137 S PEBBLE BEACH BLVD STE 203 | SUN CITY CENTER | FL | (813) 443-5566 | (813) 374-6997 | N | (GMT - 05:00) EASTERN | [5 empty] | 90 | [7 empty] | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 50 | A79 | ST PETERSBURG FL (CC1805) | 11001 ROOSEVELT BLVD N STE 100 | St. Petersburg | FL | (727) 577-7990 | (727) 576-6138 | N | (GMT - 05:00) EASTERN | [5 empty] | 95 | [7 empty] | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
|  | 54 | A80 | RICHMOND VA (CC5509) | 2603 NINE MILE RD STE 200 | RICHMOND | VA | (804) 627-5200 | (804) 627-5208 | N | (GMT - 05:00) EASTERN | [5 empty] | 340 | [7 empty] | Allison Bohn | Bon Securs Home Care by Compassus, Richmond VA | NA | Disagree |  | H3 We're stretched thin |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV, LVAD, some surgeries depending on MD, certain wound care | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | Growth | 1 | BSMH Partner creates the most challenges. Expectations to accept all patients are high but in return we are not consistently given first right of refusal if patient has no preference. | 1 | Growth | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Depending on where the referral is coming from, Growth is also responsible for gathering missing referral documents and patient information | 0 | None | 0 | Yes | 1 | Scheduling | 0 | Communication during huddle, in emails and on scheduling grid | 0 | Yes | 1 | Referral Coordinator | 0 | None | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
|  | 54 | A81 | SUFFOLK VA (CC5513) | 7007 HARBOUR VIEW BLVD STE 114 | SUFFOLK | VA | (757) 889-4663 | (757) 393-1348 | P | (GMT - 05:00) EASTERN | [5 empty] | 273 | [7 empty] | Erica Dejesus | Bon Secours with Compassus - Suffolk | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
|  | 54 | A83 | VIRGINIA BEACH VA (CC5515) | 184 BUSINESS PARK DR STE 100 | VIRGINIA BEACH | VA | (757) 889-4663 | (757) 393-1348 | P | (GMT - 05:00) EASTERN | [5 empty] | 99 | [7 empty] | Erica DeJesus | Virginia Beach VA | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
|  | 54 | A84 | LORAIN OH (CC4415) | 3500 KOLBE RD | LORAIN | OH | (440) 960-4000 | (440) 960-3359 | N | (GMT - 05:00) EASTERN | [5 empty] | 182 | [7 empty] | Andrea Faurot | Lorain OH | N/A | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV, Wound, Pleurex or chest tubes, Tube feed, TPN Total Joint patients, nephrostomy, trach patients, New O2, CABG | 1 | L1 No Plan for 2026 |  | CHAP survey pending immediately | 1 | M2 Some Coaching and Reinforcement |  | Unsure | 0 | Yes the Lorain BSMH market needs lots of education on why and they want a smoother process. They oppose change often, but sometimes will come along as long as there is good communication and collaboration. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Growth | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Growth and intake often share responsibilities or cover for each other | 1 | RN Coordinator is also in on call rotation and assists schedulers back up as well as Home Health Admin Assistant | 1 | Yes | 1 | Once sent to scheduling | 0 | escalated to DCS or ED | 0 | No | 2 | Intake & Growth | 0 | Clear expectations of responsibility and throughput diagram. So expectations are clear. Our schedulers are part of a bargaining unit, so any changes that could impact them—such as modifications to their job descriptions or working hours—would need to be reviewed and vetted through the bargaining unit. With negotiations starting next week, it would be helpful to identify any potential changes proactively so we can address them in advance. This will ensure we remain aligned with the bargaining process and avoid any delays. If there is someone else who should be looped in or involved in these discussions, please feel free to connect them. Brian Jackson and Yashica Smith is who we use to review any changes that may impact our bargaining team members we get them included early and often to discuss any potential changes. I have looped in Melissa just for transparency. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 54 | A85 | LIMA OH (CC4418) | 959 W NORTH ST | LIMA | OH | (419) 226-9062 | (419) 226-9281 | N | (GMT - 05:00) EASTERN | [5 empty] | 209 | [7 empty] | Cheryl Bechtel | Mercy Health Homecare by Compassus Lima Ohio 45805 | No | Strongly Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Skilled need IV, Wounds, Drains | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | Insurance Authorization | 1 | No | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Other | 1 | ED/DCS | 0 | n the Lima Market the scheduler is the first person to call the patient to set up a home visit. Would be nice to have the growth team verify information prior to the scheduler. This would save time as the scheduler then has to reach back to the growth team to obtain the information | 0 | DCS will assist with scheduling if scheduler is on PTO Training Clinical RN coordinator to assist with scheduling | 1 | Yes | 1 | When the referral is in the workflow of the scheduler. | 0 | Reviewed by the DCS/ED prior to scheduling if it is known at the time of referral is sent. Growth team doesn't communicate with the intake team sometimes causes problems with priority of the patient needs to be schedule appropriately. | 0 | No | 2 | Growth/Intake | 0 | To improve efficiency and reduce delays in the Start of Care (SOC) process, several opportunities for improvement have been identified within the intake and referral workflow in the Lima market. 1. Growth Team Education on Home Health Qualification and Skilled Need The new Growth Team would benefit from additional and ongoing education regarding: •Qualification criteria for home health services •Identification of skilled need for the patient Currently, referrals are accepted before the clinical skill level and priority of the patient’s needs are fully identified. This can create delays when the patient requires a higher level of clinical prioritization than initially recognized. 2. Insurance Authorization and Verification of Benefits Process Another opportunity for improvement is within the insurance verification and authorization workflow. Currently, delays occur when: •Verification of Benefits is completed, but •The scheduler later needs to re-request insurance authorization, which slows the referral and SOC process. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 54 | A86 | TIFFIN OH (CC4419) | 45 ST LAWRENCE DR | TIFFIN | OH | (419) 455-8180 | (567) 316-2977 | N | (GMT - 05:00) EASTERN | [5 empty] | 73 | [7 empty] | Brandy Fredritz | Mercy Home Care by Compassus Tiffin Ohio | N/A | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day needs, daily needs, IV care, and wound care. | 2 | L1 No Plan for 2026 |  | Hiring full therapy team (versus contracted) in 2026 and adding more nursing staff. Hiring increases started in February 2026 until all positions are filled. | 1 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Schedulers | 2 | When utilizing CarePort, the larger hospitals like OSU and Cleveland Clinic send out "blast referrals" and are poor/slow to respond. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | NA | 0 | Our BOC covers scheduling when our PSC is off. DCS/ED cover scheduling on the weekends. | 1 | Yes | 1 | Varies depending on how quickly the referral is worked and when the SOC is needed. We typically are reactive to our referral process and plot people quickly due to low staffing. Typically, the welcome/readiness call is completed the day before. | 1 | Communication between all Growth/RC/ED/DCS in TEAMS/Email. | 0 | No | 2 | RC/Growth with DCS/ED input | 0 | n/a | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 54 | A87 | YOUNGSTOWN OH (CC4412) | 979 TIBBETTS WICK RD STE A | GIRARD | OH | (330) 480-3776 | (330) 480-4584 | N | (GMT - 05:00) EASTERN | [5 empty] | 373 | [7 empty] | Melanie Boyts | Youngstown OH | NA | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | CABG (open heart), Mitral Valve Replace, Carotid endarterectomry, fem-pop bypass, Infusion patients. orthopedic patients needing same day or next day visit, Enteral/Tub Feed, Trach, wounds/wound vacs, pleurx drains/drains | 1 | L1 No Plan for 2026 |  | Focusing on recruitment and retention. Recruitment in this market has been slow. Starting to make some movement in 2026 but it's really to maintain current operations and not necessarily to support growth. PT/OT/ST extremely difficult to recruit for. Other competitor agencies in area who have established relationships/presence in our JV BSMH hospitals. | 1 | L1 Open to Change Adapt Quickly |  | Growth, Referral Coordinators | 2 | The referral source relationships within the JV BSMH hospitals present operational challenges, particularly within the case management team. A notable issue is the development of relationships with competitor home health agencies within our hospitals, which results in these competitors being prioritized with favorable payors. These dynamics highlight a broader struggle in this market hospital to embrace the joint venture (JV) as a true partnership. From the inception of the JV, the relationships have been challenged, largely tied to efforts in managing payor mix effectively. Several case managers and physicians continue to demonstrate a preference for competitor home health agencies, which undermines the intended collaboration of the JV. While the Area Market Executive in this market has worked diligently to improve relationships and enhance communication around partnerships, significant barriers remain despite these efforts. An additional challenge involves the pressure to accept patients that are often declined by other home health agencies. When explanations are provided about why we cannot accept these patients, resistance frequently arises, escalating the matter to the JV director on the BSMH side. This creates unnecessary friction, adding to the operational complexity. Lastly, the communication dynamic often positions our team as separate from the partnership. This creates the perception that the partnership is one-sided, rather than a true collaborative effort. Addressing these challenges is critical to fostering a unified partnership, optimizing payor relationships, and removing operational inefficiencies. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Confusion from operations team on who is doing what when a referral comes together. Several roles involved in one patient referral. | 0 | scheduling works weekend here. RC's in this market covered growth for a very long time, i think there is still confusion from the operations team on who does what part of a referral when requesting additional information | 1 | Yes | 1 | the scheduler completes this the day before. Done around 330pm when we consider our scheduling grid final. | 0 | Growth team CTC, HHCC and PTC communicate and move patients around on the scheduling grid accordingly. if there is a request to add a patient on outside of what our capacity is DCS and/or ED approve that. | 1 | Yes | 1 | RC & Growth | 0 | The implementation of the new scheduling grid on 12/8/25 has shown promise in aiding payor mix management. However, discharge planning continues to present significant challenges, particularly within the BSMH hospitals. Many patients appear on the scheduling grid for specific discharge dates, but frequently either do not go home as planned or are discharged on unanticipated dates. You expect this if they are discharges planned far in the future but the concern here is you review the patients on the 230pm call set up schedules after 330pm and come in following morning and patient didn't dc. We expect things change and this happens, but it is a more frequent occurrence here. It has been noted that BSMH referrals are sometimes assigned discharge dates that are not definitive, simply to facilitate their acceptance. This creates difficulties in accurately following patients day to day and predicting their actual discharge dates. As a result, we often face situations where patients scheduled for admission do not go home as anticipated. This creates complications in confirming schedules, as clinicians frequently find that patients they planned to admit are not yet discharged. To manage these issues, we attempt to pull other patients forward to fill the vacant spots, though these adjustments often occur too late to avoid disruption. Our clinicians, who operate on a pay-per-visit model, need to begin their day by 8:00 a.m. to maintain productivity and minimize financial impact. To address these ongoing discrepancies, we continue to hold two staffing huddles daily, one in the morning and one in the afternoon. These huddles are essential due to the high rate of unexpected changes in discharge timing and the need for late adjustments. I see an opportunity for improvement in this process by ensuring that patients are added to the schedule once their discharge is confirmed. Concerns with having the necessary attachments and documentation readily available on patient charts. For example, the AVS (After Visit Summary) or DC summaries are frequently requested by SOC clinicians. The DCS often has to pull supporting documentation, such as Face-to-Face supporting documentation, during the coding review process. Addressing these documentation and coordination challenges will be critical to improving the overall efficiency of the referral to scheduling workflow. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
|  | 51 | A89 | COLUMBIA MO (CC3437) | 3310 BLUFF CREEK DR STE 106 | COLUMBIA | MO | (573) 370-7577 | (111) 111-1111 | PENDING | (GMT - 06:00) CENTRAL |  |  |  | MO – 1 program – Lisa Walder, Columbia DCS |  | 17 | [7 empty] | Angie Walker | Compassus Columbia MO | NA | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Clinically complex, Increased risk for readmission, timed admission (ex. PICC w/ ABX). | 1 | L1 No Plan for 2026 |  | Leadership changes/staffing changes-current and ongoing | 1 | L1 Open to Change Adapt Quickly |  | ED/DCS | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Interim ED, DCS, RC and HHCC all help monitor referral portal. | 1 | Our BOC is also our scheduler. | 1 | No | 2 | After the referral is considered complete, and before it is scheduled to a clinician. | 0 | That referral gets prioritized and scheduled ahead of a "routine" referral. | 0 | No | 2 | Responsibility shared between our HHCC and the admin on call. | 1 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | None | 0 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
|  | 54 | A93 | COLUMBUS OH (CC4424) | 6805 PERIMETER DR FL 1 | DUBLIN | OH | (380) 219-5373 | (380) 219-5374 | P | (GMT - 05:00) EASTERN | [5 empty] | 1468 | [7 empty] | Tabitha Campbell | OHH Columbus OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients new to tube feeds | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Non admits are completed by clinicians-CC- and ED | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 54 | A94 | MANSFIELD OH (CC4426) | 50 INDUSTRIAL DR | LEXINGTON | OH | (419) 484-4688 | (419) 484-4689 | 36Q7615002 | (GMT - 05:00) EASTERN | [5 empty] | 312 | [7 empty] | Tabitha Campbell | Mansfield OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients who have wounds/depending on the severity | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | I do not know who is responsible for entering the Review External Referral Request- possibly intake? | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 54 | A95 | MARION OH (CC4425) | 1713 MARION MOUNT GILEAD RD STE 107 | MARION | OH | (740) 367-3085 | (740) 367-3087 | 36Q7615003 | (GMT - 05:00) EASTERN | [5 empty] | 282 | [7 empty] | Tabitha Campbell | Marion OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients with new ostomy or newer ostomies | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | None | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 54 | A96 | ATHENS OH (CC4427) | 444 W UNION ST STE C | ATHENS | OH | (740) 367-3076 | (740) 367-3093 | P | (GMT - 05:00) EASTERN | [5 empty] | 166 | [7 empty] | Jennifer Frost-Coon | Ohio Health at Home with Compassus - Athens | None | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV patients | 1 | L1 No Plan for 2026 |  | Not that I am aware of at the moment. | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | Yes, we have a few providers who can become challenging with signing the POC/orders/following after they agree to follow. I manage those providers in the moment with education and feedback. | 1 | ED/DCS | 1 | Growth | 0 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | There are three of us in back office that monitor the referral chats and weigh in- it is mostly me that responds. | 1 | With our office being more compact the Scheduler/BOC are the same person in my office and she can schedule patients, she is not clinical. I have a Clinical Coordinator who supports staff and completes and covers for the Scheduler/BOC when she is on PTO. I am the only one in our office who is in the rotation for weekends. | 2 | No | 2 | Specifically I am not so sure- however the welcome call is documented at bedside as well as before the referral is pushed often times. | 1 | Over communication between the HCC and PCC along with back office and ensuring good communication between the patient and the office so that the patient knows the plan too | 0 | No | 2 | The ED and or who is covering in the weekend rotation. A warm hand off is given on Friday going into the weekend with insight into capacity for the weekend and beginning of each week. | 1 | The weekends are the roughest with Intake and communication. Ensure there is good support over a weekend would be my two cents. | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
|  | 62 | B01 | Napa Valley CA |  | NAPA | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 150 |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B02 | Humbolt County CA |  | Humbolt | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 129 | [7 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B03 | Sonoma County CA |  | SANTA ROSA | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 141 |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B04 | LA County North CA |  | Burbank | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 500 | [7 empty] | Luiza Chuang | LA North | LA North | Strongly Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | status post hospitalization, IV, TKR, | 1 | H3 Currently on VBE | 3 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Scheduling | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | None | 0 | BOC covers for scheduling if needed | 0 | Yes | 1 | once referral is on schedulers workflow if not if its on MS list | 0 | within 24 hours | 0 | YEs | 1 | Same Team | 0 | we have daily stand downs and we dont see many intake reps joining and we would love to have their presence | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B05 | LA County South CA |  | Torrence | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 364 | [7 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B06 | OC Anaheim CA |  | ANAHEIM | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 600 | [7 empty] | Kathleen Hatfield | PAH with Compassus, OC Anaheim CA | PAH Orange County Mission Viejo | Neither Agree or Disagee |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Tracheostomy care, Infusion, PleurX drain, wound vac, new enteral feedings | 1 | H3 Currently on VBE | 3 | Training of and go live of AI assisted documentation with Nestmed end of March, beginning of April. | 1 | L1 Open to Change Adapt Quickly | 1 | Growth | 1 | we receive incomplete referrals from our community sources outside of Providence (UCI, Memorial Care, Optum, etc.) | 4 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Ed/DCS | 0 | our access teams share responsibility for referrals they receive the access teams are Intake, VBE, and Community Liaisons (growth). | 1 | we do have a weekend team that is supervised by an RN who also works in the field during the week. She and a team of schedulers work normal 8-5 hours on the weekend to perform scheduling, and all 3 OC agencies are supported by this team. The intake and VBE teams also have weekend coverage | 1 | Yes | 1 | the welcome calls are done by our scheduling team. | 0 | DCS/ED are involved and the referral is escalated and pushed. OC agencies also have PM RN to support staffing of same day SOC | 0 | No | 2 | The intake and VBE teams manage the referral, the schedulers who work the weekends are hired specifically for weekends | 1 | we have a centralized intake team Director is Tameia Westby. She is your best contact for this roll out in CA. | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B07 | OC Mission Viejo CA |  | MISSION VIEJO | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 421 | [7 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | Parent agency for B07 is B06 Orange County Anaheim, California | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B08 | High Dester CA |  | HESPERIA | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 213 |  | April-June 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus High Dester CA | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B09 | OC South CA |  | Irvine | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 604 | [7 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | NA | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 62 | B10 | Inland Empire CA |  | Pomona | CA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 340 |  | October-December 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus Inland Empire Pomona california | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
|  | 61 | B21 | Snohomish County WA |  | EVERETT | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 899 |  | April-June 2026 | [5 empty] | Mirna Musun | Providence at Home with Compassus HH, Snohomish | NA | Disagree |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | Prescheduled joints, recent DC from hospital, patients from our VBE | 2 | H3 Currently on VBE |  | VBE implementation actively occurring in Region 61- not all have VBE standing up. | 1 | H3 Hesitation and Significant Effort |  | Scheduling;ED/DCS;Referral Coordinators;Growth;Field staff- due to union environment | 4 | yes our Prov facilities , OPTUM and many other providers do not provide verbal orders, or want us to work in EPIC like we used to - | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | VBE supports some of the beside readiness calls and obtaining missing pt information for referrals | 1 | Sometimes our triage nurses may need to assign visits on the weekends | 1 | No | 2 | It happens at program level | 1 | At the program level | 1 | Yes | 1 | Intake | 0 | Schedulders at the location are represented at 2 of my 2 locations | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B22 | Olympia WA |  | LACEY | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 603 |  | October-December 2026 | [5 empty] | Jill Barnhart | Olympia WA | NA | Disagree |  | H3 We're stretched thin |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | Complex wound care, wound vac, PICC line needs, acute ortho | 1 | H3 Currently on VBE |  | CHAP survey planned for Q4, probable location transition to a new space in Q4 | 1 | M2 Some Coaching and Reinforcement |  | Scheduling, ED/DCS | 2 | We receive most of our referrals from our Providence HUB partners with the VBE. We just hired an account manager for the community. We struggle with accurately communicating availability to take on new patients and the referrals to match with multiple referral sources and no one who specifically manages the referrals into the agency with a warm hand off. | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Our centralized Access team manages referrals into the branch and into the scheduler workflow. They don't really fully have a connection with our agency, but work several branches at once and are primarily data entry employees. We don't have a referral coordinator per say, and our growth team is primarily our Providence hospital HUB team. There are a LOT of "pitchers" managing the flow of referrals into the system, but not a lot of attention is placed with managing viable referrals and ensuring important information is gathered timely and truly ushering patients into the agency for care. | 1 | We have 2 triage nurses who assist with adherence to TIC times, particularly assisting with new PSOC dates and transitioning ROCs back on service. | 1 | Yes | 1 | Once the patient is in the PSC workflow | 0 | Usually a TEAMS message comes from the HUB or access team if a patient has a special need, especially wound vacs, PICC line dressing changes or lab draws, ortho patients.. | 0 | No | 2 | Access team in collaboration with the Admin on Call if needed. | 1 | We would really like a referral coordinator who has oversight into the referrals coming in to the agency and helping to manage availability for new business, payor mix, and TIC times. Right now, we have referrals coming in from multiple sources with no regard to what the agency can really admit timely. Our availability is communicated in an antiquated shared spreadsheet that is challenging to read and is ever-changing depending on staffing challenges. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B26 | Seattle WA |  | TUKWILA | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 675 |  | October 2026 - January 2027 | [5 empty] | Jonelle McGee | Seattle, WA/ King County | NA | Agree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Someone who has wound care is considered urgent, as well as other nursing needs. | 1 | H3 Currently on VBE |  | I am a fairly new ED, but we are focused on really turning things around with metrics, EBITDA, census, productivity, STAR ratings, VBP, etc. We are currently recruiting/hiring for growth and there is major education initiatives and rebuilding going on in our ministry. | 0 | M2 Some Coaching and Reinforcement |  | ED/DCSs | 1 | We do accept charity care and also accept Medicaid and payor sources that make it harder to obtain EBITDA targets. As we are hiring for growth, we need to form community relationships with hospitals outside of our VBEs that DC patients to other areas of our territory that our VBEs do not DC patients to. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | The responsible roles listed in #11 above vary. If the referrals are incomplete and make it to scheduling, then more manpower is needed in the ministry to try and complete the referrals. Ideally, this would all happen at intake prior to it entering the scheduling workflow. | 1 | We still need to hire a weekend scheduler. Right now our weekday schedulers are taking turns covering weekends, which creates problems, as they need to take a comp day off, and we are currently short on schedulers. Our DCS team is supposed to be working hand-in-hand with schedulers to ensure clinician productivity is maximized and clinicians have maximum SOC visits assigned as possible. | 1 | No | 2 | When attempting to schedule the SOC visit | 0 | The DCS and/or ED should be notified | 0 | Yes | 1 | schedulers and administrator on call | 1 | We are eager to incorporate anything that could help with the conversion of referral to SOC | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B27 | Spokane WA |  | SPOKANE | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 499 | [7 empty] | Derek Salminen | PAH Spokane WA | N/a | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Those with high needs. New ostomies, wound vacs, IV ABX, ortho patients. | 1 | H3 Currently on VBE |  | For Spokane we are going to be going through a CHAPs Survey. We are looking to expand and are only limited by field clinicians at this time. | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | For all of our referral sources we have to educate that Spokane is no longer a non-profit entity and we have to look at insurance types before accepting. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | N/A | 0 | None | 0 | Yes | 1 | ? | 1 | Operations is notified by the community outreach group. When the referral comes in ED or DCS ensure that the referral is pushed timely through intake and insurance. | 1 | Yes | 1 | We have one dedicated scheduler who works the weekends | 1 | N/A | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B28 | Walla Walla WA |  | WALLA WALLA | WA |  |  |  | (GMT - 08:00) PACIFIC | [5 empty] | 114 |  | July-September 2026 | [5 empty] | Jessica Dougherty-Burt | Walla Walla, Washington | NA | Agree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV, Wound Vac, Wound, Ortho's | 1 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Our agency would benefit from hospital liason/referral coordinator so that we have complete orders for care at SOC visit. | 0 | We struggle to get POC approval from providers after admit visit. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Referral Coordinators | 1 | ED/DCS | 0 | Referral coordinators are responsible to monitor referral portals/respond to new referrals, but ED monitors pending referral report and clarifies with intake when referrals are not completed timely to see what is causing the delay. | 0 | On the weekends Spokane's scheduler supports Walla Walla. | 0 | Yes | 1 | Referral Coordinator/Intake assessment rep | 1 | ED/DCS pushing to have the referral completed and pushed through. | 1 | No | 2 | Intake | 0 | Patients are pushed to scheduling and intake has not obtained specific orders for the patient care needed. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
|  | 61 | B29 | Anchorage AK |  | Anchorage | AK |  |  |  | (GMT - 09:00) ALASKA STANDARD | [5 empty] | 187 |  | October -December 20206 | [5 empty] | Stephanie Cabiness | Providence at Home with Compassus Anchorage AK | None | Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | A patient that has discharged from the hospital with wounds or an extended stay. | 1 | H3 Currently on VBE | 3 | Not that I am aware of | 0 | M2 Some Coaching and Reinforcement | 2 | None | 0 | None | 0 | Other | 1 | Referral Coordinators | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | ED/DCS | 0 | None | 0 | I have a separate intake staff because they are union positions and we cannot take them away, so we split the referral between centralized intake and our intake staff | 1 | Yes | 1 | When we are ready to schedule the patient . | 0 | They are moved to the front of the line for admission. | 1 | No | 2 | We don't | 1 | We cannot take away work from my intake team due to a CBA. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
Region 55 - From Sherrod & Holly - Jen Daniels - Vacation week of July 27-Aug 2nd
Note on AO1: Align with pilot high acuity definition = 1 Different from pilot high acuity =2
Note on AS1: 1 for each item listed
Note on AW1: Count
Note on BA1: Growth = 0, anything else = 1
Note on BC1: Growth = 0, anything else = 1
Note on BE1: RC=0, Any other role =1
Note on BG1: RC=0, any other role =1
Note on BK1: Scheduler = 0, anything else =1
Note on BO1: ED/DCS=0, anything else = 1
Note on BQ1: 1 point for each item listed if outside of standard process
Note on BS1: 1 point for each item listed
Note on BU1: YES = 1 NO =2
Note on BW1: 1 point for anything outside of standard process; one point if no process
Note on BY1: 1 point for any process that outside of pilot process
Note on CA1: Yes = 1, No = 2
Note on CC1: Intake/Growth = 0, any other role = 1
Note on CR1: 1 = Aligns with pilot high acuity definition 2 = Different than pilot high acuity definition
Note on CU1: Total portal in #6 (8) minus portals not used in 7
Note on CW1: Count of additonal portals used
Note on CY1: Count of payors listed requiring extra steps
Note on DC1: 1 point for each initiative listed
Note on DG1: Count
Note on DI1: 1 point for each challenge listed
Note on DK1: If Growth = 0, anything else = 1
Note on DM1: If growth = 0, any other role =1
Note on DO1: If RC = 0, any other role = 1
Note on DQ1: RC = 0, any other = 1
Note on DS1: RC=0, any other = 1
Note on DU1: Scheduling = 0, any other = 1
Note on DW1: Scheduling = 0, other = 1
Note on DY1: ED/DCS = 0, other = 1
Note on EA1: 1 point for each item listed if outside standard process of DCS/ED/AME leading huddle
Note on EC1: 1 point for each cross functional role listed
Note on EE1: YES = 1 NO = 2
Note on EG1: 1 point for anything outside of the standard process - 1 point for no process
Note on EI1: 1 point for anyting deviated from pilot processes
Note on EK1: Yes = 1 No = 2
Note on EM1: Intake or Growth = 0, any other roles or no roles = 1

## GoLive Schedule (2) (hidden)
REGION | Branch Code | Branch Name | Street | City | State | ADC | # of 2025 Months <-5% Budget | 2026 CHAP Survey Anticipated | Benefits (25%) | Efforts (25%) | Risks (25%) | Alignment (25%) | Score | ED SURVEY | 1. Program Name | 2. Branches | 3. Manage increase in referrals/admissions with current clinical staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 4. Current Field Clinician Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. VBE Status | 6 SCORE | 7. Major Initiatives | 7 SCORE | 8. Team response to new process or tool | 8 SCORE | 9. Groups requiring more change management | 9 SCORE | 10. Challenging referral source relationships | 10 SCORE | 11. Task "Monitor referral portals & respond to new referrals" | 11 SCORE | 11. Task "Gather missing referral documents & patient information" | 11 SCORE | 11. Task "Create chart in HCHB for new referral" | 11 SCORE | 11. Task "Complete "Review External Referral Request" workflow in HCHB" | 11 SCORE | 11. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 11 SCORE | 11. Task "Schedule patient's SOC visit in HCHB" | 11 SCORE | 11. Task "Make welcomes/readiness calls" | 11 SCORE | 11. Task "Lead referral huddles" | 11 SCORE | 12. Divided duties | 12 SCORE | 13. Cross functional roles | 13 SCORE | 14. Growth team authority to accept referrals with no ED/DCS input | 14 SCORE | 15. When do welcome calls occur? | 15 SCORE | 16. Handling of urgent or high priority referrals? | 16 SCORE | 17. Weekend Schedulers | 17 SCORE | 18. Weekend Referral Management | 18 SCORE | 19. Additional Input | RME/AME Survey | 1. Market Name | HH Locations | 3. Manage increase in referrals/admissions with current growth staffing? | 3 SCORE | 4. Current Growth Staffing | 4 SCORE | 4. Current Intake Staffing | 4 SCORE | 4. Current Scheduling Staffing | 4 SCORE | 5. "High Priority" Patient Definition | 5 SCORE | 6. All Portals Used in Order | 7. Portals NOT used | 6 & 7 SCORE | 8. Portals Used Not Listed in #7 | 8 SCORE | 9. Payors requiring extra op steps | 9 SCORE | 10. VBE Status | 10 SCORE | 11. Major initiatives | 11 SCORE | 12. Team Response to New Process/Tool | 12 SCORE | 13. Groups requiring more change management | 13 SCORE | 14. Referral source creating challenges | 14 SCORE | 15. Task " Monitor referral portals & respond to new referrals" | 15 SCORE | 15. Task "Gather missing referral documents & patient information" | 15 SCORE | 15. Task "Create chart in HCHB for new referral" | 15 SCORE | 15. Task "Complete "Review External Referral Request" workflow in HCHB" | 15 SCORE | 15. Task "Decline ERR workflow and enters non-admit reason in HCHB" | 15 SCORE | 15. Task "Schedule patient's SOC visit in HCHB" | 15 SCORE | 15. Task "Make welcomes/readiness calls " | 15 SCORE | 15. Task "Lead referral huddles" | 15 SCORE | 16. Divided duties | 16 SCORE | 17. Cross functional roles | 17 SCORE | 18. Growth team authority to accept referrals with no ED/DCS input | 18 SCORE | 19. When do welcome calls occur? | 19 SCORE | 20. Handling of urgent or high priority referrals? | 20 SCORE | 21. Weekend Schedulers | 21 SCORE | 22. Weekend Referral Management | 22 SCORE | 23. Additional Input
61 | B29 | Anchorage AK |  | Anchorage | AK |  |  | October -December 20206 | [5 empty] | Stephanie Cabiness | Providence at Home with Compassus Anchorage AK | None | Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | A patient that has discharged from the hospital with wounds or an extended stay. | 1 | H3 Currently on VBE | 3 | Not that I am aware of | 0 | M2 Some Coaching and Reinforcement | 2 | None | 0 | None | 0 | Other | 1 | Referral Coordinators | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | ED/DCS | 0 | None | 0 | I have a separate intake staff because they are union positions and we cannot take them away, so we split the referral between centralized intake and our intake staff | 1 | Yes | 1 | When we are ready to schedule the patient . | 0 | They are moved to the front of the line for admission. | 1 | No | 2 | We don't | 1 | We cannot take away work from my intake team due to a CBA. | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
50 | A01 | PELL CITY AL (CC1027) | 2401 STEMLEY BRIDGE RD STE 7 | PELL CITY | AL | [8 empty] | Christina Isbell | Pell City AL | None | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | pt acuity criteria, referral partner consideration, time sensitive care coordination | 1 | H3 Currently on VBE | 3 | Annual Skills check off March 10-11, none other scheduled at this time | 0 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators, Scheduling, Document Specialists | 3 | None at this time | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | ED/DCS | 0 | referral portals- Growth, gather missing info- referral coordinator, non-admit reason in HCHB- DCS/ED, Schedule pt- DCS/ED, Make welcome calls- DCS/ED, Lead referral Huddles- Referral coordinator & Growth management | 3 | We currently have a scheduler on the weekends to assist DCS with schedules, we have RC/Doc specialists managing portals and keying referrals, | 2 | No | 2 | within the first 48 hrs referral received | 0 | management notifies PCC of high priority to schedule urgently | 1 | Yes | 1 | Doc specialists, RC | 0 | None | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
50 | A00 | VESTAVIA AL (CC1028) | 1900 INTERNATIONAL PARK DR STE 250 | BIRMINGHAM | AL | [8 empty] | Kerri Couch | Vestavia AL | No | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Risk for rehospitalization, ORTHO, IV, Wound, New 02 | 1 | L1 No Plan for 2026 | 1 | We currently have 3 new DCS's, 1 on leave and 2 with 6m experience. We have hired over 10 new nurses for the field currently in training. | 1 | L1 Open to Change Adapt Quickly | 1 | Scheduling | 1 | VA Getting Auth Approvals | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Referral Coordinators and DCS will process non-admits, RC will do it if it is done prior to scheduling the patient out to a clinician. We have RN clinical coordinator that will do readiness calls and run the scheduling meeting at 3:30 to triage all of admissions. | 2 | Our Schedulers work a day on the weekend and take a day off during the week, Our DCS take call during the weeknights and on the weekends work at their computers all day Saturday and Sunday. Document Specialist work weekends. | 2 | Yes | 1 | Once the SOC comes to workflow | 0 | growth team member usually gives us a heads up that it is coming in an email so we are prepared. We have a scheduling meeting daily at 3:30. It is on our grid already and we schedule it out once it comes to workflow and it is confirmed. | 1 | Yes | 1 | Document Specialists | 1 | The weekends are the worst for missed referrals and/or slow process for getting them to workflow to assign to the clinicians in the field. We use a excel spreadsheet to put the patients on daily and it could be anywhere from 40-100 patients on that grid depending on the day. So, we get a ton of emails to follow for the patient to enter on that grid. | Raleigh Boyanton | Region 50 Alabama | Pell City & Vestavia | Strongly Agree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | High acuity- IV, Wound, TF, oxygen, ortho, cardiac | 1 | Watershed;Referral Management (All scripts);Epic Carelink;Intake (NaviHealth/Curaspan);Other;Ensocare;AIDA;Aidin | Aidin, AIDA | 5 | No | 0 | Aetna Cigna Humana UHC Va optum | 6 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Scheduling | 2 | VA | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | Doc specialists work portals on weekends | 1 | NA | 0 | Yes | 1 | Once pushed to scheduling | 0 | Growth hand holds those referrals through the whole process to ensure timeliness of care | 1 | Yes | 1 | Document specialists and growth hops on randomly | 0 | NA
62 | B08 | High Dester CA |  | HESPERIA | CA |  |  | April-June 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus High Dester CA | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B02 | Humbolt County CA |  |  | CA | [8 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B10 | Inland Empire CA |  | Pomona | CA |  |  | October-December 2026 | [5 empty] | Mary Dennis | Providence at Home with Compassus Inland Empire Pomona california | NA | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV infusion, Trach, TPN or complex care needs | 1 | H3 Currently on VBE | 3 | 2 new DCS High Desert office is expecting survey around August this year | 1 | M2 Some Coaching and Reinforcement | 2 | Growth/Scheduling | 2 | Referral Portals | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | intake, growth and scheduling do readiness calls, all 3 also do non admit reasons then ED reviews. Growth, intake and DCS also get documents | 3 | DCS and ED alternate weekends to cover on call but work the full 8 hours. | 0 | Yes | 1 | before sending to scheduling | 1 | put in growth or intake chat. Listed on MS LIST under escalation/operation notes | 1 | Yes | 1 | scheduler and DCS/ED on call, intake and growth | 0 | We use the MS List for capacity management, List when they are not in workflow or unable to reach pt. Any escalations that are outside capacity is sent in a teams chat | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B04 | LA County North CA |  |  | CA | [8 empty] | Luiza Chuang | LA North | LA North | Strongly Agree |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | status post hospitalization, IV, TKR, | 1 | H3 Currently on VBE | 3 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Scheduling | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | None | 0 | BOC covers for scheduling if needed | 0 | Yes | 1 | once referral is on schedulers workflow if not if its on MS list | 0 | within 24 hours | 0 | YEs | 1 | Same Team | 0 | we have daily stand downs and we dont see many intake reps joining and we would love to have their presence | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B05 | LA County South CA |  |  | CA | [8 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B01 | Napa Valley CA |  | NAPA | CA |  |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B06 | OC Anaheim CA |  | ANAHEIM | CA | [8 empty] | Kathleen Hatfield | PAH with Compassus, OC Anaheim CA | PAH Orange County Mission Viejo | Neither Agree or Disagee |  | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Tracheostomy care, Infusion, PleurX drain, wound vac, new enteral feedings | 1 | H3 Currently on VBE | 3 | Training of and go live of AI assisted documentation with Nestmed end of March, beginning of April. | 1 | L1 Open to Change Adapt Quickly | 1 | Growth | 1 | we receive incomplete referrals from our community sources outside of Providence (UCI, Memorial Care, Optum, etc.) | 4 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Ed/DCS | 0 | our access teams share responsibility for referrals they receive the access teams are Intake, VBE, and Community Liaisons (growth). | 1 | we do have a weekend team that is supervised by an RN who also works in the field during the week. She and a team of schedulers work normal 8-5 hours on the weekend to perform scheduling, and all 3 OC agencies are supported by this team. The intake and VBE teams also have weekend coverage | 1 | Yes | 1 | the welcome calls are done by our scheduling team. | 0 | DCS/ED are involved and the referral is escalated and pushed. OC agencies also have PM RN to support staffing of same day SOC | 0 | No | 2 | The intake and VBE teams manage the referral, the schedulers who work the weekends are hired specifically for weekends | 1 | we have a centralized intake team Director is Tameia Westby. She is your best contact for this roll out in CA. | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B07 | OC Mission Viejo CA |  | MISSION VIEJO | CA | [8 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | Parent agency for B07 is B06 Orange County Anaheim, California | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B09 | OC South CA |  |  | CA | [8 empty] | Kimberly Entwistle | B07 Orange County Mission Viejo, CA & B09 Orange County South, CA | NA | Agree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Tube feeding, Trach, CABG, same day visit | 1 | H3 Currently on VBE | 3 | NestMed April 2026 | 1 | M2 Some Coaching and Reinforcement | 2 | None | 0 | Orthopedic Surgeons | 1 | Other | 1 | Other | 1 | Other | 1 | Other | 1 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | We do not have referral huddles. We have daily stand up calls that we look at capacity. Those are lead by the schedulers. DCS, intake, VBE, Growth, and the ED attend. OCMV and OCS use the Circadia platform for the welcome calls. | 2 | OC South and OC Mission Viejo cover the same area. OC Anaheim, OC South, and IE cover the same areas. OC South, OC Mission Viejo , and OC Anaheim share one weekend/ holiday supervisor they each have their own schedulers which cover two teams on the weekends and holidays. From 5pm-8am the 3 OC ministries also share a AOC. | 2 | Yes | 1 | Intake does a call to confirm the demographics. The scheduler does a welcome call to secure a SOC date once they receive the referral. | 1 | The are scheduled as they are ordered. | 1 | Yes | 1 | The intake and VBE team, schedulers, and the supervisor. | 1 | NONE | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
62 | B03 | Sonoma County CA |  | SANTA ROSA | CA |  |  | October-December 2026 | [5 empty] | Bridget Norambuen | Providence at Home with Compassus LA South, Torrance, CA; Providence at Home with Compassus Sonoma, Santa Rosa, CA; Providence at Home with Compassus Humboldt, Eureka, CA; Providence at Home with Compassus Napa Valley, Napa, CA | See column Y | Disagree |  | H3 We're stretched thin | 3 | H3 We're stretched thin | 3 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | Clinical needs needing time-sensitive treatments (IV, Wound VAC, TPN, etc); high profile patients (especially in the LA area) | 2 | H3 Currently on VBE | 3 | I have one program that has a VBE that will be going live in 2026 (Torrance/San Pedro) but has a VBE in Santa Monica (LA South). In Napa and Santa Rosa, there are functioning VBEs but Napa's Providence Hospital is being sold so that may disrupt that environment. In Humboldt, there is one liaison and no coverage on weekends. | 2 | L1 Open to Change Adapt Quickly | 1 | Referral Coordinators | 1 | Providence St. John's hospital in Santa Monica sends a VERY small percentage of their referrals our way, despite it being a VBE Hub and part of Providence. We have our first HHCCs in Napa/Sonoma (1 person) and LA South (a different person) which is exciting a long overdue. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | N/A | 0 | On weekends, Nor Cal has one scheduler shared between Humboldt and Sonoma and only intermittent coverage in Napa due to schedulers being represented. | 1 | Yes | 1 | It is supposed to happen with Intake but rarely does. Typically completed by scheduling but continually have to hound intake to get viable phone numbers. | 1 | We expedite holding space for them and call them right away to schedule visits, also make sure assigned to very reliable clinicians. | 1 | Yes | 1 | Intake | 0 | N/A | Rhea Laughlin | California | Napa Valley CA Humbolt County CA Sonoma County CA LA County North CA LA County South CA OC Anaheim CA OC Mission Viejo CA High Desert CA OC South CA Inland Empire CA | Strongly Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | VBE, PMF providers, PMF payers, SNF Collaborative, Ortho Surgeons, Community Hospitals, TEAMS Initiative Hospital, DRG specific patient | 5 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;Ensocare;Referral Management (All scripts);Watershed;Other | Careport | 6 | NA | 0 | NA | 0 | H3 Currently on VBE |  | We need to remain swift and timely to our community partners so that we can competitively partner with outside organizations, as historically we have been a barrier to speed to access care. Once care is accessed we prove to be the best. . | 0 | L1 Open to Change Adapt Quickly |  | Referral coordinators, ED/DCS | 2 | We continue to let down community hospital partnerships outside of our own Providence Hospitals, other hospitals that rely on our Intake and Growth relationships struggle to be heard and seen. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Respond to new referrals is shared by Growth and Referral Coordinator, Gather Missing Referral Documents is managed by Referral Coordinator, and sent back to Growth to gather the data. | 0 | Unknown | 0 | No | 2 | In the VBE intake process we call them immediately, in the community process I'm unsure. | 1 | All Regional and AME escalations pathways are followed | 1 | Yes | 1 | VBE caregivers work weekends, Intake work weekends and DCS/schedulers work weekends | 0 | VBE owns 100% of the intake/scheduling intake process for CA, my community AME/Growth team relys on intake process for their support that is the only difference between my two workflows.
50 | A53 | JACKSONVILLE FL (CC1801) | 7235 BENTLEY RD STE 236 | JACKSONVILLE | FL |  |  | Jan-April 2026 |  |  |  |  | 11 | Daisy | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A58 | PANAMA CITY FL (CC1803) | 2211 S HIGHWAY 77 STE 203A | LYNN HAVEN | FL |  |  | October 2026 - January 2027 | [5 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A55 | PENSACOLA FL (CC1802) | 1115 E GONZALES ST STE 1001 | PENSACOLA | FL | [8 empty] | Gary Woodham | Pensacola and Panama City Fl | Pensacola and Panama City Fl | Strongly Agree |  | H2 Managing but it's tight | 2 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | IV , Orthos , Wound Care | 1 | M2 2026 GoLive | 2 | Possible CHAPS survey in Panama CIty timeline unknown | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Staffing Orthos , They have specific admit dates and in a broad geography to cover | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | NA | 0 | Admin on call covers schedule changes that happen over the weekend ( DCS ) | 0 | Yes | 1 | When in work flow | 0 | In a team scheduling call we prioritize admits and delegated to clinicians first | 0 | No | 2 | Admin on Call | 1 | Growth needs to stay vigilant about clearing "asks" to keep patients referrals pushing to workflow for scheduling | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A79 | ST PETERSBURG FL (CC1805) | 11001 ROOSEVELT BLVD N STE 100 | St. Petersburg | FL | [7 empty] | 11 | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
50 | A78 | TAMPA FL (CC1804) | 137 S PEBBLE BEACH BLVD STE 203 | SUN CITY CENTER | FL | [7 empty] | 11 | Michelle Crawford | [55 empty] | Brad Waid | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Jacksonville, St. Petersburg, Tampa, Pensacola and Panama City Florida | Strongly Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | L1 Well Staffed |  | Wound Vac, IV, Peg Tube | 1 | Ensocare;Epic Carelink;Intake (NaviHealth/Curaspan);Aidin;AIDA;Referral Management (All scripts);Watershed;Other | No | 7 | None | 0 | Humana Gold | 1 | M2 2026 GoLive |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Ascension Partnerships | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Other | 1 | Growth | 1 | Other | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | after patient has been accepted | 0 | Within a few hours | 0 | Yes | 1 | Intake | 0 | None
51 | A20 | ANDERSON IN (CC2311) | 600 CORPORATION DR STE 104 | PENDLETON | IN |  |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A24 | Bloomingham IN (Bedford) | 1324 K ST STE 150 | BLOOMINGTON | IN | [8 empty] | Darla Bell |  | Bloomington (managed by Darla)is actually branch of Idianapolis managed by Suchi | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | None | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A26 | EVANSVILLE IN (CC2313) | 7321 EAGLE CREST BLVD STE A | EVANSVILLE | IN |  |  | Jan-April 2026 | [5 empty] | Darla Bell |  | None | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | ASVE and aligned partners, IVs, wound vacs, PEG teaching. | 1 | L1 No Plan for 2026 | 1 | We are in the CHAP window in Evansville 1st quarter. | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | I am not aware of the "review external referral request" in workflow. If a referral needs review I, the ED, am notified in the DL email to review by the growth member if they want to appeal or have any questions about the acuity of the patient. | 0 | None | 0 | Yes | 1 | Our PCCs use the DL emails to make these calls, in order to prevent TICs. We have a very close team that works well together and we discuss these on referral huddle daily. We are very proactive with the welcome calls. We don't want to waste sending out a PPV staff to a visit that is not viable. We want to make sure our field staff is productive so we feel this call is valuable. Also, if we would wait for them to hit the PCC workflow we could be out of the time range. Our growth team is awesome to help find other numbers if we are not successful with getting through with what is entered as well. We seem to have a lot of patients that request certain days as well so it helps if we need to get a POSOC entered. We have 100% on our TIC for this reason. Our PCCs are awesome! | 0 | Growth contacts ED, we discuss if we can get to the patient timely after ED talks with PCCs. Normally we are able to get them admitted. It is a team effort. | 0 | Yes | 1 | On call team. They can always call ED, We do an email on Friday with our availability and plans for weekend and Monday to our weekend RC, PCC, and admin. We spend a lot of time on Friday until 5 making sure we have all workflow complete and calls made. Our Region 51 RC group is also amazing as well. | 1 | We were thankful to pilot the F2F. RCs in our region are making sure this is in the referral information to best of their ability and it has really helped us resolve those F2F issues and has increase the satisfaction of the field clinician going into the home. It gives them the clinical information they need to prioritize the focus of care for the patient. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A22 | INDIANAPOLIS IN (CC2314) | 8909 PURDUE RD STE 107 | INDIANAPOLIS | IN | [8 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A21 | KOKOMO IN (CC2315) | 2626 S WEBSTER RD STE B | KOKOMO | IN |  |  | Jan-April 2026 | [5 empty] | Beth Brehm | Ascension at Home Together With Compassus Anderson Indiana | Kokomo | Strongly Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | Every patient, but if I need to be specific, I would say IV, Tube feed, Trach, Wound Vac, Timed skills, etc. | 1 | M2 2026 GoLive | 2 | Nothing. We are ready! | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | Referral Awareness Gap, Competitive Dynamics, Reputation or Brand Perception: | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Decline ERR workflow and enters non-admit reason in HCHB: RC does if prior to scheduling, ED does after pushed to scheduling. | 1 | NA | 0 | YEs | 1 | After Referral pushed to scheduling workflow. | 0 | Increased communication to assure happens as planned. | 0 | Yes | 1 | On Call weekend Team. RC, PCC, PTC, (Admin as needed) | 0 | Anderson and Kokomo Indiana are ready! | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A67 | LAFAYETTE IN (CC2319) | 703 N 36TH ST | LAFAYETTE | IN | [8 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A25 | NORTH VERNON IN (CC2316) | 2337 NICHOLAS CT STE C | SEYMOUR | IN | [8 empty] | Suchi Modi | AAH Indianapolis/ IN | AAH @Lafayette and AAH North Vernon IN + Bloomington IN (Darla manages Bloomington) | Agree |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV, Wound Care, Joint Replacement | 1 | M2 2026 GoLive | 2 | Pre VBE would be ideal. | 0 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Referral Huddles: Indy Ran by Scheduling, NV ran by RC and Lafayatte ran by DCS | 1 | NA | 0 | YEs | 1 | After pushed to schedule workflow | 0 | Occasionally we would hold spots for IV | 1 | Yes | 1 | PTC | 0 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
52 | A28 | PITTSBURG KS (CC2503) | 200 E CENTENNIAL DR STE 13 | PITTSBURG | KS | [8 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
52 | A27 | WICHITA KS (CC2504) | 301 N MAIN ST STE 950 | WICHITA | KS | [8 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 1 | None | 0 | L1 No Plan for 2026 |  | - | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
54 | A77 | PADUCAH KY (CC2602) | 225 MEDICAL CENTER DR STE 203 | PADUCAH | KY | [8 empty] | Renee Wurth | Mercy Health Homecare by Compassus - Paducah, KY | N/A - (submitted for Metropolis IL branch but have not yet received approval) | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | H1 Well Staffed | 1 | H3 We're stretched thin | 3 | High Priority patients are those that are discharging from acute hospitals, as well as, those who had outpatient orthopedic surgery the day before. We also have many wound vacs/infusion patients who have specific times/needs that are quick turnarounds from referral. | 1 | L1 No Plan for 2026 | 1 | We have applied to have a branch in Metropolis, IL but have not received approval from CMS at this point. Otherwise no major known events. | 1 | M2 Some Coaching and Reinforcement | 2 | Field Staff | 0 | Our orthopedic physicians send referrals early and we have to follow up regularly with them to ensure surgeries remain scheduled and that we are out to see the patient the next day. Vanderbilt and Barnes Jewish often send us requests and it takes days of follow up to get confirmation of patient choosing us (occasionally even after patient is already discharged). We hold spots on our scheduling grid for these patients, requiring a lot of attention and follow up. Multiple local physicians' offices send referrals at the very end of the day making it difficult to process them timely for the referral coordinators. | 3 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Referral Coordinators cover portals on weekends and attend to faxed referrals. RCs and ED/DCS assist with gathering missing referral information as needed. Growth makes welcome calls and Scheduling makes readiness call. Scheduler assists growth in referral huddles with current avialability and episodic percentage of referrals admitted for month to date. | 1 | Referral Coordinators cover weekends for referrals. Administrator on Call (DCS) covers scheduling from Friday at 5pm to Monday at 8 am. | 1 | Yes | 1 | Welcome call is the day the referral is accepted. Readiness call occurs the day before admission (Friday before for Monday admission). | 0 | During office hours, communication comes into DCS/ED and is coordinated by the DCS that is on call for the week. Administrator on call (DCS) coordinates the process to get the patient's chart to the clinician if it is after hours or on the weekends. | 0 | No | 2 | Referral Coordinators manage the referrals and Administrator On Call is the accept/decline decision maker. | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout. | Farrah Gay | Paducah KY | Paducah, KY and we have applied for Metropolis, IL to be a branch. | Neither Agree or Disagee |  | L1 Well Staffed |  | H3 We're stretched thin | 3 | M2 Managing but it's tight |  | Complex, unstable or acute needs requiring urgent intervention to prevent hospitalization, nursing home placement or further decline. | 1 | Epic Carelink;Aidin;Other;Ensocare;Referral Management (All scripts);AIDA;Intake (NaviHealth/Curaspan);Watershed | #5-8 are not | 4 | Not that I am aware of. | 0 | VA - required auth at intake before we can start care. Trisha Curtis is our insurance manager and looking into this if you would like to circle back with her for more information. | 1 | L1 No Plan for 2026 |  | We've requested to make the Metropolis, IL location a branch. The application was submitted in 2024. | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Referral sources seem to understand the universal staffing capacity issue among all healthcare, so they have not verbalized as much frustration recently as they have in the past. | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | Make readiness call - completed by scheduling Lead referral huddles - completed by both growth and branch | 0 | RC/intake covers weekend referral management. Administrator on call covers scheduling and accepting/decline. | 0 | Yes | 1 | Welcome call - day the referral is accepted by growth/patient PCC readiness - day prior to start of care except for weekends. | 1 | Notification to administrator on call who then communicated and schedules | 1 | No | 2 | RC/intake and Administrator on call | 0 | Growth and Branch do not want to lose the ability to choose to accept/decline and we want to make sure that we have a warm hand off with the provider if we choose to decline a referral. Our team works best with clear definition of ownership of tasks and a clear process to follow. I feel like as a group our growth/intake/ops team work well together and we would be ready to rollout.
52 | A02 | PORTAGE MI (CC3146) | 5136 LOVERS LN STE 200A | PORTAGE | MI | [8 empty] | Stephanie Watkins | Compassus Home Health - Portage MI | NA | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Infusion, Tube Feeding, Chest Tubes, Pleurx or Aspira drains, Chole Tubes, Nephrostomy Tubes, Tracheostomy, new to Self Catheterization, some wound care patients as they all may need same day care and education. | 1 | L1 No Plan for 2026 |  | We are actually just starting our Commure Pilot, Realignment of agency activities and trainings to standardize across the company in April and May. | 0 | M2 Some Coaching and Reinforcement |  | Growth, Scheduling, ED/DCS | 3 | Beacon Hospitals just went online with a new EMR and referral portal of Ensocare but they are not functioning efficiently in those platforms at this time impacting timeliness of referral updates, orders and even notification of discharges. They have no current format to write home care orders in their EMR and using a paper form and faxing but frequently forget, they are not routinely confirming assignment of referrals to agency in Ensocare and are not utilizing the system for updates or communication. Previously when they were Ascension facilities, we had access in the version of Cerner being used and could assist their Care Management and Discharge Planning teams in getting the necessary information to agency timely. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | Referral Coordinators also monitor referral portals and respond to new referrals on the weekends. ED/DCS assist with assigning patient's SOC visit in HCHB on weekends or afterhours, Scheduling assists Growth PTC with welcome and readiness calls. | 0 | As above we have no weekend scheduling so ED/DCS covering the Administrator on Call role assigns out needed SOC/ROC visits for weekend and Mondays. Will also sometimes work to track down referral information but does not have access to all needed portals or EMRs as growth does. The Admin on Call also responds to the referral emails if agency is unable to accept a referral for follow up by the referral coordinators/growth team. | 1 | Yes | 1 | When the discharge is confirmed and the referral is complete. | 0 | Growth notifies the team when received with anticipated DC date and location to confirm branch can safely accept and admit. | 0 | No | 2 | Referral Coordinators, occasionally growth will assist if they are expecting information on the weekends who then email th | 0 | None | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
52 | A04 | WARREN MI (CC3144) | 28120 DEQUINDRE RD | WARREN | MI |  |  | November 2026-February 2027 |  |  |  |  | 11 | Cynthia Voelker | [55 empty] | Penelope Wilson | MI - Warren & Portage | Warren, Portage | Strongly Agree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | High acuity, infusion, significant wounds | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Other;AIDA;Aidin;Intake (NaviHealth/Curaspan);Watershed | AIDA, Aidin, NaviHealth, Watershed | 4 | None | 0 | Unsure | 0 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Referral Coordinator | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | ED / AME lead referral huddles. | 0 | Laurie Peruzzi - evening start of care readiness calls. | 1 | Yes | 1 | Unsure | 1 | Addressed at the start of morning huddles; direct contact to ED | 0 | Yes | 1 | Referral Coordinators | 0 | Unsure
52 | A68 | ALPENA MI (CC3153) | 109 N SECOND AVE STE 202 | ALPENA | MI | [7 empty] | 11 | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
52 | A03 | GRAND BLANC MI (CC3145) | 5445 ALI DR DEPT 500 | GRAND BLANC | MI | [7 empty] | 11 | Cynthia Voelker | [55 empty] | Ronald Boggia
52 | A06 | TAWAS CITY MI (CC3147) | 808 W CEDAR ST BLDG A | STANDISH | MI | [7 empty] | 11 | Krystal Schmidt | Compassus Tawas- Standish, MI and Compassus Alpena- Alpena MI | Alpena is currently running under Tawas branch while full licensure approval is pending. | Neither Agree or Disagee |  | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | IV therapy, Enteral feeding, Wound vac and other high skilled wound care. | 1 | M2 2026 GoLive |  | No major changes | 0 | M2 Some Coaching and Reinforcement |  | Scheduling, Growth | 2 | No challenges | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | When chart is completed and pushed to scheduling | 0 | Utilize oncall staff if needed | 1 | No | 2 | DCS on call | 1 | None | Ronald Boggia
51 | A89 | COLUMBIA MO (CC3437) | 3310 BLUFF CREEK DR STE 106 | COLUMBIA | MO | [8 empty] | Angie Walker | Compassus Columbia MO | NA | Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | Clinically complex, Increased risk for readmission, timed admission (ex. PICC w/ ABX). | 1 | L1 No Plan for 2026 |  | Leadership changes/staffing changes-current and ongoing | 1 | L1 Open to Change Adapt Quickly |  | ED/DCS | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Interim ED, DCS, RC and HHCC all help monitor referral portal. | 1 | Our BOC is also our scheduler. | 1 | No | 2 | After the referral is considered complete, and before it is scheduled to a clinician. | 0 | That referral gets prioritized and scheduled ahead of a "routine" referral. | 0 | No | 2 | Responsibility shared between our HHCC and the admin on call. | 1 | NA | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | None | 0 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
53 | A51 | BILLINGS MT (CC3506) | 490 N 31ST ST STE 130B | BILLINGS | MT | [8 empty] | Joanne Wirtjes | Billings MT | NA | Strongly Disagree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | ortho pts, IV abx pts, cardiac pts | 1 | L1 No Plan for 2026 |  | New ED in 1/2026, new DCS in 3/26, rapid growth over last couple of months - plan on continuing growth, added 6 new clinicians in 2 months. | 2 | L1 Open to Change Adapt Quickly |  | None | 0 | VA - awaiting auth for SOC of pts and bundled and non-bundled for patients. | 1 | Growth | 0 | Referral Coordinators | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | EDDCS | 1 | Referral Coordinators | 1 | not sure whose task to build the hchb chart | 0 | NA | 0 | Yes | 1 | Ideally prior to chart getting pushed to scheduling | 0 | discussed in daily huddle/referral meeting and via TEAMS | 0 | No | 2 | AC Team | 0 | None | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A52 | BUTTE MT (CC3508) | 19 DISCOVERY DR | BUTTE | MT |  |  | Jan-April 2026 | [5 empty] | Jacqueline Mathews | Compassus Home Health - Butte MT | None | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Wound care, fresh surgical patient discharging from the hospital and most patients coming out of the hospital. | 1 | L1 No Plan for 2026 |  | 2 new nurses will be training over the next couple of months so it would be best to roll out after they are trained. Also have new PTC who needs to feel more comfortable with her role. | 2 | M2 Some Coaching and Reinforcement |  | Growth, Referral Coordinators | 2 | We need improved referral source relationships so we can generate referrals needed | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 0 | At times the ED will enter the ERR workflow and enter non-admit reason if it hasn't been done timely At time the ED will schedule patients if scheduler is not available. Make welcome calls is growth, readiness calls is scheduling | 2 | ED is also the DCS and BOC is also the scheduler | 2 | Yes | 1 | HCC is responsible for any bedsides, PTC is responsible for welcome call. BOC/scheduler is responsible for readiness calls once referral is complete and ready to be scheduled according to growth team. | 0 | Discussed in daily huddle, make a plan as to when patient can be admitted. | 0 | No | 2 | Administrator on call if needed | 1 | HHCC is new to having PTC, having a hard time relinquishing duties | Kelly Swartz | Wisconsin, New Mexico, Montana | Billings, Butte | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A50 | ALBUQUERQUE NM (CC4004) | 7770 JEFFERSON ST NE STE 110 | ALBUQUERQUE | NM | [7 empty] | 13 | Raechel Dominguez | [55 empty] | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A54 | SANTA FE NM (CC4005) | 1692B HOSPITAL DR STE 102 | SANTA FE | NM | [7 empty] | 13 | Raechel Dominguez | [55 empty] | Kelly Swartz | Wisconsin, New Mexico, Montana | Albuquerque & Santa Fe | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
54 | A85 | LIMA OH (CC4418) | 959 W NORTH ST | LIMA | OH | [8 empty] | Cheryl Bechtel | Mercy Health Homecare by Compassus Lima Ohio 45805 | No | Strongly Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Skilled need IV, Wounds, Drains | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | Insurance Authorization | 1 | No | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Other | 1 | ED/DCS | 0 | n the Lima Market the scheduler is the first person to call the patient to set up a home visit. Would be nice to have the growth team verify information prior to the scheduler. This would save time as the scheduler then has to reach back to the growth team to obtain the information | 0 | DCS will assist with scheduling if scheduler is on PTO Training Clinical RN coordinator to assist with scheduling | 1 | Yes | 1 | When the referral is in the workflow of the scheduler. | 0 | Reviewed by the DCS/ED prior to scheduling if it is known at the time of referral is sent. Growth team doesn't communicate with the intake team sometimes causes problems with priority of the patient needs to be schedule appropriately. | 0 | No | 2 | Growth/Intake | 0 | To improve efficiency and reduce delays in the Start of Care (SOC) process, several opportunities for improvement have been identified within the intake and referral workflow in the Lima market. 1. Growth Team Education on Home Health Qualification and Skilled Need The new Growth Team would benefit from additional and ongoing education regarding: •Qualification criteria for home health services •Identification of skilled need for the patient Currently, referrals are accepted before the clinical skill level and priority of the patient’s needs are fully identified. This can create delays when the patient requires a higher level of clinical prioritization than initially recognized. 2. Insurance Authorization and Verification of Benefits Process Another opportunity for improvement is within the insurance verification and authorization workflow. Currently, delays occur when: •Verification of Benefits is completed, but •The scheduler later needs to re-request insurance authorization, which slows the referral and SOC process. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A84 | LORAIN OH (CC4415) | 3500 KOLBE RD | LORAIN | OH | [8 empty] | Andrea Faurot | Lorain OH | N/A | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | IV, Wound, Pleurex or chest tubes, Tube feed, TPN Total Joint patients, nephrostomy, trach patients, New O2, CABG | 1 | L1 No Plan for 2026 |  | CHAP survey pending immediately | 1 | M2 Some Coaching and Reinforcement |  | Unsure | 0 | Yes the Lorain BSMH market needs lots of education on why and they want a smoother process. They oppose change often, but sometimes will come along as long as there is good communication and collaboration. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Growth | 1 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Growth and intake often share responsibilities or cover for each other | 1 | RN Coordinator is also in on call rotation and assists schedulers back up as well as Home Health Admin Assistant | 1 | Yes | 1 | Once sent to scheduling | 0 | escalated to DCS or ED | 0 | No | 2 | Intake & Growth | 0 | Clear expectations of responsibility and throughput diagram. So expectations are clear. Our schedulers are part of a bargaining unit, so any changes that could impact them—such as modifications to their job descriptions or working hours—would need to be reviewed and vetted through the bargaining unit. With negotiations starting next week, it would be helpful to identify any potential changes proactively so we can address them in advance. This will ensure we remain aligned with the bargaining process and avoid any delays. If there is someone else who should be looped in or involved in these discussions, please feel free to connect them. Brian Jackson and Yashica Smith is who we use to review any changes that may impact our bargaining team members we get them included early and often to discuss any potential changes. I have looped in Melissa just for transparency. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A86 | TIFFIN OH (CC4419) | 45 ST LAWRENCE DR | TIFFIN | OH | [8 empty] | Brandy Fredritz | Mercy Home Care by Compassus Tiffin Ohio | N/A | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day needs, daily needs, IV care, and wound care. | 2 | L1 No Plan for 2026 |  | Hiring full therapy team (versus contracted) in 2026 and adding more nursing staff. Hiring increases started in February 2026 until all positions are filled. | 1 | L1 Open to Change Adapt Quickly |  | Referral Coordinators, Schedulers | 2 | When utilizing CarePort, the larger hospitals like OSU and Cleveland Clinic send out "blast referrals" and are poor/slow to respond. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | NA | 0 | Our BOC covers scheduling when our PSC is off. DCS/ED cover scheduling on the weekends. | 1 | Yes | 1 | Varies depending on how quickly the referral is worked and when the SOC is needed. We typically are reactive to our referral process and plot people quickly due to low staffing. Typically, the welcome/readiness call is completed the day before. | 1 | Communication between all Growth/RC/ED/DCS in TEAMS/Email. | 0 | No | 2 | RC/Growth with DCS/ED input | 0 | n/a | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A87 | YOUNGSTOWN OH (CC4412) | 979 TIBBETTS WICK RD STE A | GIRARD | OH | [8 empty] | Melanie Boyts | Youngstown OH | NA | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | CABG (open heart), Mitral Valve Replace, Carotid endarterectomry, fem-pop bypass, Infusion patients. orthopedic patients needing same day or next day visit, Enteral/Tub Feed, Trach, wounds/wound vacs, pleurx drains/drains | 1 | L1 No Plan for 2026 |  | Focusing on recruitment and retention. Recruitment in this market has been slow. Starting to make some movement in 2026 but it's really to maintain current operations and not necessarily to support growth. PT/OT/ST extremely difficult to recruit for. Other competitor agencies in area who have established relationships/presence in our JV BSMH hospitals. | 1 | L1 Open to Change Adapt Quickly |  | Growth, Referral Coordinators | 2 | The referral source relationships within the JV BSMH hospitals present operational challenges, particularly within the case management team. A notable issue is the development of relationships with competitor home health agencies within our hospitals, which results in these competitors being prioritized with favorable payors. These dynamics highlight a broader struggle in this market hospital to embrace the joint venture (JV) as a true partnership. From the inception of the JV, the relationships have been challenged, largely tied to efforts in managing payor mix effectively. Several case managers and physicians continue to demonstrate a preference for competitor home health agencies, which undermines the intended collaboration of the JV. While the Area Market Executive in this market has worked diligently to improve relationships and enhance communication around partnerships, significant barriers remain despite these efforts. An additional challenge involves the pressure to accept patients that are often declined by other home health agencies. When explanations are provided about why we cannot accept these patients, resistance frequently arises, escalating the matter to the JV director on the BSMH side. This creates unnecessary friction, adding to the operational complexity. Lastly, the communication dynamic often positions our team as separate from the partnership. This creates the perception that the partnership is one-sided, rather than a true collaborative effort. Addressing these challenges is critical to fostering a unified partnership, optimizing payor relationships, and removing operational inefficiencies. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Scheduling | 1 | Confusion from operations team on who is doing what when a referral comes together. Several roles involved in one patient referral. | 0 | scheduling works weekend here. RC's in this market covered growth for a very long time, i think there is still confusion from the operations team on who does what part of a referral when requesting additional information | 1 | Yes | 1 | the scheduler completes this the day before. Done around 330pm when we consider our scheduling grid final. | 0 | Growth team CTC, HHCC and PTC communicate and move patients around on the scheduling grid accordingly. if there is a request to add a patient on outside of what our capacity is DCS and/or ED approve that. | 1 | Yes | 1 | RC & Growth | 0 | The implementation of the new scheduling grid on 12/8/25 has shown promise in aiding payor mix management. However, discharge planning continues to present significant challenges, particularly within the BSMH hospitals. Many patients appear on the scheduling grid for specific discharge dates, but frequently either do not go home as planned or are discharged on unanticipated dates. You expect this if they are discharges planned far in the future but the concern here is you review the patients on the 230pm call set up schedules after 330pm and come in following morning and patient didn't dc. We expect things change and this happens, but it is a more frequent occurrence here. It has been noted that BSMH referrals are sometimes assigned discharge dates that are not definitive, simply to facilitate their acceptance. This creates difficulties in accurately following patients day to day and predicting their actual discharge dates. As a result, we often face situations where patients scheduled for admission do not go home as anticipated. This creates complications in confirming schedules, as clinicians frequently find that patients they planned to admit are not yet discharged. To manage these issues, we attempt to pull other patients forward to fill the vacant spots, though these adjustments often occur too late to avoid disruption. Our clinicians, who operate on a pay-per-visit model, need to begin their day by 8:00 a.m. to maintain productivity and minimize financial impact. To address these ongoing discrepancies, we continue to hold two staffing huddles daily, one in the morning and one in the afternoon. These huddles are essential due to the high rate of unexpected changes in discharge timing and the need for late adjustments. I see an opportunity for improvement in this process by ensuring that patients are added to the schedule once their discharge is confirmed. Concerns with having the necessary attachments and documentation readily available on patient charts. For example, the AVS (After Visit Summary) or DC summaries are frequently requested by SOC clinicians. The DCS often has to pull supporting documentation, such as Face-to-Face supporting documentation, during the coding review process. Addressing these documentation and coordination challenges will be critical to improving the overall efficiency of the referral to scheduling workflow. | Rebecca Anderson | BSMH OH -JV | Tiffin, Lima, Lorain, Youngstown | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | IV, Wounds, Pleurex drains, Ortho Joint patients, tube feed, CABG patients, TPN | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Other;Intake (NaviHealth/Curaspan);Watershed;AIDA | Watershed, AIDA, and NaviHealth/Curaspan | 4 | No | 0 | Unknown | 0 | L1 No Plan for 2026 |  | October-end of year with budget and strategic planning | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Yes, not having access to non-BSMH EMR's to access appropriate referral documents needed. Cleveland Clinic and University Hospitals | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Scheduling | 1 | Decline ERR workflow and enters the non-admit- this is a share responsibility between Growth and RC's. Growth enters the non admit reason, RC complete thh workflow Make welcome calls- Growth completes the first touchpoint and verification. Schedulers complete a scheduling/Readiness call | 2 | None | 0 | Yes | 1 | compelted by growth when referral is received and then once placed on grid for scheduling a second call is placed to coordinate the soc | 1 | Good communication and notes on the scheduling grid | 1 | No | 2 | Growth PTC | 0 | BSMH high sensitivity to change and process
54 | A96 | ATHENS OH (CC4427) | 444 W UNION ST STE C | ATHENS | OH | [8 empty] | Jennifer Frost-Coon | Ohio Health at Home with Compassus - Athens | None | Agree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV patients | 1 | L1 No Plan for 2026 |  | Not that I am aware of at the moment. | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | Yes, we have a few providers who can become challenging with signing the POC/orders/following after they agree to follow. I manage those providers in the moment with education and feedback. | 1 | ED/DCS | 1 | Growth | 0 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | There are three of us in back office that monitor the referral chats and weigh in- it is mostly me that responds. | 1 | With our office being more compact the Scheduler/BOC are the same person in my office and she can schedule patients, she is not clinical. I have a Clinical Coordinator who supports staff and completes and covers for the Scheduler/BOC when she is on PTO. I am the only one in our office who is in the rotation for weekends. | 2 | No | 2 | Specifically I am not so sure- however the welcome call is documented at bedside as well as before the referral is pushed often times. | 1 | Over communication between the HCC and PCC along with back office and ensuring good communication between the patient and the office so that the patient knows the plan too | 0 | No | 2 | The ED and or who is covering in the weekend rotation. A warm hand off is given on Friday going into the weekend with insight into capacity for the weekend and beginning of each week. | 1 | The weekends are the roughest with Intake and communication. Ensure there is good support over a weekend would be my two cents. | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
54 | A93 | COLUMBUS OH (CC4424) | 6805 PERIMETER DR FL 1 | DUBLIN | OH | [8 empty] | Tabitha Campbell | OHH Columbus OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients new to tube feeds | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | Non admits are completed by clinicians-CC- and ED | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
54 | A94 | MANSFIELD OH (CC4426) | 50 INDUSTRIAL DR | LEXINGTON | OH | [8 empty] | Tabitha Campbell | Mansfield OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients who have wounds/depending on the severity | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | I do not know who is responsible for entering the Review External Referral Request- possibly intake? | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
54 | A95 | MARION OH (CC4425) | 1713 MARION MOUNT GILEAD RD STE 107 | MARION | OH | [8 empty] | Tabitha Campbell | Marion OH | Marion OH, Mansfield OH | Disagree |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Patients with new ostomy or newer ostomies | 1 | H3 Currently on VBE |  | None | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | None | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | Growth | 0 | None | 0 | We have clinical coordinators that work weekend and through the week that help with scheduling and help with ROCs. They also work closely with the growth team and intake on our morning huddle call | 1 | Yes | 1 | Growth tries to do them, but some fall on scheduling. | 1 | Growth or intake reaches out to the Branch and notifies via teams chat | 0 | Yes | 1 | DCS on call | 1 | None | Holly Stewart | Ohio Health - Columbus, Marion, Mansfield, Athens OH | Columbus, Marion, Mansfield, Athens | Strongly Disagree |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | L1 Well Staffed |  | Ortho, CABG/TAVR, OPAT/IV, Tube Feed | 1 | Epic Carelink;Other;Ensocare;Aidin;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed | AIDA, Watershed, All Scripts, Curaspan | 4 | Careport is not listed but is our 2nd highest portal however I would be hesitant to have this platform auto pulled as we only admit about 3% of the hundreds of referrals received. The main hospital that uses them mass refers to 20+ agencies, and it kills our conversion rate | 1 | Unsure | 0 | L1 No Plan for 2026 |  | NA | 0 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | Ohio Health expects responses in under 30min to accept or decline a referral. As their JV partner, we cannot afford delays in this communication. Careport referrals are not true referrals most of the time. They mass refer and then cancel most referrals. We may be 300+ in a month and only admit 3% as the others did not actually request us. I would not want those numbers added to our conversion rate or waste the time keying their charts etc. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Growth | 1 | For gathering missing referral documents and patient information this depends on if the referral source has a growth member assigned or not. About 12-15% of our referral sources do not have growth members assigned as their BOBs are already way too large and difficult to manage. Without growth assigned- intake acts as growth for those referrals. | 1 | Growth assists intake on the weekends to monitor for Ohio Health hospital discharges. | 1 | Yes | 1 | Growth makes the call either on the phone or face to face (bedside at hospital) when referral is received and accepted. | 1 | Growth is usually pushing the team (intake and scheduling) to move quickly through notes and teams messages. LOTS of communication in various formats to ensure everyone is on the same page. | 1 | Yes | 1 | Intake | 0 | We really struggle with capacity so we have lots of patients with M0102 dates. We struggle to identify which patients need to be seen when and getting patients through the intake process quickly enough that they can be scheduled out in time. We need some sort of method to easily alert all departments of TIOC risks.
52 | A30 | BARTLESVILLE OK (CC4513) | 3061 SE WASHINGTON BLVD | BARTLESVILLE | OK |  |  | Feb-June 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | None | 0 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
52 | A29 | TULSA OK (CC4514) | 4612 S HARVARD AVE STE C | TULSA | OK |  |  | April-July 2026 | [5 empty] | Julie Atlee | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Wichita, KS, Pittsburg, KS, Tulsa, OK, Bartlesville, OK | Agree |  | H1 Well Staffed | 1 | H1 Well Staffed | 1 | H2 Managing but it's tight | 2 | H2 Managing but it's tight | 2 | IV's, trachs, wound care, prolonged hospitalization | 2 | L1 No Plan for 2026 | 1 | Bartlesville and Tulsa are due for CHAP surveys | 1 | L1 Open to Change Adapt Quickly | 1 | None | 0 | St John's Tulsa- unhappy with not being in network with patient's insurance | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth members monitor referral portals for non Ascension hospitals. | 0 | DCS assist with referral process on the weekends as needed. | 1 | Yes | 1 | When the chart is in scheduling | 0 | discussed on daily referral call or Growth member sends an email to office staff | 0 | No | 2 | Intake member and DCS | 0 | N/A | Jeri Meyer | Oklahoma/Kansas | Tulsa, Bartlesville, Pittsburg, Wichita | Agree |  | L1 Well Staffed |  | L1 Well Staffed |  | M2 Managing but it's tight |  | Ascension hospital & high acuity patient | 1 | Ensocare;Epic Carelink;Other;Intake (NaviHealth/Curaspan);Referral Management (All scripts);AIDA;Watershed;Aidin | NAVI Health, AIDA?, Waterhed, Aidin, We use the equivlent of Ensocare in Oklahoma and Kansas | 4 | We are trying to get Careport in place for our Wesley Hospital account in Kansas, large volume | 0 | None | 0 | L1 No Plan for 2026 |  | There was a "rumor" Oklahoma would move to VBE in 2026 but I have not confirmed with leadership or heard anything affirmative. | 1 | L1 Open to Change Adapt Quickly |  | Schedulers, Referral Coordinators | 2 | The Affordable Care Organization monitors the speed with which we respond to referrals from the hospitals in Oklahoma and they have just rolled out a new ACO in Kansas which I anticipate will do the same. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Other | 1 | Other | 1 | Scheduling | 0 | Referral Coordinators | 1 | Referral Coordinators | 1 | Growth will assist with gathering necessary documents if needed for referrals. | 0 | My PTC supports cross functional tasks by filling in for my CTC and Vice-Versa as well as Growth members stepping in if needed. | 1 | Yes | 1 | Ideally within 20 minutes of accepting a referral, that is the directive. | 1 | Via pending calls and in-the-moment communication with necessary parties. | 0 | No | 2 | Intake | 0 | Our greatest challenge with intake is having to wait on insurance verification which has been a huge challenge due to frustrating our referral sources by not getting a quick answer to them.
54 | A76 | GREENVILLE SC (CC4909) | 1836 W GEORGIA RD | SIMPSONVILLE | SC | [8 empty] | Regina Ervin | Bon Secours Home Care by Compassus - Greenville, SC | None | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H2 Managing but it's tight |  | A patient with high acuity discharging same day(Pleurex patients, IV abx, tube feeds, TPN, etc.) | 1 | H3 Currently on VBE |  | None at this time | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | We have a large Total Ortho Program that we are committed to. We work with this group closely and process referrals quicky to see pateint timely. Some of these patients go home same day of surgery and we try to see patient next day. We are on the hospital committee and have built a strong relationship with this program. We would want to continue to function well for this group. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | RC's complete referral portals and respond to new referrals on the weekend. Readiness calls can be done by growth or scheduling | 1 | RC's complete growth responsibilities on the weekend. There are times DCSs schedules visits on the weekend. | 1 | Yes | 1 | Typically, when growth completes demos | 1 | Discussed during huddle with growth and scheduling to try and get patient seen timely. DCS and EC is on call to discuss barriers. | 0 | No | 2 | RCs & DCSs | 1 | Communication is strong between our team (intake, growth, schedulers, leaders) and we would not want to lose that. | Kimberly Manson | Greenville SC | Greenville SC only | Disagree |  | L1 Well Staffed |  | H3 We're stretched thin |  | L1 Well Staffed |  | Higher acuity patients that would better seen within 24-hour timeframe - his include new oxygen, IV antibiotics, new tube feeds, and TPN patients. | 1 | Intake (NaviHealth/Curaspan);Ensocare;Other;Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Watershed | Referrals are not received directly via all scripts, AIDA, Aidin, or Watershed. | 3 | No - unless faxes will no longer create an ERR within HCHB. There are still referrals that are sent to our branch by fax. | 0 | Humana is one that I am aware of, not sure if there are others. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Referral Coordinators | 1 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCs | 0 | Growth is primary for portals during non-holiday and business hours, Referral Coordinators are responsible for these portals during holiday and non-business hours. Growth typically makes welcome/readiness calls. If they are unable to reach a patient during scheduling, the scheduling team will contact patient. | 1 | None | 0 | Yes | 1 | When Growth has accepted the referral and is calling to verify physician and demographics. This is approximately 24-48 hours prior to admission. | 1 | They are reviewed by Growth and discussed with DCS/ED/scheduling to coordinate care and ensure that the patient is seen within a timely manner and any barriers are discussed as a team. This also happens during huddle calls. | 0 | Yes | 1 | The Referral Coordinators manage referrals and coordinate with the weekend DCS on declining or accepting. They also work with the Sunday scheduler to address any additional needs. | 0 | It would be great to continue to communicate and coordinate care across multiple teams, but ensuring that there is less patient communication via email/Teams would be GREAT.
51 | A74 | CENTERVILLE TN (CC5111) | 135 E SWAN ST | CENTERVILLE | TN | [8 empty] | Brandi Tayloe-Jones | Centerville TN | NA | Strongly Agree |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | Clinical needs and acuity such as IV, wounds, etc. | 1 | M2 2026 GoLive |  | VBE launch in June/July | 1 | M2 Some Coaching and Reinforcement |  | Field Clincians | 0 | None | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | DCS does quite a bit with referral management and no admits | 1 | BOC also performs scheduling functions due to size of program. | 1 | Yes | 1 | After the referral is sent to scheduling. | 1 | The DCS is very active and pushes the referrals through as needed. | 1 | Yes | 1 | There is a regional a scheduling and growth rotation. | 0 | The size of the program can limit functions at times. | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
51 | A75 | NASHVILLE TN (CC5112) | 402 BNA DR STE 320 | NASHVILLE | TN | [8 empty] | Angela Corman | Nashville TN | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | IV antibiotic, Wound Vac, Recent Joint Replacement, LVAD, Cardiac Drip | 1 | M2 2026 GoLive |  | VBE to go live 5/28 currently hiring for increase in referrals | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Referral Coordinators | 1 | Referral Huddles are lead by RC, Scheduler and or ED. Welcome calls are being made by growth, then scheduler/clinicians | 2 | Growth and schedulers work weekend rotations to cover region, ED currently doing large portion of DCS leadership such as payroll etc, all staff under ED. 2 new DCS's have been hired and training all DCS's to take over those responsibilities for clinical team leadership. BOC is cross trained to manage scheduler workflow, Scheduler cross trained to complete some BOC responsibilities. | 1 | Yes | 1 | Growth contacts patient to verify demographics and makes initial welcome call. Clinicians/Scheduler call for readiness. | 1 | Growth informs team of priority admission and intake/scheduler/ED ensure process is completed smoothly | 0 | Yes | 1 | Growth from the region and weekend RCs | 0 | None | Erica Vanlandingham | Region 51 Indiana, TN , MO | Indpls IN Anderson IN Kokomo IN North Vernon IN Bloomington IN Evansville IN Lafayette IN Columbia MO Nashville TN Centerville TN | Agree |  | L1 Well Staffed |  | M2 Managing but it's tight |  | L1 Well Staffed |  | High acuity patients ie: wounds, drains, tubes, etc. VIPs | 1 | Referral Management (All scripts);Epic Carelink;Ensocare;Aidin;Watershed;Intake (NaviHealth/Curaspan);Other;AIDA | AIDA | 6 | NA | 0 | NA | 0 | M2 2026 GoLive |  | VBE TN and IN - June and July 2026 | 1 | H3 Hesitation and Significant Effort |  | None | 0 | Hospitals because they need super quick responses. We lose referrals because we are too slow in responding. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Leads referral huddles: EDs and some use the schedulers. | 1 | NA | 0 | No | 2 | Once the referral is accepted and patient agrees to services. | 0 | Escalated to the ED or DCS | 0 | Yes | 1 | Growth CTCs & PTCs | 0 | We need quick turn around and responses of acceptance for our referrals.
52 | A17 | AUSTIN TX (CC5235) | 9430 RESEARCH BLVD STE II310 | AUSTIN | TX |  |  | May-August |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A16 | BURNET TX (CC5233) | 309 INDUSTRIAL BLVD STE 2 | BURNET | TX |  |  | May-August |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A18 | KYLE TX (CC5234) | 1300 DACY LN STE 170 | KYLE | TX |  |  | Feb-June 2026 |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A56 | SMITHVILLE TX (CC5238) | 150 SETTLEMENT DR STE F2 | BASTROP | TX |  |  | Feb-June 2026 |  |  |  |  | 13 | Jordan Wojnarski | Austin, Burnet, Kyle, Bastrop - Texas | Austin - Parent Burnet Kyle - Parent Bastrop | Disagree |  | H1 Well Staffed |  | H3 We're stretched thin |  | H1 Well Staffed |  | H3 We're stretched thin |  | With VBE - we are prioritizing all Ascension patients | 1 | H3 Currently on VBE |  | We are live in VBE and have the AI launch in April. | 1 | L1 Open to Change Adapt Quickly |  | Everyone is open to change as long as they understand the why | 0 | MAP - we are working through that pain point currently. As issues arise we partner with our growth team to have those conversations with referral source relationships | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | In my market we created a flow chart outlining clinical roles and responsibilities and where the hand-off occurs | 0 | We currently do not have anyone in cross-functional tasks. | 0 | Yes | 1 | When it comes to the scheduling workflow. | 0 | Discussion between growth and PSC scheduler, use of our tools (grid management) | 0 | No | 2 | Intake | 0 | Intake and insurance could use more support, quite frequently SOC get held up for one of those two reasons. Pre-verification on front end for referral sources
52 | A19 | WACO TX (CC5236) | 510 N VALLEY MILLS DR STE 504 | WACO | TX |  |  | April-July 2026 |  |  |  |  | 13 | Wendi Pack | Ascension at Home Waco TX | NA | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Immediate skilled needs such as wound care, IV, or Ortho patients. | 1 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | Scheduling | 1 | NA | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | NA | 0 | NA | 0 | Yes | 1 | Once the chart has been green tagged. | 1 | Growth member lets the DCS and schedulers know | 0 | No | 2 | Intake checks the portals and the DCS on call monitors the emails/ schedules out the admissions. | 0 | NA
54 | A80 | RICHMOND VA (CC5509) | 2603 NINE MILE RD STE 200 | RICHMOND | VA | [8 empty] | Allison Bohn | Bon Securs Home Care by Compassus, Richmond VA | NA | Disagree |  | H3 We're stretched thin |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | IV, LVAD, some surgeries depending on MD, certain wound care | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | Growth | 1 | BSMH Partner creates the most challenges. Expectations to accept all patients are high but in return we are not consistently given first right of refusal if patient has no preference. | 1 | Growth | 0 | Referral Coordinators | 1 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Depending on where the referral is coming from, Growth is also responsible for gathering missing referral documents and patient information | 0 | None | 0 | Yes | 1 | Scheduling | 0 | Communication during huddle, in emails and on scheduling grid | 0 | Yes | 1 | Referral Coordinator | 0 | None | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
54 | A81 | SUFFOLK VA (CC5513) | 7007 HARBOUR VIEW BLVD STE 114 | SUFFOLK | VA | [8 empty] | Erica Dejesus | Bon Secours with Compassus - Suffolk | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
54 | A83 | VIRGINIA BEACH VA (CC5515) | 184 BUSINESS PARK DR STE 100 | VIRGINIA BEACH | VA | [8 empty] | Erica DeJesus | Virginia Beach VA | NA | Strongly Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H3 We're stretched thin |  | H2 Managing but it's tight |  | Ortho , IV, Wound vac | 1 | H3 Currently on VBE |  | N/A | 0 | L1 Open to Change Adapt Quickly |  | Growth | 1 | N/A | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth and ED share accepting/declining referrals. Nonadmits done by RC, ED, Scheduling | 2 | N/A | 0 | Yes | 1 | When scheduling SOC | 0 | Called first | 1 | Yes | 1 | DCS/Growth/Weekend Scheduler | 0 | NA | Heather Detmer | Richard VA Hampton Roads (Suffolk & Virginia Beach) VA | Richmond, VA Suffolk, VA Virginia Beach, VA | Neither Agree or Disagee |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | H3 We're stretched thin |  | Patients that need to be seen next day that are high acuity i.e. IV's, Wounds | 1 | Intake (NaviHealth/Curaspan);Epic Carelink;Referral Management (All scripts);AIDA;Aidin;Ensocare;Watershed;Other | 4-7 are not in my market | 3 | We are in need of EPIC access for Sentara, Riverside, Chesapeake Regional & VCU. We only have Bon Secours EPIC Carelink | 1 | I'm not aware of any at this time | 0 | L1 No Plan for 2026 |  | Not to my knowledge | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | We consistently ask our JV Acute Care for Hampton Roads and Richmond to give us first right of refusal. That typically does not happen and they still blast referrals | 1 | Other | 1 | Other | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral coordinators | 0 | Scheduling | 0 | scheduling | 0 | ED/DCS | 0 | RC's have been helping with Growth Task as I did not have enough growth team members for the number of referrals that come to my branches. I'm currently onboarding and hiring new members for growth. | 1 | Growth has been asked to volunteer for a weekend shift | 1 | No | 2 | The call happens when the patient gets scheduled. | 0 | We communicate in real time to make sure there is no delay in care | 0 | Yes | 1 | RC's and most weekends I have a growth team member for 4 hours per day | 0
61 | B22 | Olympia WA |  | LACEY | WA |  |  | October-December 2026 |  |  |  |  | 15 | [56 empty] | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B26 | Seattle WA |  | TUKWILA | WA |  |  | October 2026 - January 2027 | [5 empty] | Jonelle McGee | Seattle, WA/ King County | NA | Agree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Someone who has wound care is considered urgent, as well as other nursing needs. | 1 | H3 Currently on VBE |  | I am a fairly new ED, but we are focused on really turning things around with metrics, EBITDA, census, productivity, STAR ratings, VBP, etc. We are currently recruiting/hiring for growth and there is major education initiatives and rebuilding going on in our ministry. | 0 | M2 Some Coaching and Reinforcement |  | ED/DCSs | 1 | We do accept charity care and also accept Medicaid and payor sources that make it harder to obtain EBITDA targets. As we are hiring for growth, we need to form community relationships with hospitals outside of our VBEs that DC patients to other areas of our territory that our VBEs do not DC patients to. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | The responsible roles listed in #11 above vary. If the referrals are incomplete and make it to scheduling, then more manpower is needed in the ministry to try and complete the referrals. Ideally, this would all happen at intake prior to it entering the scheduling workflow. | 1 | We still need to hire a weekend scheduler. Right now our weekday schedulers are taking turns covering weekends, which creates problems, as they need to take a comp day off, and we are currently short on schedulers. Our DCS team is supposed to be working hand-in-hand with schedulers to ensure clinician productivity is maximized and clinicians have maximum SOC visits assigned as possible. | 1 | No | 2 | When attempting to schedule the SOC visit | 0 | The DCS and/or ED should be notified | 0 | Yes | 1 | schedulers and administrator on call | 1 | We are eager to incorporate anything that could help with the conversion of referral to SOC | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B21 | Snohomish County WA |  | EVERETT | WA |  |  | April-June 2026 |  |  |  |  | 15 | Mirna Musun | [55 empty] | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B27 | Spokane WA |  | SPOKANE | WA | [8 empty] | Derek Salminen | PAH Spokane WA | N/a | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | Those with high needs. New ostomies, wound vacs, IV ABX, ortho patients. | 1 | H3 Currently on VBE |  | For Spokane we are going to be going through a CHAPs Survey. We are looking to expand and are only limited by field clinicians at this time. | 1 | L1 Open to Change Adapt Quickly |  | None | 0 | For all of our referral sources we have to educate that Spokane is no longer a non-profit entity and we have to look at insurance types before accepting. | 1 | Referral Coordinators | 1 | Referral Coordinators | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | Growth | 1 | N/A | 0 | None | 0 | Yes | 1 | ? | 1 | Operations is notified by the community outreach group. When the referral comes in ED or DCS ensure that the referral is pushed timely through intake and insurance. | 1 | Yes | 1 | We have one dedicated scheduler who works the weekends | 1 | N/A | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
61 | B28 | Walla Walla WA |  | WALLA WALLA | WA |  |  | July-September 2026 |  |  |  |  | 15 | Jessica Dougherty-Burt | [55 empty] | Samuel Snyder | Region 61: All of WA and AK | Olympia, WA Seattle, WA Everett, WA Spokane, WA, Walla Walla, WA Anchorage, AK | Disagree |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | M2 Managing but it's tight |  | Hospitalized patient | 2 | AIDA;Epic Carelink;Intake (NaviHealth/Curaspan);Referral Management (All scripts);Aidin;Ensocare;Watershed;Other | Aidin, Ensocare, Watershed | 4 | Fax | 0 | Kaiser, VA, Charity | 3 | H3 Currently on VBE |  | VBE go-lives will be complete by end of 1st quarter. New CLM starting in Olympia on 4/20. Open AME position . | 0 | L1 Open to Change Adapt Quickly |  | ED/DCS; Growth, Scheduling | 3 | Expectations from ortho surgeons and clinics. | 2 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Steps 1 and 2 are both growth and referral coordinators/intake | 0 | None on the growth/VBE side. I do see the need for the PTC/Air traffic controller role within the VBE to allow our CTA's to be on the floor more. | 0 | Yes | 1 | After intake is complete and sent to scheduling | 0 | Escalated through Teams chats for awareness to ensure specific SOC's are confirmed. | 0 | Yes | 1 | Intake for non-VBE; Growth VBE team for VBE hospitals | 1 | We are in the process of rolling out a patient tracker across WA and AK. It should be fully up and running in all locations by end of April. We have a lot of new staff in our VBE locations who are still learning current state. Many of our VBE hospitals will have launched during first quarter and have gone through a tremendous amount of change.
53 | A12 | RHINELANDER WI (CC5827) | 111 E DAVENPORT ST STE 101 | RHINELANDER | WI | [8 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A64 | CHIPPEWA FALLS WI (CC5835) | 134 W COLUMBIA ST STE 2 | CHIPPEWA FALLS | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A57 | GREEN BAY WI (CC5834) | 480 PILGRIM WAY STE 1250 | ASHWAUBENON | WI | [8 empty] | Brenda Lefeber | Green Bay WI | Neenah WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A09 | MARSHFIELD WI (CC5822) | 303 W UPHAM ST STE 208 | MARSHFIELD | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A14 | MILWAUKEE WI (CC5823) | 135 S 84TH ST STE 150 | MILWAUKEE | WI | [8 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A07 | NEENAH WI (CC5824) | 816 W WINNECONNE AVE | NEENAH | WI | [8 empty] | Brenda Lefeber | Neenah Wi | Green Bay WI | Disagree |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | If the referral comes from our Ascension Hospital partners, Infusion patients, High risk patients | 1 | L1 No Plan for 2026 |  | Leadership change in April with DCS | 1 | M2 Some Coaching and Reinforcement |  | None | 0 | Wound clinics are often challenging to work with in order to decrease the frequency of our visits | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | Ed/DCS | 0 | None | 0 | PTCs do the majority of the behind the scenes work for the referrals as far as getting the information, following up on referrals and sometimes calling patients. HHCCs are out and about meeting with referral sources | 1 | No | 2 | usually withing 24-48 hours of receiving the referral | 1 | Discussed either on huddle or referral Teams chat. | 0 | Yes | 1 | PTC | 1 | Nothing Else | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A10 | PLOVER WI (CC5825) | 1840 POST RD STE 5 | PLOVER | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A15 | RACINE WI (CC5826) | 13200 GLOBE DR STE 228 | MOUNT PLEASANT | WI | [8 empty] | Melissa Steger | Racine | NA | Agree |  | H1 Well Staffed |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H1 Well Staffed |  | Episodic, infusion, ortho, wound | 2 | L1 No Plan for 2026 |  | No | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | No | 0 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | HHCC and CTC make welcome calls. PTC monitors referral portals and gather info as needed. | 1 | If schedulers are unable to contact patients, our PTC will sometimes assist with contacting. | 1 | No | 2 | Once the referral is 'pushed to scheduling' and is in our scheduler's workflow, the scheduler will make the readiness call. The growth team members make their welcome calls prior to this step. | 1 | ED and AME involvement as needed | 0 | Yes | 1 | RC team, AOC, and scheduler | 0 | NA | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A13 | ARBOR VITAE WI (CC5821) | 1571 HIGHWAY 51 N STE C | ARBOR VITAE | WI | [8 empty] | Wendy Freese | Rhinelander WI | Arbor Vitae WI | Disagree |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H2 Managing but it's tight |  | Hospitalized patients with CHF, COPD, multiple comorbidities | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Our competitors, Aspirus, create challenges with referral coordination and offering patients a choice. They often will try to admit our current patients if they are in an Aspirus facility or divert patients to their own HH agency. | 1 | Referral Coordinators | 1 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | NA | 0 | None | 0 | No | 2 | Prior to discharge or at the time of discharge from a facility. Community referrals are contacted once there is an admission date assigned | 1 | The are prioritized and scheduled as soon as possible. They may need to be admitted on call if staffing is a challenge and the care can't wait. | 1 | No | 2 | We get very few weekend referrals and the admin on call is available for review, but we don't process or schedule weekend referrals until Monday. | 1 | It would be great to see more of a clinical review of referrals upfront for appropriateness prior to entering them into HCHB | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A59 | SHEBOYGAN WI (CC5833) | 2124 KOHLER MEMORIAL DR STE 200 | SHEBOYGAN | WI | [8 empty] | Kyle Kumbier | Milwaukee WI | Milwaukee, Sheboygan, Racine | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H1 Well Staffed |  | H3 We're stretched thin |  | Same day or next day needs. Typically IV medications, TPN, Enteral feeds, ortho | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Yes, some of our JV system hospitals and their discharge processes delay and disrupt operations causing loss of productivity due to their inability to commit to discharges when requesting urgent availability | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Growth | 1 | Referral Coordinators | 1 | Scheduling | 0 | Scheduling | 0 | ED/DCS | 0 | Growth also helps make readiness calls when scheduling cannot get ahold of the patient. | 0 | we have a weekend program and weekend scheduling for the Milwaukee license. | 1 | Yes | 1 | If not at bedside, once patient is plotted . | 1 | attempt to make additional space or triage lower acuity patients to later times. | 0 | Yes | 1 | Referral Coordinator | 0 | Having a heads up view from the leadership side on what to expect so we can change manage with significant time before implementation. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A08 | STURGEON BAY WI (CC5828) | 231 KEEL CT | STURGEON BAY | WI | [8 empty] | Marla Wills | AAH w/Compassus Sturgeon Bay | N/A | Neither Agree or Disagee |  | H1 Well Staffed |  | H1 Well Staffed |  | H1 Well Staffed |  | H3 We're stretched thin |  | IV patient, pleurex, CHF/COPD | 1 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | NA | 0 | ED/DCS | 1 | Referral Coordinators | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | ED/DCS | 1 | ED/DCS | 1 | Referral Coordinators | 1 | Ed/DCS | 0 | NA | 0 | NA | 0 | No | 2 | After Intake | 0 | By Ed Direction | 0 | No | 2 | Admin on Call | 1 | N/A | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
53 | A11 | WAUSAU WI (CC5829) | 2600 STEWART AVE STE 160 | WAUSAU | WI | [8 empty] | Calvin Retzki | Central Home Health. Wisconsin | Marshfield, WI Plover, WI Wausau, WI Chippewa Falls, WI | Neither Agree or Disagee |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | H2 Managing but it's tight |  | Ortho, Cardiac, post surgical, hospital discharge to home, wound care | 1 | L1 No Plan for 2026 |  | No | 0 | L1 Open to Change Adapt Quickly |  | None | 0 | Ortho population and turnaround time for outpatient therapy. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | ED/DCS | 0 | None | 0 | None | 0 | Yes | 1 | growth team members will speak to the patient prior to sending the completed referral to scheduling. | 1 | growth identifies high priority admits and alerts the team on the referral email and also updates on the daily huddle. The patients are flagged priority on the scheduling grid. | 0 | No | 2 | ACs work the weekends to move patient referrals through the system, the administrator on call schedules starts | 1 | We have 4 branches that are combined under 1 provider number. We have a main referral email that routes in the referrals and then splits them into the branch they belong to with growth, intake, and branch level involvement. Growth will reach out to the ED for referral reviews and acceptance of patients when concerns arise. I would like an overview of the intake process being rolled out prior to going live. | Kelly Swartz | Wisconsin, New Mexico, Montana | All WI | Agree |  | M2 Managing but it's tight |  | H3 We're stretched thin |  | M2 Managing but it's tight |  | acuity, ortho surgery, new COPD/CHF dx with hospital discharge, mostly medical necessity | 1 | Epic Carelink;Intake (NaviHealth/Curaspan);Watershed;Ensocare;Referral Management (All scripts);AIDA;Aidin;Other | AIDA and Aidin | 6 | Tango, Repisodic | 2 | Unknown | 0 | L1 No Plan for 2026 |  | None | 0 | M2 Some Coaching and Reinforcement |  | None | 0 | Our Ascension patients are a priority and if we have delays there can be issues and pressure. | 1 | Growth | 0 | Growth | 0 | Referral Coordinators | 0 | Referral Coordinators | 0 | Scheduling | 1 | Scheduling | 0 | Growth | 1 | Growth | 1 | Lead referral huddles is usually Growth some programs its the ED or DCS and rare occasion scheduler | 0 | Weekend AOC at times moves patients to the schedule in some markets. | 1 | Yes | 1 | We push for the welcome call to be ASAP to secure the admission the readiness call is when we are ready to bring them on. | 1 | As a team the growth team collaborates with operations and we work together to get the patient scheduled. | 0 | No | 2 | referrals come through intake | 0 | We rely heavily on our PTC's to assist growth with clerical tasks to keep the referral flow moving in order to exceed our budget. We work closely with operations when we have challenges with conversion to identify barriers and get a resolution quickly in place.
DeNovos
Denver CO
Colorado Springs
Note on AD1: Align with pilot high acuity definition = 1 Different from pilot high acuity =2
Note on AH1: 1 for each item listed
Note on AL1: Count
Note on AP1: Growth = 0, anything else = 1
Note on AR1: Growth = 0, anything else = 1
Note on AT1: RC=0, Any other role =1
Note on AV1: RC=0, any other role =1
Note on AZ1: Scheduler = 0, anything else =1
Note on BD1: ED/DCS=0, anything else = 1
Note on BF1: 1 point for each item listed if outside of standard process
Note on BH1: 1 point for each item listed
Note on BJ1: YES = 1 NO =2
Note on BL1: 1 point for anything outside of standard process; one point if no process
Note on BN1: 1 point for any process that outside of pilot process
Note on BP1: Yes = 1, No = 2
Note on BR1: Intake/Growth = 0, any other role = 1
Note on CG1: 1 = Aligns with pilot high acuity definition 2 = Different than pilot high acuity definition
Note on CJ1: Total portal in #6 (8) minus portals not used in 7
Note on CL1: Count of additonal portals used
Note on CN1: Count of payors listed requiring extra steps
Note on CR1: 1 point for each initiative listed
Note on CV1: Count
Note on CX1: 1 point for each challenge listed
Note on CZ1: If Growth = 0, anything else = 1
Note on DB1: If growth = 0, any other role =1
Note on DD1: If RC = 0, any other role = 1
Note on DF1: RC = 0, any other = 1
Note on DH1: RC=0, any other = 1
Note on DJ1: Scheduling = 0, any other = 1
Note on DL1: Scheduling = 0, other = 1
Note on DN1: ED/DCS = 0, other = 1
Note on DP1: 1 point for each item listed if outside standard process of DCS/ED/AME leading huddle
Note on DR1: 1 point for each cross functional role listed
Note on DT1: YES = 1 NO = 2
Note on DV1: 1 point for anything outside of the standard process - 1 point for no process
Note on DX1: 1 point for anyting deviated from pilot processes
Note on DZ1: Yes = 1 No = 2
Note on EB1: Intake or Growth = 0, any other roles or no roles = 1

## List (hidden)
Phase | Overall Categories
Discovery | Governance | Governance
Pre-Pilot Development | Project Team/OpEx | Project Team
UAT | Team Member Experience Plan + Recognition | Org Communication
Active Pilot | Training, Materials & Ambassadors | Team Member Experience Plan + Recognition
Enterprise Rollout | Measurement - Analytics & Feedback | Training
Solution Extensions | Shared Services | Analytics & Engagement
Ongoing Management | Workforce | IT
| Communications | Contracting
Workforce
Status
Not Started
Predecessor Required
In Process
Need Assist
Complete
At Risk
Past Due
On Hold
Not Applicable